## Sheet1
FIELDS Near-Term Activites, J. Macri
from date | to date | item | category | from | to | responsible | status/ note
2011-09-08 |  | MIP of FM1 Gun boards at IWF | MIP | SwRI |  | SwRI | done
2011-09-09 |  | FRR: EDI beam gen system | FRR | UNH |  | Turco | done
2011-09-11 |  | FM1 AEB | DEL | UNH | KTH | King | done
2011-09-12 |  | FM1 A-BEB bench test | TST | KTH |  | Olsson | done
2011-09-12 |  | Receipt of EM Gun and GDE | DEL | UNH | IWF | Williams | done
2011-09-12 |  | FM1 SDP Probe assemblies | DEL | Oulu | KTH | Lindqvist | done
2011-09-12 |  | TRR | TRR | UCLA |  | Strangeway | done
2011-09-13 | 2011-09-14 | FM2 FG Sensor vibe | TST | UCLA | ` | Strangeway | done
2011-09-14 | 2011-09-16 | Acceptance test FM1 DSP boards (2) | TST | LASP | UNH | Rau | done
2011-09-14 | 2011-10-04 | Assembly of FM1 CEB (box and electronics) | ASSY | UNH |  | Nolin | done
2011-09-15 | 2011-09-19 | FM1 AEB testing (IRFU) | TST | IRFU |  | King | done
2011-09-15 |  | FRR: CEB assembly | FRR | UNH |  | Turco | done
2011-09-16 | 2011-09-28 | FM2 FG Sensors thermal and bakeout | TST | UCLA |  | Strangeway | done
2011-09-16 |  | FM1-1 HV Filament Board (ship) | DEL | UNH | IWF | Williams | done
2011-09-16 |  | FM1 ADP Ext. Booms (EIDP review) | DEL | ATK | LASP | Westfall | done
2011-09-16 |  | EDI Gun CDR follow-up (9 a.m. EDT) | CDR | UNH |  | Macri | done
2011-09-19 | 2011-09-21 | FM1-1 beam generation system test | TST | UNH |  | Singer | done
2011-09-20 | 2011-09-23 | Parylene coating of FM1 AEB boards (Sweden) | ASSY | KTH |  | King | done
2011-09-20 |  | FRR: EDI Sensor assembly | FRR | UNH |  | Turco | done
2011-09-20 |  | LVPS, AFG, DFG parylene coating complete | MILE | UNH |  | Turco | done
2011-09-21 | 2011-09-26 | FM1 S-BEB testing (IRFU) | TST | IRFU |  | King | done
2011-09-22 |  | FM1 S-BEB testing (IRFU) | TRR |  |  | King | done
2011-09-22 12:00 | 2011-09-23 | CDPU SW acceptance test (Needell) | TST | UNH |  | Needell | done
2011-09-23 |  | FM1-1 HV Filament Board (received) | DEL | UNH | IWF | Steller | done
2011-09-23 11:30 | 2011-09-23 15:00 | PER: FM2 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-09-26 | 2011-09-27 | MMS SWT | MTG | UNH |  | Torbert | done
2011-09-26 |  | FM1 AEB | DEL | KTH | UNH | Lindqvist | done
2011-09-26 |  | Current generator (GSE) | DEL | IWF | UNH | Magnes | done
2011-09-26 12:00 | 2011-09-27 | EM FIT testing at UNH | TST | UNH |  | Dors | done
2011-09-28 | 2011-10-03 | FM1 S-BEB parylene coating | ASSY | KTH |  | King | done
2011-09-28 |  | FM1 AEB receiving inspection (morning) |  | UNH |  | Turco | done
2011-09-28 |  | FRR for mag harnesses | FRR | UNH |  | Turco | done
2011-09-28 |  | Reynolds HV cable received at IWF | DEL | VEND | IWF | Steller | done
2011-09-28 |  | PRODEX/ESA approval of GDE circuit modification | DES | IWF |  | Steller | done
2011-09-28 |  | MMS SWG (PIs, Wed morning) | MTG | UNH |  | Torbert | done
2011-09-28 13:00 | 2011-09-29 | FIELDS Science Data Processing Working Group | MTG | UNH |  | Chutter | done
2011-09-29 |  | FM1-1 beam generation system | DEL | UNH | IWF | Singer | done
2011-09-29 |  | FM2 DFG Sensor | DEL | UCLA | UNH | Strangeway | done
2011-09-29 |  | FM1-2 HV Filament Board | DEL | UNH | IWF | Turco | done
2011-09-30 | 2011-10-03 | FM1 SDP Probes TV testing | TST | KTH |  | Lindqvist | done
2011-09-30 |  | FM2 DFG receiving inspection and EIDP review | EIDP | UNH |  | Turco | done
2011-09-30 |  | FM4 & FS DFG boards | DEL | UNH | IWF | Williams | done
2011-09-30 |  | FM2 DFG Sensor | DEL | UNH | IWF | Williams | done
2011-10-03 | 2011-10-04 | FM1 S-BEB parylene (Sweden) | ASSY | KTH |  | King | done
2011-10-03 | 2011-10-05 | FM1 SCM Sensor and Preamp | DEL/TST | LPP | UNH | Leroy | done
2011-10-03 |  | ADP Simulator | DEL | LASP | UNH | Westfall | done
2011-10-03 |  | Connector brackets for DSPs 4-7 | DEL | UNH | LASP | Nolin | done
2011-10-03 |  | EIDP Review: FM1 SCM | EIDP |  |  | Macri | done
2011-10-06 | 2011-10-21 | Final definition: FM motors & harnesses | MILE | UNH |  | King | done
2011-10-06 |  | FM1 CEB FFT | TST | UNH |  | Rau | done
2011-10-06 |  | FM1 SDP Probes (4) | DEL | KTH | UNH | King | done
2011-10-06 |  | FM1 S-BEB | DEL | KTH | UNH | King | done
2011-10-07 |  | EM4 SCM Sensor and BB Preamp (receive @ UNH) | DEL | LPP | UNH | Williams | done
2011-10-07 |  | FM1 AEB functional test | TST | UNH |  | Rau | done
2011-10-07 |  | TRR: FM1 CEB (AEB & SCM) EMI/EMC test | TRR | UNH |  | Myers | done
2011-10-10 | 2011-10-27 | TV chamber characterization for outgassing certification measurements | TST | UNH |  | Turco | done
2011-10-11 | 2011-10-20 | FM1 CEB (AEB & SCM) EMI/EMC testing @ Retlif | TST | UNH |  | Dors | done
2011-10-14 | 2011-10-21 | Review TV chamber data and readinesss for outgassing certificaiton with Jack Sanders | TRR | UNH |  | Turco | done
2011-10-14 |  | Distribute materials for EDI SW TRR | TRR | UNH |  | Briggs | done
2011-10-17 | 2011-10-18 | FM1-1 EDI Gun inspection (Granoff, Macri) | INS | UNH | IWF | Macri | done
2011-10-17 | 2011-11-02 | FM1 SCM harness bakeout and certification | TST | UNH |  | Turco | done
2011-10-17 |  | Connector brackets for DSPs 8-9 | DEL | UNH | LASP | Nolin | done
2011-10-24 |  | FG nulling coil GSE (1st of 4) | DEL | UCLA | UNH | Strangeway | done
2011-10-24 |  | FM1 CEB retest planning (DSP FPGA change) | FRB | SwRI |  | Black | done
2011-10-25 | 2011-10-28 | FM1 SDP preamp/cable rework, fine wire assy and boom wire marking @ UNH | ASSY | LASP |  | Vermeer | done
2011-10-25 |  | CDPU SW acceptance test (post-test review) | REV | UNH |  | Heirtzler | done
2011-10-26 |  | EDI FSW TRR | TRR | UNH |  | Briggs | done
2011-10-27 | 2011-11-29 | Plan for SDP deployments on S/C decks to GSFC | DOC | UNH | GSFC | Macri | done
2011-10-27 |  | ADP FM1 booms (SN01, SN02) delivery to LASP | DEL | ATK | LASP | Westfall | done
2011-10-28 |  | FM1 AEB (plus 2 FM1 DSP boards and 1 EM A-BEB) & ADP simulator | DEL | UNH | LASP | Rau | done
2011-10-29 |  | FM1-2 EDI beam generation system | DEL | UNH | IWF | Singer | done
2011-10-31 | 2011-11-02 | CIDP Road Show at GSFC | TST | UNH |  | Needell | done
2011-10-31 |  | FIELDS Simulator (received at SwRI) | DEL | UNH | SwRI | Chutter | done
2011-10-31 |  | EM4 SCM Sensor deliver to GSFC for tests with qual boom | DEL | UNH | GSFC | Rau | done
2011-11-02 |  | EM4 SCM Sensor installation on QM mag boom (GSFC) | INT | GSFC |  | Sturm | done
2011-11-02 |  | ASPOC PER | PER | IIRT |  |  | done
2011-11-03 | 2011-11-09 | FM1 SCM Sensor & Preamp bakeout & cert. | TST | UNH |  | Turco | done
2011-11-04 |  | Return EM1 AFG board to UNH | DEL | UCLA |  | Strangeway | done
2011-11-07 | 2011-11-30 | FM2 A-BEB PWAs | ASSY | Iowa | UNH | Turco | done
2011-11-09 |  | PER: FM ship set 3 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-11-10 |  | EDI FSW Acceptance test | TST | UNH |  | Briggs | done
2011-11-10 |  | TRR: FM1 SDP EMI/EMC testing (1 deployer) | TRR | UNH |  | Dors | done
2011-11-10 |  | TRR: FM1-1 EDI Sensor thermal and vacuum tests | TRR | UNH |  | Macri | done
2011-11-14 |  | FM1-1 SDP FFT | TST | UNH |  | King | done
2011-11-14 |  | Change soldered FPGA on EM DSP board | ASSY | LASP |  | Westfall | done
2011-11-15 | 2011-11-16 | FM1-1 EDI Sensor thermal test | ETST | UNH |  | Singer | done
2011-11-15 | 2011-11-18 | FM1 SDP EMI/EMC testing (1 deployer) | ETST | UNH |  | Dors | done
2011-11-15 |  | PER: FM1 SDP | PER | UNH |  | Myers | done
2011-11-17 | 2011-12-02 | Review EM AEB testing at LASP and plan forward | REV |  |  | Macri | done
2011-11-17 | 2011-12-07 | SDP preamp thermal test plan prep and review |  |  |  | Nolin | done
2011-11-17 |  | DSP & CDPU FPGAs (pre-burn review) | REV |  |  | Macri | done
2011-11-18 |  | Beam Gen Syst. Anode and focus weldments (pre- plating, receipt @ UNH) | DEL | VEND | UNH | Nolin | done. Rejected.
2011-11-22 |  | FM2 LVPS PWA | DEL | SYN | UNH | Turco | done
2011-11-22 |  | TRR: FM1 SDP vibration (1 unit) | TRR |  |  | Macri | done
2011-11-28 | 2011-12-02 | FM3 DFG Sensor capacitor installation | ASSY | UCLA |  | Strangeway | done
2011-11-29 | 2011-12-01 | FM S/N2 EDI Sensor thermal test | ETST | UNH |  | Singer | done
2011-11-30 | 2011-12-02 | FM1 SDP vibration (1 unit) | ETST | UNH |  | Granoff | done
2011-11-30 |  | FM2 A-BEB PWAs | DEL | Iowa | UNH |  | done
2011-11-30 |  | PER: FM ship set 4 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-12-02 | 2011-12-05 | FM S/N3-4 CDPU thermal tests | ETST | UNH |  | Bodet | done
2011-12-02 |  | FM1 AEB return to UNH for repair | DEL | LASP | UNH | King | done
2011-12-03 |  | FM2 LVPS PWA | DEL | UNH | KTH | Turco | done
2011-12-05 |  | FM3 LVPS PWA | DEL | SYN | UNH | Turco | done
2011-12-05 |  | Burn 2nd FPGA for FM1 DSP | ASSY | UNH | LASP | Summers | done
2011-12-07 |  | Beam Gen Syst. weldments (in process inspection) Done for one set. Okay. Go-ahead for remainder given to vendor | MILE | UNH |  | Salwen | done
2011-12-08 | 2011-12-09 | FM SDP preamp TV survival cycle (3 units, S/N2-4) | ETST | UNH |  | Nolin | done
2011-12-08 |  | SDP preamp thermal model and test plan review | REV |  |  | Macri | done
2011-12-12 | 2011-12-16 | CDPU S/Ns 3&4 parylene coating | ASSY | SCS |  | Turco | done
2011-12-12 | 2011-12-16 | EDI Gun Support Collar wiring at UNH. | ASSY | Iowa | UNH |  | done
2011-12-14 | 2011-12-16 | SOC peer review and TIM | REV |  |  | Needell | done
2011-12-14 |  | FM1 AEBs (modified) to KTH for test | DEL | UNH | KTH | King | done
2011-12-14 |  | FM3 LVPS PWA | DEL | UNH | KTH | King | done
2011-12-20 |  | Mount thermal HW on FM1 CEB | ASSY | UNH |  | Nolin | done
2011-12-20 |  | FM1 AEB (tested) return to UNH | DEL | KTH | UNH | King | done
2011-12-20 |  | FM2 LVPS | DEL | KTH | UNH | King | done
2011-12-21 |  | FM1 GDE | DEL | RUAG | IWF | Steller | done
2012-01-03 |  | FM1 AEB (tested) return to LASP | DEL | UNH | LASP | King | done
2012-01-04 |  | FM4&FS LVPS PWAs | DEL | SYN | UNH | Turco | done
2012-01-05 | 2012-01-06 | SDP 2 - 4 Preamp TV Retest | ETST | UNH |  |  | done
2012-01-05 | 2012-01-18 | Syntech FM2 set SBEB assembly | ASSY | SYN |  | Turco | done
2012-01-05 |  | PER: FM3 FG Sensors (Webex) | PER | UCLA |  | Strangeway | done
2012-01-06 |  | FM1 DSP boards (return to UNH) | DEL | LASP | UNH | Wesfall | done
2012-01-09 |  | TRR: EQM SDP Vibration | TRR | UNH |  | Macri | done
2012-01-09 |  | PER: FM2/3 SCM (WebEx) | PER | LPP |  | Leroy | done
2012-01-10 | 2012-01-11 | IS SIR | SIR |  |  |  | done
2012-01-10 | 2012-01-11 | EQM SDP Vibe | ETST | UNH |  | Granoff | done
2012-01-10 |  | FM1 GDE secondary ground isolation problem | PROB | RUAG | IWF | Steller | done
2012-01-10 |  | TRR: FG3 vibration and thermal | TRR |  |  |  | done
2012-01-11 |  | Discussion of SDP damping test | REV | GSFC |  | Frost | done
2012-01-13 |  | TRR: FM SCM sets 2&3 environmental tests | TRR |  |  | Macri | done
2012-01-16 | 2012-02-24 | FM2 set SCM environmental tests | ETST | LPP |  | Leroy | done
2012-01-17 | 2012-01-20 | SDP S/N 1 and EQM vibration | ETST | UNH |  |  | done
2012-01-17 | 2012-01-20 | SDP FM SN2-4 Preamp/Sphere integration | ASSY | UNH |  | King | done
2012-01-17 |  | FM2 set SDP Preamps and 5-8 doors | DEL | LASP | UNH | Westfall | done
2012-01-17 |  | Prep FM2 set SDP preamps for TV test | ASSY |  |  | King | done
2012-01-18 | 2012-01-20 | TV test FM S/N5-8 SDP Preamps | ETST | UNH |  | King | done
2012-01-18 |  | EDI beam gen system weldments (remaining anode and focus units) | DEL | VEND | UNH | Salwen | done
2012-01-18 |  | PER: FM1 CEB (@UNH) | PER | UNH |  | Myers | done
2012-01-20 |  | FM2 S-BEB PWA | DEL | SYN | UNH | Turco | done
2012-01-20 |  | TRR: FM1 CEB vibration | TRR |  |  | Macri | done
2012-01-23 |  | PER: FM1 pair Receiving Elements (@LASP) | PER | LASP |  | Westfall | done
2012-01-25 | 2012-01-27 | FM1 CEB vibration | ETST | UNH |  | Nolin | done
2012-01-30 | 2012-03-15 | FM3 set SCM vibration | ETST | LPP |  | Leroy | Done.
2012-01-30 | 2012-03-15 | FM3 set SCM vibe | ETST | LPP |  | Leroy | done
2012-01-30 |  | TRR: FM1 set Receiving Elements vibration | TRR | LASP |  | Westfall | done
2012-01-31 |  | PER: FM1 AEB (WebEx) | PER | LASP |  | Westfall | done
2012-02-01 | 2012-02-03 | Baseline outgassing measurements for FM1 CEB | ETST | UNH |  | Turco | done
2012-02-01 | 2012-02-03 | FM1 set Receiving Elements vibration | ETST | LASP |  | Westfall | done
2012-02-03 |  | SDP deployment problem (update for project) | MTG | UNH |  | Macri | done
2012-02-03 |  | TRR: FM1 AEB vibration testing | TRR | LASP |  | Macri | done
2012-02-03 09:00 |  | TRR: FM1 CEB TV | TRR |  |  | Macri | done
2012-02-06 |  | FM1 AEB vibration testing | ETST | LASP |  | Westfall | done
2012-02-07 |  | FM3 DFG Sensor. Return 2nd tuning harness to UNH. | DEL | UCLA | UNH | Rowe | Done.
2012-02-09 | 2012-02-10 | SDP vibration investigation | ETST | UNH |  | Granoff | done
2012-02-10 |  | TRR: FM1 Receiving Element TV testing | TRR | LASP |  | Westfall | done
2012-02-11 | 2012-02-16 | Myers at IWF (schedule work) |  | UNH |  |  | done
2012-02-11 |  | FM3 DFG Sensor | DEL | UNH | IWF | Myers | done
2012-02-13 | 2012-03-01 | FM1 Receiving Element TV testing | ETST | LASP |  | Westfall | Done.
2012-02-17 | 2012-02-24 | FM2 SCM Preamp TV | ETST | LPP |  | Leroy | done
2012-03-23 |  | New over-shield material for SCM harnesses | DEL | UNH | LPP | Turco | done
2012-03-14 |  | FRR: EDI GDU (internal review) | FRR | UNH |  | Turco | Done.
2012-03-16 | 2012-03-23 | Repeat SCM Preamp S/N4 (SCM SS#3) TV test | ETST | LPP |  | Leroy | done
2012-03-19 |  | FM2 CEB housing ready |  |  |  | Nolin | Done.
2012-03-20 | 2012-03-21 | MMS SWT (San Antonio) | MTG |  |  | Torbert | Done.
2012-03-20 |  | EM4 SCM Sensor delivery to LPP. Thermal test for verification following QM boom deploy (shock) test | DEL | UNH | LPP | Williams | done
2012-03-20 |  | SDP ship set #4 boom cables (and spares?) | DEL | UNH | LASP | Beckman | done
2012-03-22 |  | MMS SWG |  |  |  | Torbert | Done.
2012-03-22 15:00 |  | FIELDS data processing meeting (San Antonio) | MTG |  |  | Torbert | done
2012-03-22 |  | FM2 CEB housing assembly complete | DEL | UNH | UNH | Nolin | done
2012-03-23 |  | FM2 AEB | DEL | UNH | LASP | Rau | done
2012-03-26 | 2012-03-28 | FIELDS FM1 FIT (part 1, magnetometer timing) testing. FM1 CEB, AFG, DFG, SCM | TST | UNH |  | Dors | underway
2012-03-26 | 2012-04-20 | FM1 FIELDS I&T: CPT, FIT, procedure and script development | TST | UNH |  | Rau | FM1 CEB, AEB (and ADP Simulator), AFG, DFG, SCM; SDPs: (FIT BEBs w/ motors and HOP load sims (more if/when available); IVM GDEs (2) (more if/when available)
2012-03-26 |  | 2nd Nulling Coil GSE | DEL | UCLA | UNH | Strangeway | Strangeway: Planning to deliver with FM2 AFG delivery.
2012-03-27 | 2012-03-30 | SDP prototype (SN1 w/ RWC) vibe | ETST | UNH |  | Granoff
2012-03-29 |  | S/N3 & 4 EDI Beam Gen Syst | DEL | UNH | IWF | Valavanoglou | Arrived with resitors?
2012-03-29 |  | FM3 set A-BEB PWA | DEL | SYN | UNH | Turco | Done.
2012-03-26 |  | FM2 AFG Delivery and acceptance test. | DEL | UCLA | UNH | Strangeway | done
2012-04-02 | 2012-04-06 | FIELDS FM1 FIT testing (double probe timing). FM1: CEB, AEB. EM: SDPs | TST | UNH |  | Dors | status?
2012-04-03 | 2012-04-03 | Integrate first set EDI Optics (S/N2) with Sensor (S/N1) at UNH | ASSY | Iowa | UNH | Dvorsky | Done. One NCR (wiring paperwork error).
2012-03-27 |  | FM2 DFG delivery and acceptance test | DEL | IWF | UNH | Valavanoglou | done
2012-04-04 |  | FM2 BPM ready for FM2 CEB | DEL | UNH |  | Bodet | MIP and coating complete. Testing underway.
2012-03-27 | 2012-03-28 | SwRI PMs at UNH (schedule review) | MTG | UNH |  | Macri | done
2012-04-05 |  | EM4 SCM Sensor verification following QM boom deploy (shock) test | ETST | LPP |  | Leroy | status?
2012-03-26 |  | TRR: FIELDS FM1 FIT test part 1 (magnetometer timing) | TRR | UNH |  | Macri | Done.
2012-04-09 | 2012-04-13 | FIELDS FM1 FIT testing (interference, part-1) FM1: CEB, AFG, DFG, SCM, AEB EM: Rest | TST | UNH |  | Dors | Date is Macri's WAG
2012-04-09 |  | Return SN1 EDI Gun BGS to UNH for filament swap | DEL | IWF | UNH | Steller | With delivery of FM SN2 Gun and GDE
2012-04-09 |  | FM3 AEB | DEL | UNH | KTH | Turco | Date? Date is 1 week after expected receipt from Syntech.
2012-04-10 |  | Peer Review: SDP RWC mechanism | REV | UNH |  | Granoff | After prototype vibe. Before GDU integration.
2012-04-11 | 2012-04-17 | Parylene coating of FM2 CDPU A&B, AFG, DFG, EDI Controller | ASSY | UNH |  | Turco | Date is 4 Apr Turco estimate
2012-04-11 |  | FM2 LVPS ready for CEB I&T | TST | UNH |  | Troop | Incoming test with GSE at UNH
2012-04-12 | 2012-04-18 | FM SN1 GDU integration | ASSY | UNH |  | Vaith | IWF and Iowa support at UNH
2012-04-12 | ? | FM S/N2 EDI Gun & GDE (first unit) | DEL | IWF | UNH | Steller | Confirm date with Steller. Duration of IWF support?
2012-04-13 |  | FM1 and FM2 ship sets ADP booms (S/Ns 1-4) | DEL | ATK | LASP |  | Date is from Tucker, 3 Apr.
2012-04-13 |  | FM3 set S-BEB PWA | DEL | SYN | UNH | Turco | Date is Macri's WAG. Kits delivered 12 Mar to Syntech
2012-04-15 |  | SDP TV test procedure for review. | REV |  |  | Beckman | Needell request. dual deployment
2012-04-15 |  | ADP Simulator and test harness for IS | DEL | LASP | UNH |  | tie with FIT-2
2012-04-16 | 2012-04-18 | FM SN1 GDU integration (Iowa support) | ASSY | Iowa |  | Bounds | Confirm dates with Vaith
2012-04-16 |  | FM SDP Doors F/Ms 9-16 | DEL | LASP | UNH |  | Hold at LASP until SDP FRB approves plan forward. Approval looking likely.
2012-04-16 |  | Remaining Gun DFL2 PWBs | DEL | UNH | IWF | Turco | Date is Macri's WAG. Need date at IWF? 3 of 4 coupons passed.
2012-04-17 |  | FM2 CDPU (2) delivery to CEB | DEL | UNH | UNH | Turco | Awaiting parylene
2012-04-17 |  | FM2 EDI Contrtoller Delivery to CEB | DEL | UNH | UNH | Turco | Awaiting parylene
2012-04-17 |  | FM2 AFG Delivery to CEB | DEL | UNH | UNH | Turco | Awaiting parylene
2012-04-17 |  | FM2 DFG Delivery to CEB | DEL | UNH | UNH | Turco | Awaiting parylene
2012-04-20 | 2012-04-25 | FM 2 SCM harness outgasing cert (TQCM). Requires cleaning and rework with new over-shield material | ETST | LPP |  | Leroy | Confirm dates with LPP. Over-shield material received at LPP 03 Apr 2012.
2012-04-21 | 2012-04-23 | FIELDS FM1 FIT testing (interference, part-2) FM1: SDPs EM: Rest | TST | UNH |  | Dors | Date is Macri's WAG
2012-04-23 |  | SDP ship set 3 preamp/cable assemblies (S/Ns 9-12) | DEL | LASP | UNH | Westfall | Date is Vermeer estimate (04 Apr). TV survival test at UNH is subsequent task. Vermeer support at UNH?
2012-04-25 | ? | FM1 EDI GDU EMI/EMC Testing (1 unit) | ETST |  |  | Dors | Date is from Tyler 3 Apr.
2012-04-25 |  | Goddard network setup for FIELDS testing | TST |  |  | Needell | Coordinate with Pope. Combine trip with commissioning meeting?
2012-04-26 |  | FM2 DSP (2) Delivery | DEL | LASP | UNH | Westfall | Date is from LASP Feb schedule
2012-04-30 | 2012-05-02 | TV survival test: SDP ship set 3 preamp/cable assemblies (S/Ns 9-12). | ETST | UNH |  | King | Dates? starts 1 week after delivery to UNH
2012-04-30 | 2012-05-04 | FM1 SCM harness bakeout and certification (new overshield). | ETST | UNH |  | Turco
2012-04-30 |  | PER: FM2 set AEB and Receiving Elements | PER |  |  |  | Date is from Westfall, 27 Mar.
2012-04-30 |  | FM4 DFG Sensor capacitor installation | ASSY | IWF |  | Strangeway | Coordinate with IWF and UCLA
2012-05-01 |  | SDP thermal test plan distribution | RFA |  |  | King | RFA from PER. Draft distributed. Needs vetting before SDP delta PER
2012-05-01 |  | PER: FM1 EDI GDU | PER
2012-05-03 | 2012-07-20 | IS#1 Component I&T | TST |  |  |  | Date from IS I&T schedule
2012-05-04 | ? | FM1 EDI GDU Vibration Testing (1 unit) | ETST |  |  | Granoff | Date is from Tyler 3 Apr.
2012-05-07 | 2012-05-18 | SDP damping test at GSFC | TST | GSFC |  | Frost
2012-05-07 |  | FM2 CEB test start |  |  |  |  | Follows delivery of last boards (DSP)
2012-05-11 |  | Delta PER: SDP S/Ns 3&4 | PER
2012-05-15 | 2012-04-27 | IS Delta SIR | SIR |  |  |  | Date from Araujo. Must do EDI PER before this.
2012-05-15 | 2012-05-18 | FIELDS FM1 FIT testing (double probe timing). FM1: SDPs. EM: CEB | TST | UNH |  | Dors | Date is Macri's WAG
2012-05-15 |  | FM SDP S/N3-4 EMI/EMC tests (@UNH) | ETST | UNH |  | Dors | Date is Macri's WAG
2012-05-17 | ? | FM SDP SN3-4 EMI/EMC Testing | ETST |  |  | Dors | Date is from Tyler 3 Apr.
2012-05-18 |  | FM2 AEB (or EM AEB) | DEL | LASP | UNH | Westfall | To support completion of FM1 FIT testing prior to and following partial delivery of FM1 FIELDS to IS. LASP/UNH holding June delivery date for FM2 rec/del list
2012-05-20 |  | TRR: FM SDP TV (2 units, S/Ns3-4) | TRR | UNH |  | Macri | Delayed. Pending SDP FRB approval of plan forward
2012-05-21 | 2012-05-23 | FIELDS FM1 FIT testing (EDI timing). FM1: EDI-GDUs EM: CEB | TST | UNH |  | Dors | Date is Macri's WAG
2012-05-21 |  | SDP FM SN 3-4 I&T complete (avail. For FIT w/ FM1 CEB |  |  |  |  | prior to SDP vibe and FM1 CEB deliv. to IS
2012-05-22 | 2012-05-23 | PSR: FM1 FIELDS (partial) delivery to IS (includes all except EDI & SDP) | PSR | UNH |  | Myers
2012-05-23 | 2012-05-24 | FIELDS FM1 FIT testing (interference, part-3) FM1: GDUs. EM: Rest | TST | UNH |  | Dors | Date is Macri's WAG
2012-05-23 |  | Fluxgate harness deliveries | DEL | UCLA | UNH
2012-05-24 | ? | FM SDP SN3-4 Vibration Testing | ETST |  |  | Granoff | Date is from Tyler 3 Apr.
2012-05-24 |  | FM2 SCM Delivery | DEL | LPP | UNH | Leroy | Date is from Dominique via Laurent (16 Feb)
2012-05-25 | ? | FM1 EDI GDU TV Testing (2 units?) | ETST |  |  | Vaith | Date is from Tyler 3 Apr.
2012-05-30 |  | FM1 FIELDS (partial) Delivery to IS. FM1 CEB, DFG, AFG and SCM and Harnesses, SDPs: (FIT BEBs w/ motors and HOP load sims) ; ADP simulator | DEL | UNH |  |  | Date follows Mem. Day holiday. Deliver more if available.
2012-06-01 |  | QM ADP Boom abd Receiving Element delivery to GSFC | DEL | LASP | GSFC | Westfall | Date from Borelli received 30 Mar. Install 6/18; 1st motion deployment 7/24
2012-06-05 | ? | FM SDP SN3-4 TV Testing | ETST |  |  | King | Date is from Tyler 3 Apr.
2012-06-30 | 2012-07-09 | Receive/Inspect EDI GDU at IS (GSFC) | TST |  |  |  | Date from IS I&T schedule
2012-07-05 |  | Assemble and test spare SDP doors (SNs 17-18)? | ASSY | LASP |  | Macri | Placeholder. No decision yet. Need date for at least 1 door: Nov 2012.
2012-07-09 | 2012-07-13 | SDP (1-unit) calibration in Faraday cage at LASP | TST | UNH | LASP | King | Ergun: Goal is directly comparable ADP and SDP calibrations. Can be FM or fully representative EM. Spring or summer 2012.
2012-07-13 | 2012-07-19 | Receive/Inspect SDP at IS (GSFC) | TST |  |  |  | Date from IS I&T schedule
2012-07-20 | 2012-08-10 | IS#1 integrated testing | TST |  |  |  | Date from IS I&T schedule
2012-08-01 | 2012-08-02 | Mission SIR | SIR |  |  |  | delayed
2012-08-10 |  | IS#1 PSR | PSR |  |  |  | Date from IS I&T schedule
2012-08-28 |  | FM2 FIELDS (partial?) delivery to IS | DEL | UNH | SwRI |  | Date from IS I&T schedule
2012-09-01 |  | FM1 set Boom and Receiving ELEMENT | DEL | LASP | GSFC |  | Approximate need date. Harbaugh to confirm