## NearTerm
FIELDS Near-Term Activites, J. Macri
from date | to date | item | category | from | to | responsible | status/ note
2011-09-08 |  | MIP of FM1 Gun boards at IWF | MIP | SwRI |  | SwRI | done
2011-09-09 |  | FRR: EDI beam gen system | FRR | UNH |  | Turco | done
2011-09-11 |  | FM1 AEB | DEL | UNH | KTH | King | done
2011-09-12 |  | FM1 A-BEB bench test | TST | KTH |  | Olsson | done
2011-09-12 |  | Receipt of EM Gun and GDE | DEL | UNH | IWF | Williams | done
2011-09-12 |  | FM1 SDP Probe assemblies | DEL | Oulu | KTH | Lindqvist | done
2011-09-12 |  | TRR | TRR | UCLA |  | Strangeway | done
2011-09-13 | 2011-09-14 | FM2 FG Sensor vibe | TST | UCLA | ` | Strangeway | done
2011-09-14 | 2011-09-16 | Acceptance test FM1 DSP boards (2) | TST | LASP | UNH | Rau | done
2011-09-14 | 2011-10-04 | Assembly of FM1 CEB (box and electronics) | ASSY | UNH |  | Nolin | done
2011-09-15 | 2011-09-19 | FM1 AEB testing (IRFU) | TST | IRFU |  | King | done
2011-09-15 |  | FRR: CEB assembly | FRR | UNH |  | Turco | done
2011-09-16 | 2011-09-28 | FM2 FG Sensors thermal and bakeout | TST | UCLA |  | Strangeway | done
2011-09-16 |  | FM1-1 HV Filament Board (ship) | DEL | UNH | IWF | Williams | done
2011-09-16 |  | FM1 ADP Ext. Booms (EIDP review) | DEL | ATK | LASP | Westfall | done
2011-09-16 |  | EDI Gun CDR follow-up (9 a.m. EDT) | CDR | UNH |  | Macri | done
2011-09-19 | 2011-09-21 | FM1-1 beam generation system test | TST | UNH |  | Singer | done
2011-09-20 | 2011-09-23 | Parylene coating of FM1 AEB boards (Sweden) | ASSY | KTH |  | King | done
2011-09-20 |  | FRR: EDI Sensor assembly | FRR | UNH |  | Turco | done
2011-09-20 |  | LVPS, AFG, DFG parylene coating complete | MILE | UNH |  | Turco | done
2011-09-21 | 2011-09-26 | FM1 S-BEB testing (IRFU) | TST | IRFU |  | King | done
2011-09-22 |  | FM1 S-BEB testing (IRFU) | TRR |  |  | King | done
2011-09-22 12:00 | 2011-09-23 | CDPU SW acceptance test (Needell) | TST | UNH |  | Needell | done
2011-09-23 |  | FM1-1 HV Filament Board (received) | DEL | UNH | IWF | Steller | done
2011-09-23 11:30 | 2011-09-23 15:00 | PER: FM2 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-09-26 | 2011-09-27 | MMS SWT | MTG | UNH |  | Torbert | done
2011-09-26 |  | FM1 AEB | DEL | KTH | UNH | Lindqvist | done
2011-09-26 |  | Current generator (GSE) | DEL | IWF | UNH | Magnes | done
2011-09-26 12:00 | 2011-09-27 | EM FIT testing at UNH | TST | UNH |  | Dors | done
2011-09-28 | 2011-10-03 | FM1 S-BEB parylene coating | ASSY | KTH |  | King | done
2011-09-28 |  | FM1 AEB receiving inspection (morning) |  | UNH |  | Turco | done
2011-09-28 |  | FRR for mag harnesses | FRR | UNH |  | Turco | done
2011-09-28 |  | Reynolds HV cable received at IWF | DEL | VEND | IWF | Steller | done
2011-09-28 |  | PRODEX/ESA approval of GDE circuit modification | DES | IWF |  | Steller | done
2011-09-28 |  | MMS SWG (PIs, Wed morning) | MTG | UNH |  | Torbert | done
2011-09-28 13:00 | 2011-09-29 | FIELDS Science Data Processing Working Group | MTG | UNH |  | Chutter | done
2011-09-29 |  | FM1-1 beam generation system | DEL | UNH | IWF | Singer | done
2011-09-29 |  | FM2 DFG Sensor | DEL | UCLA | UNH | Strangeway | done
2011-09-29 |  | FM1-2 HV Filament Board | DEL | UNH | IWF | Turco | done
2011-09-30 | 2011-10-03 | FM1 SDP Probes TV testing | TST | KTH |  | Lindqvist | done
2011-09-30 |  | FM2 DFG receiving inspection and EIDP review | EIDP | UNH |  | Turco | done
2011-09-30 |  | FM4 & FS DFG boards | DEL | UNH | IWF | Williams | done
2011-09-30 |  | FM2 DFG Sensor | DEL | UNH | IWF | Williams | done
2011-10-03 | 2011-10-04 | FM1 S-BEB parylene (Sweden) | ASSY | KTH |  | King | done
2011-10-03 | 2011-10-05 | FM1 SCM Sensor and Preamp | DEL/TST | LPP | UNH | Leroy | done
2011-10-03 |  | ADP Simulator | DEL | LASP | UNH | Westfall | done
2011-10-03 |  | Connector brackets for DSPs 4-7 | DEL | UNH | LASP | Nolin | done
2011-10-03 |  | EIDP Review: FM1 SCM | EIDP |  |  | Macri | done
2011-10-06 | 2011-10-21 | Final definition: FM motors & harnesses | MILE | UNH |  | King | done
2011-10-06 |  | FM1 CEB FFT | TST | UNH |  | Rau | done
2011-10-06 |  | FM1 SDP Probes (4) | DEL | KTH | UNH | King | done
2011-10-06 |  | FM1 S-BEB | DEL | KTH | UNH | King | done
2011-10-07 |  | EM4 SCM Sensor and BB Preamp (receive @ UNH) | DEL | LPP | UNH | Williams | done
2011-10-07 |  | FM1 AEB functional test | TST | UNH |  | Rau | done
2011-10-07 |  | TRR: FM1 CEB (AEB & SCM) EMI/EMC test | TRR | UNH |  | Myers | done
2011-10-10 | 2011-10-27 | TV chamber characterization for outgassing certification measurements | TST | UNH |  | Turco | done
2011-10-11 | 2011-10-20 | FM1 CEB (AEB & SCM) EMI/EMC testing @ Retlif | TST | UNH |  | Dors | done
2011-10-14 | 2011-10-21 | Review TV chamber data and readinesss for outgassing certificaiton with Jack Sanders | TRR | UNH |  | Turco | done
2011-10-14 |  | Distribute materials for EDI SW TRR | TRR | UNH |  | Briggs | done
2011-10-17 | 2011-10-18 | FM1-1 EDI Gun inspection (Granoff, Macri) | INS | UNH | IWF | Macri | done
2011-10-17 | 2011-11-02 | FM1 SCM harness bakeout and certification | TST | UNH |  | Turco | done
2011-10-17 |  | Connector brackets for DSPs 8-9 | DEL | UNH | LASP | Nolin | done
2011-10-24 |  | FG nulling coil GSE (1st of 4) | DEL | UCLA | UNH | Strangeway | done
2011-10-24 |  | FM1 CEB retest planning (DSP FPGA change) | FRB | SwRI |  | Black | done
2011-10-25 | 2011-10-28 | FM1 SDP preamp/cable rework, fine wire assy and boom wire marking @ UNH | ASSY | LASP |  | Vermeer | done
2011-10-25 |  | CDPU SW acceptance test (post-test review) | REV | UNH |  | Heirtzler | done
2011-10-26 |  | EDI FSW TRR | TRR | UNH |  | Briggs | done
2011-10-27 | 2011-11-29 | Plan for SDP deployments on S/C decks to GSFC | DOC | UNH | GSFC | Macri | done
2011-10-27 |  | ADP FM1 booms (SN01, SN02) delivery to LASP | DEL | ATK | LASP | Westfall | done
2011-10-28 |  | FM1 AEB (plus 2 FM1 DSP boards and 1 EM A-BEB) & ADP simulator | DEL | UNH | LASP | Rau | done
2011-10-29 |  | FM1-2 EDI beam generation system | DEL | UNH | IWF | Singer | done
2011-10-31 | 2011-11-02 | CIDP Road Show at GSFC | TST | UNH |  | Needell | done
2011-10-31 |  | FIELDS Simulator (received at SwRI) | DEL | UNH | SwRI | Chutter | done
2011-10-31 |  | EM4 SCM Sensor deliver to GSFC for tests with qual boom | DEL | UNH | GSFC | Rau | done
2011-11-02 |  | EM4 SCM Sensor installation on QM mag boom (GSFC) | INT | GSFC |  | Sturm | done
2011-11-02 |  | ASPOC PER | PER | IIRT |  |  | done
2011-11-03 | 2011-11-09 | FM1 SCM Sensor & Preamp bakeout & cert. | TST | UNH |  | Turco | done
2011-11-04 |  | Return EM1 AFG board to UNH | DEL | UCLA |  | Strangeway | done
2011-11-07 | 2011-11-30 | FM2 A-BEB PWAs | ASSY | Iowa | UNH | Turco | done
2011-11-09 |  | PER: FM ship set 3 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-11-10 |  | EDI FSW Acceptance test | TST | UNH |  | Briggs | done
2011-11-10 |  | TRR: FM1 SDP EMI/EMC testing (1 deployer) | TRR | UNH |  | Dors | done
2011-11-10 |  | TRR: FM1-1 EDI Sensor thermal and vacuum tests | TRR | UNH |  | Macri | done
2011-11-14 |  | FM1-1 SDP FFT | TST | UNH |  | King | done
2011-11-14 |  | Change soldered FPGA on EM DSP board | ASSY | LASP |  | Westfall | done
2011-11-15 | 2011-11-16 | FM1-1 EDI Sensor thermal test | ETST | UNH |  | Singer | done
2011-11-15 | 2011-11-18 | FM1 SDP EMI/EMC testing (1 deployer) | ETST | UNH |  | Dors | done
2011-11-15 |  | PER: FM1 SDP | PER | UNH |  | Myers | done
2011-11-17 | 2011-12-02 | Review EM AEB testing at LASP and plan forward | REV |  |  | Macri | done
2011-11-17 | 2011-12-07 | SDP preamp thermal test plan prep and review |  |  |  | Nolin | done
2011-11-17 |  | DSP & CDPU FPGAs (pre-burn review) | REV |  |  | Macri | done
2011-11-18 |  | Beam Gen Syst. Anode and focus weldments (pre- plating, receipt @ UNH) | DEL | VEND | UNH | Nolin | done. Rejected.
2011-11-22 |  | FM2 LVPS PWA | DEL | SYN | UNH | Turco | done
2011-11-22 |  | TRR: FM1 SDP vibration (1 unit) | TRR |  |  | Macri | done
2011-11-28 | 2011-12-02 | FM3 DFG Sensor capacitor installation | ASSY | UCLA |  | Strangeway | done
2011-11-29 | 2011-12-01 | FM S/N2 EDI Sensor thermal test | ETST | UNH |  | Singer | done
2011-11-30 | 2011-12-02 | FM1 SDP vibration (1 unit) | ETST | UNH |  | Granoff | done
2011-11-30 |  | FM2 A-BEB PWAs | DEL | Iowa | UNH |  | done
2011-11-30 |  | PER: FM ship set 4 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-12-02 | 2011-12-05 | FM S/N3-4 CDPU thermal tests | ETST | UNH |  | Bodet | done
2011-12-02 |  | FM1 AEB return to UNH for repair | DEL | LASP | UNH | King | done
2011-12-03 |  | FM2 LVPS PWA | DEL | UNH | KTH | Turco | done
2011-12-05 |  | FM3 LVPS PWA | DEL | SYN | UNH | Turco | done
2011-12-05 |  | Burn 2nd FPGA for FM1 DSP | ASSY | UNH | LASP | Summers | done
2011-12-07 |  | Beam Gen Syst. weldments (in process inspection) Done for one set. Okay. Go-ahead for remainder given to vendor | MILE | UNH |  | Salwen | done
2011-12-08 | 2011-12-09 | FM SDP preamp TV survival cycle (3 units, S/N2-4) | ETST | UNH |  | Nolin | done
2011-12-08 |  | SDP preamp thermal model and test plan review | REV |  |  | Macri | done
2011-12-12 | 2011-12-16 | CDPU S/Ns 3&4 parylene coating | ASSY | SCS |  | Turco | done
2011-12-12 | 2011-12-16 | EDI Gun Support Collar wiring at UNH. | ASSY | Iowa | UNH |  | done
2011-12-14 | 2011-12-16 | SOC peer review and TIM | REV |  |  | Needell | done
2011-12-14 |  | FM1 AEBs (modified) to KTH for test | DEL | UNH | KTH | King | done
2011-12-14 |  | FM3 LVPS PWA | DEL | UNH | KTH | King | done
2011-12-20 |  | Mount thermal HW on FM1 CEB | ASSY | UNH |  | Nolin | done
2011-12-20 |  | FM1 AEB (tested) return to UNH | DEL | KTH | UNH | King | done
2011-12-20 |  | FM2 LVPS | DEL | KTH | UNH | King | done
2011-12-21 |  | FM1 GDE | DEL | RUAG | IWF | Steller | done
2012-01-03 |  | FM1 AEB (tested) return to LASP | DEL | UNH | LASP | King | done
2012-01-04 |  | FM4&FS LVPS PWAs | DEL | SYN | UNH | Turco | done
2012-01-05 | 2012-01-06 | SDP 2 - 4 Preamp TV Retest | ETST | UNH |  |  | done
2012-01-05 | 2012-01-18 | Syntech FM2 set SBEB assembly | ASSY | SYN |  | Turco | done
2012-01-05 |  | PER: FM3 FG Sensors (Webex) | PER | UCLA |  | Strangeway | done
2012-01-06 |  | FM1 DSP boards (return to UNH) | DEL | LASP | UNH | Wesfall | done
2012-01-09 |  | TRR: EQM SDP Vibration | TRR | UNH |  | Macri | done
2012-01-09 |  | PER: FM2/3 SCM (WebEx) | PER | LPP |  | Leroy | done
2012-01-10 | 2012-01-11 | IS SIR | SIR |  |  |  | done
2012-01-10 | 2012-01-11 | EQM SDP Vibe | ETST | UNH |  | Granoff | done
2012-01-10 |  | FM1 GDE secondary ground isolation problem | PROB | RUAG | IWF | Steller | done
2012-01-10 |  | TRR: FG3 vibration and thermal | TRR |  |  |  | done
2012-01-11 |  | Discussion of SDP damping test | REV | GSFC |  | Frost | done
2012-01-13 |  | TRR: FM SCM sets 2&3 environmental tests | TRR |  |  | Macri | done
2012-01-16 | 2012-02-24 | FM2 set SCM environmental tests | ETST | LPP |  | Leroy | done
2012-01-17 | 2012-01-20 | SDP S/N 1 and EQM vibration | ETST | UNH |  |  | done
2012-01-17 | 2012-01-20 | SDP FM SN2-4 Preamp/Sphere integration | ASSY | UNH |  | King | done
2012-01-17 |  | FM2 set SDP Preamps and 5-8 doors | DEL | LASP | UNH | Westfall | done
2012-01-17 |  | Prep FM2 set SDP preamps for TV test | ASSY |  |  | King | done
2012-01-18 | 2012-01-20 | TV test FM S/N5-8 SDP Preamps | ETST | UNH |  | King | done
2012-01-18 |  | EDI beam gen system weldments (remaining anode and focus units) | DEL | VEND | UNH | Salwen | done
2012-01-18 |  | PER: FM1 CEB (@UNH) | PER | UNH |  | Myers | done
2012-01-20 |  | FM2 S-BEB PWA | DEL | SYN | UNH | Turco | done
2012-01-20 |  | TRR: FM1 CEB vibration | TRR |  |  | Macri | done
2012-01-23 |  | PER: FM1 pair Receiving Elements (@LASP) | PER | LASP |  | Westfall | done
2012-01-25 | 2012-01-27 | FM1 CEB vibration | ETST | UNH |  | Nolin | done
2012-01-30 | 2012-03-15 | FM3 set SCM vibration | ETST | LPP |  | Leroy | Done.
2012-01-30 | 2012-03-15 | FM3 set SCM vibe | ETST | LPP |  | Leroy | done
2012-01-30 |  | TRR: FM1 set Receiving Elements vibration | TRR | LASP |  | Westfall | done
2012-01-31 |  | PER: FM1 AEB (WebEx) | PER | LASP |  | Westfall | done
2012-02-01 | 2012-02-03 | Baseline outgassing measurements for FM1 CEB | ETST | UNH |  | Turco | done
2012-02-01 | 2012-02-03 | FM1 set Receiving Elements vibration | ETST | LASP |  | Westfall | done
2012-02-03 |  | SDP deployment problem (update for project) | MTG | UNH |  | Macri | done
2012-02-03 |  | TRR: FM1 AEB vibration testing | TRR | LASP |  | Macri | done
2012-02-03 09:00 |  | TRR: FM1 CEB TV | TRR |  |  | Macri | done
2012-02-06 |  | FM1 AEB vibration testing | ETST | LASP |  | Westfall | done
2012-02-07 |  | FM3 DFG Sensor. Return 2nd tuning harness to UNH. | DEL | UCLA | UNH | Rowe | Done.
2012-02-09 | 2012-02-10 | SDP vibration investigation | ETST | UNH |  | Granoff | done
2012-02-10 |  | TRR: FM1 Receiving Element TV testing | TRR | LASP |  | Westfall | done
2012-02-11 | 2012-02-16 | Myers at IWF (schedule work) |  | UNH |  |  | done
2012-02-11 |  | FM3 DFG Sensor | DEL | UNH | IWF | Myers | done
2012-02-13 | 2012-03-01 | FM1 Receiving Element TV testing | ETST | LASP |  | Westfall | Done.
2012-02-17 | 2012-02-24 | FM2 SCM Preamp TV | ETST | LPP |  | Leroy | done
2012-02-17 |  | TRR: FM2 AFG/DFG Joint Calibration | TRR |  |  | Magnes | Done.
2012-02-21 |  | Deliveries to KTH: FM2 AEB (modified), FM2 set S-BEB (modified) PWAs, FM2 set SDP Preamp/Cable assemblies, and FM4 & FM5 LVPS. | DEL | UNH | KTH | King | Done.
2012-02-21 |  | SDP vibration investigation (radial clamp) | ETST | UNH |  | Granoff | Done.
2012-02-22 |  | TRR: FM1 CEB vibration (workmanship, 1 axis) | TRR | UNH |  | Macri | Done.
2012-02-23 |  | TRR: FM1 AEB TV Test | TRR | LASP |  | Westfall | Done.
2012-02-23 |  | FM1 CEB vibration (workmanship, 1 axis) | ETST | UNH |  | Nolin | Done.
2012-02-24 | 2012-03-01 | FM1 AEB TV Test | ETST | LASP |  | Westfall | done
2012-02-24 | 2012-03-08 | FM1 CEB TV | ETST | UNH |  | Rau | done
2012-02-24 |  | TRR: FM1 CEB TV | TRR | UNH |  | Macri | Done.
2012-02-24 |  | Submit GFY13 PPBE | DEL | UNH |  | Macri | done
2012-02-24 |  | Return EM4 SCM Sensor to UNH | DEL | GSFC | UNH | Sturm | done
2012-02-27 |  | SDP deployment problem (update for project) | REV | UNH |  | Granoff | done
2012-02-28 | 2012-03-09 | FM2 AFG/DFG Joint Calibration | ETST |  |  | Magnes | done
2012-02-29 |  | Update on ADP Boom plan forward | MTG | LASP |  | Westfall | done
2012-03-01 |  | ***CANCELLED***. EQM SDP delivery to GSFC for qual deck testing | DEL | UNH | GSFC | King | Done.
2012-03-05 | 2012-03-14 | FM1 AEB-RE calibration | TST | LASP |  | Ergun | done
2012-03-05 | 2012-03-15 | FM2 SCM Calibration | ETST | LPP |  | Leroy | done
2012-03-10 |  | Tested hardware delivery (FM2 AEB, Probes through BEBs S/Ns 5-8) | DEL | KTH | UNH | King | done
2012-03-12 |  | EDI Correlator (Xilinx) peer review | REV | UNH |  | Vaith | done
2012-03-14 |  | FRR: EDI GDU (internal review) | FRR | UNH |  | Turco | Done.
2012-03-14 |  | FRR: EDI GDU (internal review) | FRR | UNH |  | Turco | Done.
2012-03-16 | 2012-03-22 | Repeat SCM Preamp S/N4 TV test | ETST | LPP |  | Leroy | done
2012-03-16 | 2012-03-23 | Repeat SCM Preamp S/N4 (SCM SS#3) TV test | ETST | LPP |  | Leroy | done
2012-03-16 |  | FM1 AEB (and ADP simulators (2 channels)) Delivery | DEL | LASP | UNH | Westfall | done
2012-03-19 |  | FM2 CEB housing ready |  |  |  | Nolin | Done.
2012-03-20 | 2012-03-21 | MMS SWT (San Antonio) | MTG |  |  | Torbert | done
2012-03-20 | 2012-03-21 | MMS SWT (San Antonio) | MTG |  |  | Torbert | Done.
2012-03-20 |  | EM4 SCM Sensor delivery to LPP. Thermal test for verification following QM boom deploy (shock) test | DEL | UNH | LPP | Williams | done
2012-03-20 |  | SDP ship set #4 boom cables (and spares?) | DEL | UNH | LASP | Beckman | done
2012-03-21 |  | S/N3 EDI Beam Gen Syst | DEL | UNH | IWF | Vaith | done
2012-03-22 | 2012-03-23 | SDP prototype (SN1 w/ RWC) vibe | ETST | UNH |  | Granoff | done
2012-03-22 |  | MMS SWG |  |  |  | Torbert | done
2012-03-22 |  | TRR: FIELDS FM1 FIT (timing) testing | TRR | UNH |  | Macri | done
2012-03-22 |  | MMS SWG |  |  |  | Torbert | Done.
2012-03-22 |  | FM2 CEB housing assembly complete | DEL | UNH | UNH | Nolin | done
2012-03-22 15:00 |  | FIELDS data processing meeting (San Antonio) | MTG |  |  | Torbert | done
2012-03-22 15:00 |  | FIELDS data processing meeting (San Antonio) | MTG |  |  | Torbert | done
2012-03-23 |  | New over-shield material for SCM harnesses | DEL | UNH | LPP | Turco | done
2012-03-23 |  | FM2 AEB | DEL | UNH | LASP | Rau | done
2012-03-26 | 2012-03-28 | FIELDS FM1 FIT (part 1, magnetometer timing) testing. FM1 CEB, AFG, DFG, SCM | TST | UNH |  | Dors | done
2012-03-26 | 2012-05-25 | FM1 FIELDS I&T: CPT, FIT, procedure and script development | TST | UNH |  | Rau | done
2012-03-26 |  | FM2 AFG Delivery and acceptance test. | DEL | UCLA | UNH | Strangeway | done
2012-03-26 |  | TRR: FIELDS FM1 FIT test part 1 (magnetometer timing) | TRR | UNH |  | Macri | Done.
2012-03-27 | 2012-03-28 | SwRI PMs at UNH (schedule review) | MTG | UNH |  | Macri | done
2012-03-27 | 2012-03-30 | SDP prototype (SN1 w/ RWC) vibe | ETST | UNH |  | Granoff | Done.
2012-03-27 |  | FM2 DFG delivery and acceptance test | DEL | IWF | UNH | Valavanoglou | done
2012-03-29 |  | S/N3 & 4 EDI Beam Gen Syst | DEL | UNH | IWF | Valavanoglou | done
2012-03-29 |  | FM3 set A-BEB PWA | DEL | SYN | UNH | Turco | Done.
2012-04-03 | 2012-04-03 | Integrate first set EDI Optics (S/N2) with Sensor (S/N1) at UNH | ASSY | Iowa | UNH | Dvorsky | Done.
2012-04-05 | 2012-05-09 | EM4 SCM Sensor verification following QM boom deploy (shock) test | ETST | LPP |  | Alison | done.
2012-04-10 |  | Peer Review: SDP RWC mechanism | REV | UNH |  | Granoff | done
2012-04-11 | 2012-04-18 | SNs 3&4 EDI Sensor boards ready for bench testing | ASSY | UNH |  | Tyler | done
2012-04-11 |  | FM2 LVPS ready for CEB I&T (incoming functional test wth UNH GSE) | TST | UNH |  | Troop | done
2012-04-12 | 2012-04-20 | FM S/N2 EDI Gun & GDE (first unit). IWF support at UNH | ASSY | IWF | UNH | Steller | done
2012-04-12 | 2012-04-24 | FM SN2 GDU (1st unit) integration | ASSY | UNH |  | Vaith | done
2012-04-13 |  | FM1 and FM2 ship sets ADP booms (S/Ns 1-4) | DEL | ATK | LASP |  | done
2012-04-16 | 2012-04-24 | Parylene coating of FM2 CDPU A&B, AFG, DFG, EDI Controller | ASSY | UNH |  | Turco | done
2012-04-17 | 2012-04-19 | FM S/N2 GDU integration (Iowa support) | ASSY | Iowa |  | Bounds | Done.
2012-04-17 | 2012-05-15 | Revised random environment analyses for SDP | ANA | GSFC | UNH | Dirks | done
2012-04-17 | 2012-05-15 | Revised random environment analyses for EDI | ANA | GSFC | UNH | Dirks | done.
2012-04-19 | 2012-04-20 | FIELDS FM1 FIT testing (AEB timing) FM1:CEB, AEB | TST | UNH |  | Dors | done
2012-04-20 |  | Remaining Gun DFL2 PWBs | DEL | UNH | IWF | Steller | Done.
2012-04-20 |  | SDP preamp/cable assemblies (S/Ns 9-12) | DEL | LASP | UNH | Vermeer | done
2012-04-23 |  | Return EM AEB to LASP | DEL | UNH | LASP | Rau | Done.
2012-04-23 |  | Nulling Coil GSE. UCLA will send 2 with a SW update; return 1 to UCLA for addional coil turns. | DEL | UCLA | UNH | Strangeway | done
2012-04-24 |  | FM2 BPM ready for FM2 CEB | DEL | UNH |  | Bodet | done
2012-04-24 |  | STP file for AEB interface plate | DEL | LASP | SwRI | Tucker | done
2012-04-25 |  | TRR: S/N2 GDU bench test | TRR | UNH |  | Macri | done
2012-04-25 12:00 | 2012-04-26 | GDU SN2 bench test | TST | UNH |  | Vaith | done
2012-04-26 |  | FM2 CDPU (2) delivery to CEB | DEL | UNH | UNH | Turco | done
2012-04-26 |  | Discussion of ADP and SDP deployment test plans at Obs. | MTG |  |  | Pope | done
2012-04-26 |  | FM2 DFG Delivery to CEB | DEL | UNH | UNH | Turco | Done.
2012-04-30 | 2012-05-03 | FM2 SCM Harness outgassing certification | ETST | LPP |  | Alison | Done.
2012-04-30 |  | PER: FM2 set AEB and Receiving Elements | PER |  |  |  | Done.
2012-04-30 |  | TRR: FM2 set Receiving Elements vibration | TRR | LASP |  |  | done
2012-05-02 | 2012-05-04 | SDP S/N1 vibration (RWC on new outer cylinder) | VTST | UNH |  | Granoff | Done.
2012-05-03 |  | FM2 EDI Contrtoller Delivery to CEB | DEL | UNH | UNH | Turco | done
2012-05-03 |  | FM2 AFG Delivery to CEB | DEL | UNH | UNH | Turco | done
2012-05-07 | 2012-05-18 | FM3 DFG TU-BS calibration |  |  |  |  | Done.
2012-05-07 |  | S/N2 GDU FFT (room 145 chamber) | ETST |  |  | Singer | Done.
2012-05-07 |  | TRR: FM2 AEB TV test | TRR |  |  |  | done
2012-05-08 | 2012-05-16 | S/N2 GDU characterization (room 145 chamber) | ETST | UNH |  | Singer | Done.
2012-05-08 |  | TRR: S/N2 GDU vacuum test and characterization | TRR | UNH |  | Macri | done
2012-05-11 |  | SDP thermal test plan distribution | RFA |  |  | King | done.
2012-05-15 | 2012-05-24 | Repair of FTS (UNH TV) | TV |  |  | Ellis | done
2012-05-17 |  | Outer cylinders ready for SDP S/N3 integration | ASSY | UNH |  | Granoff | done
2012-05-17 |  | GDU SN2 test with FM1 CEB |  |  |  | Vaith | done.
2012-05-18 | 2012-05-24 | FM1 SCM harness bakeout and certification (new overshield). | TV | UNH |  | Turco | done
2012-05-18 | 2012-06-05 | Integration SN3 SDP | ASSY | UNH |  | Granoff | done.
2012-05-18 |  | FIELDS FM1 FIT testing (EDI timing). FM S/N2 EDI-GDU, EM CEB. | TST | UNH |  | Dors | done.
2012-05-18 |  | SDP RWC covers returned from vendor PFE | DEL | VEND | UNH | Granoff | done
2012-05-18 |  | SDP pins returned from vendor Tiodize | DEL | VEND | UNH | Granoff | done
2012-05-18 |  | SDP boom cable S/Ns 17-18 | DEL | UNH | LASP | Beckman | done
2012-05-18 |  | TRR: SN FM2 EDI GDU EMI/EMC Testing (1st unit). | TRR | UNH |  | Macri | done.
2012-05-21 | 2012-05-25 | SN FM2 EDI GDU EMI/EMC Testing (1st unit). | ETST |  |  | Dors | done
2012-05-21 |  | Fluxgate harness deliveries | DEL | UCLA | UNH |  | done.
2012-05-21 |  | PER: S/N2 EDI GDU (1st unit) | PER |  |  | Myers | done.
2012-05-22 | 2012-05-23 | PSR: FM1 FIELDS (partial) delivery to IS (includes all except EDI & SDP) | PSR | UNH |  | Myers | done
2012-05-22 |  | FM2 set DSP (2) Delivery | DEL | LASP | UNH | Westfall | done
2012-05-23 | 2012-05-24 | SDP Sphere/Preamp integration s/ns 3 and 4 and crimping outer guards with probes for 5 and 6. Vermeer support | ASSY | UNH |  | King | done.
2012-05-23 |  | Return SN1 Gun Support Collar to UNH | DEL | Iowa | UNH | Bounds | done
2012-05-23 |  | FM SDP Doors F/Ms 9-16 | DEL | LASP | UNH | Vermeer | done
2012-05-25 |  | Test FM1 AFG/DFG harnesses with FIELDS | TST | UNH |  | Rau | done.
2012-05-29 | 2012-06-01 | FM4 DFG Sensor Capacitor installation | ASSY |  |  | Valavanoglou | done.
2012-05-29 | 2012-06-05 | Return SN1 and SN3 EDI Gun BGS to UNH for filament swap and short investigation | DEL | IWF | UNH | Steller | done.
2012-05-29 | 2012-06-05 | TV survival test: SDP ship set 3 preamp/cable assemblies (S/Ns 9-12). | TV | UNH |  | King | done
2012-05-29 |  | TRR: EDI GDU SN2 Vibe | TRR |  |  |  | Done.
2012-05-29 |  | EM4 SCM Sensor return to UNH | DEL | LPP | UNH | Alison | Done.
2012-05-30 | 2012-05-31 | FM1 FIELDS (partial) Delivery to IS. FM1 CEB, DFG, AFG and SCM and Harnesses, SDPs: (SN1, FIT BEBs w/ motor and HOP load sims) ; | DEL | UNH |  | Rau | done
2012-05-30 | 2012-06-01 | S/N 2 EDI GDU Vibration Testing (1st unit) | VTST |  |  | Granoff | done
2012-05-31 | 2012-06-15 | FIELDS FM1 IS I&T (except SDP and GDU) | TST | UNH |  | Rau | done.
2012-06-04 | 2012-06-17 | Calibration: FM2 set RE & AEB | TST | LASP |  | Tucker | done
2012-06-04 |  | ADP Simulator and test harness for IS | DEL | LASP | UNH | Tucker | Done.
2012-06-06 |  | BGS S/N5 | DEL | UNH | IWF | Singer | done
2012-06-06 |  | TRR: S/N2 EDI GDU TV Testing | TRR |  |  | Macri | Done.
2012-06-07 | 2012-06-28 | S/N2 EDI GDU TV Testing | TV |  |  | Vaith | done
2012-06-07 |  | FM3 set S-BEB PWAs | DEL | SYN | UNH | Turco | Done.
2012-06-07 |  | FM2 DSP boards acceptance test | TST | UNH |  | Dors | done
2012-06-11 |  | Delta PER: SDP S/sN 3&4 (WebEx agreed) | PER | UNH |  | Myers | done
2012-06-11 |  | TRR: SDP S/N3 & 4 vibration | TRR | UNH |  | Granoff | done
2012-06-12 | 2012-06-15 | FM SDP SN3-4 Vibration Testing | VTST |  |  | Granoff | done
2012-06-12 |  | FM3 AEB | DEL | UNH | KTH | King | done
2012-06-15 |  | FM2 CEB mehanical assemby complete | ASSY | UNH |  | Nolin | done
2012-06-20 | 2012-06-21 | FM SDP S/N 3 EMI/EMC CE and magnetics test (@UNH) | ETST | UNH |  | Dors | Done.
2012-06-20 |  | FM2 AEB | DEL | LASP | UNH | Tucker | done
2012-06-20 |  | TRR: FM SDP S/Ns 3&4 EMI/EMC tests (@UNH) | TRR | UNH |  | Dors | done
2012-06-22 |  | FM4&5 AEB boards | DEL | SYN | UNH | Turco | done
2012-06-25 | 2012-06-26 | FM2 CEB 1st FFT | TST | UNH |  | Dors | done
2012-06-29 |  | Outgassing certification of SS#1 ADP booms | TST | LASP |  | Tucker | Status?
2012-06-26 |  | PER: FM4 AFG/DFG Sensors | PER | UCLA |  | Strangeway | done
2012-06-26 |  | TRR: FM4 AFG/DFG Sensors (all env tests) | TRR | UCLA |  | Strangeway | done
2012-06-28 | 2012-06-29 | FM SDP S/N 4 EMI/EMC test (@UNH) | ETST | UNH |  | Dors | done
2012-06-28 |  | SDP TV test procedure for review. | REV |  |  | Beckman | done
2012-06-29 |  | TRR: FM SDP SN3-4 TV Testing | TRR | UNH |  | Macri | done
2012-06-29 |  | AFG tuning harness | DEL | UNH | UCLA | Rau | Status?
2012-07-03 | 2012-07-20 | FM SDP SN3-4 TV Testing | TV | UNH |  | King | underway
2012-07-09 |  | FIELDS ADP Simulator | DEL | LASP | UNH | Tucker | Status?
2012-07-09 |  | Fluxgate Sensor labels for bakeout | DEL | UCLA | UNH | Strangeway | Send to UNH when shipping back the tuning harness.
2012-07-11 |  | TRR: FM2 CEB EMI/EMC CE testing @UNH | TRR | UNH |  | Dors
2012-07-12 |  | PER: FM2 CEB | PER | UNH |  | Myers | 3:15 pm EDT
2012-07-13 | 2012-07-13 | FM2 CEB EMI/EMC CE testing @UNH | ETST | UNH |  | Dors
2012-07-16 |  | FM2 CEB magnetics testing @UNH | TST | UNH |  | Dors
2012-07-16 |  | TRR: CEB FM2 vibration | TRR | UNH |  | Macri
2012-07-17 | 2012-07-18 | SDP SNs 5/6 sphere/preamp integration. | ASSY | LASP | UNH | King | Vermeer support at UNH?
2012-07-18 | 2012-07-20 | CEB FM2 vibration | VTST | UNH |  | Nolin | at BAE - confirmed
2012-07-19 |  | Fit check ADP Booms and REs (ship sets 1&2) | TST | LASP |  | Tucker | Item is from LASP's June monthly report
2012-07-20 |  | SDP preamp/cable assemblies (S/Ns 13-16) | DEL | LASP | UNH | Tucker | Date?
2012-07-20 |  | SDP preamp/cable assemblies (S/Ns 17-18) | DEL | LASP | UNH | Tucker | Date?
2012-07-20 |  | SDP Doors SN17 - SN18 | DEL | LASP | UNH | Tucker | Date?
2012-07-23 | 2012-07-27 | Magnetometer week at UNH (AFG, DFG, SCM) |  |  |  |  | Coordinate
2012-07-23 | 2012-08-01 | SDP FM1 set IS I&T | TST
2012-07-23 |  | FM3 AFG (and test harnesses) | DEL | UCLA | UNH | Rowe | Coordinate. Rau prefers AFG and DFG delivered at the same time.
2012-07-23 |  | FM4 DFG Sensor | DEL | UCLA | UNH | Rowe | Hand carry, Rowe. When delivering FM3 AFG.
2012-07-24 |  | FM2 CEB EMI/EMC Magnetics testing | ETST | UNH |  | Dors | Must be after vibe
2012-07-24 |  | FM3 DFG | DEL | IWF | UNH | Valavanoglou | 23 Jul travel date.
2012-07-24 |  | PER: S/N1 EDI GDU (2nd unit) | PER |  |  |  | Date is Macri's WAG.
2012-07-24 |  | QM ADP Boom and Receiving Element installation | ASSY | LASP | GSFC | Tucker | Date is from Harbaugh, 31 May 2012. Installation 24 July; testing to follow
2012-07-25 | 2012-07-26 | FM2 SCM (Sensor, Preamp and harness) and FM3 SCM (Sensor and Preamp only) | DEL | LPP | UNH | Leroy | FM2 is ready as of 1 June. Ship FM3 harness after outgassing certification (Aug)
2012-07-27 |  | PER: SDP SNs 5&6 | PER |  |  |  | Date? FFT awaits GSE upon completion of TV of SNs 3&4
2012-07-27 |  | FM4 DFG Sensor | DEL | UNH | IWF | Valavanoglou | Hand carry following delivery of FM3 DFG.
2012-07-30 |  | TRR: SDP SNs 5&6 Vibration | TRR | UNH |  | Granoff
2012-07-31 | 2012-08-03 | SDP SNs 5&6 Vibration | VTST | UNH |  | Granoff | BAE. Vibration slot reserved
2012-07-31 |  | FM3 AEB | DEL | KTH | UNH | King | Rework before test. Ship to UNH.
2012-07-31 |  | FM3 set DSP boards (SNs 5&11) | DEL | LASP | UNH | Tucker | Date is from LASP's June monthly report
2012-08-01 | 2012-07-30 | SN1 SDP participation in QM s/c deck testing |  |  |  |  | Project request. Not decided.
2012-08-01 |  | SN FM1 Gun and GDE | DEL | IWF | UNH | Steller | Delayed
2012-08-01 |  | FM3 AEB | DEL | UNH | LASP | King | King confirms 1 Aug date realistic.
2012-08-01 |  | QM ADP Boom and Receiving Element delivery to GSFC | DEL | LASP | GSFC | Tucker | Date is from Harbaugh, 21 Jun 2012. Installation 7 Aug, testing to follow
2012-08-01 |  | 2 more AFG/DFG Nulling Coils | DEL | UCLA | UNH | Rowe
2012-08-02 |  | FM4&5 AEB | DEL | UNH | KTH | King | Date?
2012-08-10 |  | IS#1 PSR | PSR |  |  |  | Date from IS I&T schedule
2012-08-14 |  | PSR: FM1 set EDI GDUs | PSR |  |  |  | Date is Macri's WAG.
2012-08-14 |  | PSR: FM1 set SDP (4 units) | PSR |  |  |  | Date is Macri's WAG.
2012-08-15 | 2012-08-15 | SDP (1-unit) calibration in Faraday cage at LASP | TST | UNH | LASP | King | Ergun: Goal is directly comparable ADP and SDP calibrations. Can be FM or fully representative EM. Spring or summer 2012. Test in Uppsala should preclude the test Ergun is suggesting. Could be done later.
2012-08-15 |  | SDP damping test at GSFC | TST | GSFC |  | Frost | Date? Requested Minh Phan's support.
2012-08-15 |  | QM SDP BEB testing at IS | TST | UNH |  | Rau | Date? NCR closeout. With SDP FM1 set delivery?
2012-08-15 |  | EM AEB (UNH/LASP shared item) | DEL |  |  |  | Date? Currently at LASP for verifying simulator box functionality. Needed again at UNH after FM2 CEB TV.
2012-08-15 |  | FM3, 4 and 5 sets S-BEB PWAs | DEL | UNH | KTH | King | King travel to KTH
2012-08-15 |  | FM3 SCM harness | DEL | LPP | UNH | Leroy | Ship after outgassing certification
2012-08-17 |  | FM4 AEB | DEL | KTH | UNH | King | Date?
2012-08-17 |  | FM5 (spare) AEB | DEL | KTH | UNH | King | Date?
2012-08-21 |  | FM4 AEB | DEL | UNH | LASP | King | Date?
2012-08-27 | 2012-08-30 | Mission SIR | SIR | GSFC |  |  | Date from Ron Black, 20 Apr 2012
2012-08-28 |  | FM2 FIELDS (partial?) delivery to IS | DEL | UNH | SwRI |  | Date from IS I&T schedule
2012-09-01 |  | FM1 set Boom and Receiving ELEMENT | DEL | LASP | GSFC |  | Approximate need date. Harbaugh to confirm
2012-09-15 |  | ADP Simulator and test harness for S/C | DEL | LASP |  | Tucker | Harbaugh to provide need date.
2012-10-31 |  | FM3 AEB | DEL | LASP | UNH | Tucker | Date from Tyler
2012-12-28 |  | FM4 AEB | DEL | LASP | UNH | Tucker | Date from Tyler

## Sheet1
| CEB | SDP | EDI
2012-06-26 | FFT | screws and washers
2012-06-27
2012-06-28
2012-06-29
2012-06-30
2012-07-01
2012-07-02
2012-07-03
2012-07-04
2012-07-05
2012-07-06
2012-07-07
2012-07-08
2012-07-09
2012-07-10

## CritiacalPath
Update: | 2012-04-25
Component | Milestone | Critcal Path(s) | Note
FIELDS
| FM1 FIELDS CPT and script development complete (prior to partial delivery to IS) | No clear path in schedule….tasks not defined that clearly…. | I don't have that much detail built into the software portion of the schedule.
| FM1 FIELDS FIT interference measurements complete (prior to partial delivery to IS) | SN03 SDP Deployer………and FM SN02 GDU??? | Dave would like to have one FM SDP and an FM GDU at this test, he will wait to conduct this test until the third week in May in hopes that SN03 SDP can participate.
CEB
| FM2 CEB 1st FFT | Delivery of FM2 DSP | Delivery of the FM2 DSP's could be moved up if LASP does not use their reserve
| FM2 set DSP boards (SNs 8&9) delivery to UNH | Calibration of DSP's
SCM
| FM2 set delivery to UNH | FM2 Harness Outgassing Certification | From schedule
| FM3 set calibration | FM3 Harness Outgassing Certification | From schedule
AFG
| FM3 set delivery to UNH | FM3 Cross Calibration
| FM4 set ready for tuning | FM4a/FM4b Sensor Assembly
DFG
| FM3 set delivery to UNH | FM3 Cross Calibration
| FM4 set ready for tuning | FM4a/FM4b Sensor Assembly
SDP
| S/N3 1st FFT | Fabrication and Coating of SN03 RWC | Major schedule driver
| S/N4 1st FFT | SN04 FFT
| S/N5 1st FFT | SN04 Assembled
| S/N6 1st FFT | SN05 FFT
| FM 3 set SBEB assembly at Syntech | ???? | Need input from Turco…..
EDI GDU
| FM2 set Sensor Stack characterization | Bench Testing of FM2 Sensor Boards
| SN1 Gun and GDE delivery to UNH | Re-integration of FM1-1 Gun
| FM3 set Sensor boards ready for test | FM3 Sensor Board Population
ADP
| FM3 AEB delivery to KTH for testing | Brians travel schedule…… | Possible travel in mid-May? Otherwise, end of May…..then we run into vacation plans in Sweden……
| QM boom and RE delivery to GSFC for QM S/C deck testing | Don't have visibility……need Westfall input. | Need to ask Westfall