## NearTerm
FIELDS Near-Term Activites, J. Macri
from date | to date | Subs. | item | category | from | to | Lead/ participants | status/note
2011-09-08 |  |  | MIP of FM1 Gun boards at IWF | MIP | SwRI |  | SwRI | done
2011-09-09 |  |  | FRR: EDI beam gen system | FRR | UNH |  | Turco | done
2011-09-11 |  |  | FM1 AEB | DEL | UNH | KTH | King | done
2011-09-12 |  |  | FM1 A-BEB bench test | TST | KTH |  | Olsson | done
2011-09-12 |  |  | Receipt of EM Gun and GDE | DEL | UNH | IWF | Williams | done
2011-09-12 |  |  | FM1 SDP Probe assemblies | DEL | Oulu | KTH | Lindqvist | done
2011-09-12 |  |  | TRR | TRR | UCLA |  | Strangeway | done
2011-09-13 | 2011-09-14 |  | FM2 FG Sensor vibe | TST | UCLA | ` | Strangeway | done
2011-09-14 | 2011-09-16 |  | Acceptance test FM1 DSP boards (2) | TST | LASP | UNH | Rau | done
2011-09-14 | 2011-10-04 |  | Assembly of FM1 CEB (box and electronics) | ASSY | UNH |  | Nolin | done
2011-09-15 | 2011-09-19 |  | FM1 AEB testing (IRFU) | TST | IRFU |  | King | done
2011-09-15 |  |  | FRR: CEB assembly | FRR | UNH |  | Turco | done
2011-09-16 | 2011-09-28 |  | FM2 FG Sensors thermal and bakeout | TST | UCLA |  | Strangeway | done
2011-09-16 |  |  | FM1-1 HV Filament Board (ship) | DEL | UNH | IWF | Williams | done
2011-09-16 |  |  | FM1 ADP Ext. Booms (EIDP review) | DEL | ATK | LASP | Westfall | done
2011-09-16 |  |  | EDI Gun CDR follow-up (9 a.m. EDT) | CDR | UNH |  | Macri | done
2011-09-19 | 2011-09-21 |  | FM1-1 beam generation system test | TST | UNH |  | Singer | done
2011-09-20 | 2011-09-23 |  | Parylene coating of FM1 AEB boards (Sweden) | ASSY | KTH |  | King | done
2011-09-20 |  |  | FRR: EDI Sensor assembly | FRR | UNH |  | Turco | done
2011-09-20 |  |  | LVPS, AFG, DFG parylene coating complete | MILE | UNH |  | Turco | done
2011-09-21 | 2011-09-26 |  | FM1 S-BEB testing (IRFU) | TST | IRFU |  | King | done
2011-09-22 |  |  | FM1 S-BEB testing (IRFU) | TRR |  |  | King | done
2011-09-22 12:00 | 2011-09-23 |  | CDPU SW acceptance test (Needell) | TST | UNH |  | Needell | done
2011-09-23 |  |  | FM1-1 HV Filament Board (received) | DEL | UNH | IWF | Steller | done
2011-09-23 11:30 | 2011-09-23 15:00 |  | PER: FM2 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-09-26 | 2011-09-27 |  | MMS SWT | MTG | UNH |  | Torbert | done
2011-09-26 |  |  | FM1 AEB | DEL | KTH | UNH | Lindqvist | done
2011-09-26 |  |  | Current generator (GSE) | DEL | IWF | UNH | Magnes | done
2011-09-26 12:00 | 2011-09-27 |  | EM FIT testing at UNH | TST | UNH |  | Dors | done
2011-09-28 | 2011-10-03 |  | FM1 S-BEB parylene coating | ASSY | KTH |  | King | done
2011-09-28 |  |  | FM1 AEB receiving inspection (morning) |  | UNH |  | Turco | done
2011-09-28 |  |  | FRR for mag harnesses | FRR | UNH |  | Turco | done
2011-09-28 |  |  | Reynolds HV cable received at IWF | DEL | VEND | IWF | Steller | done
2011-09-28 |  |  | PRODEX/ESA approval of GDE circuit modification | DES | IWF |  | Steller | done
2011-09-28 |  |  | MMS SWG (PIs, Wed morning) | MTG | UNH |  | Torbert | done
2011-09-28 13:00 | 2011-09-29 |  | FIELDS Science Data Processing Working Group | MTG | UNH |  | Chutter | done
2011-09-29 |  |  | FM1-1 beam generation system | DEL | UNH | IWF | Singer | done
2011-09-29 |  |  | FM2 DFG Sensor | DEL | UCLA | UNH | Strangeway | done
2011-09-29 |  |  | FM1-2 HV Filament Board | DEL | UNH | IWF | Turco | done
2011-09-30 | 2011-10-03 |  | FM1 SDP Probes TV testing | TST | KTH |  | Lindqvist | done
2011-09-30 |  |  | FM2 DFG receiving inspection and EIDP review | EIDP | UNH |  | Turco | done
2011-09-30 |  |  | FM4 & FS DFG boards | DEL | UNH | IWF | Williams | done
2011-09-30 |  |  | FM2 DFG Sensor | DEL | UNH | IWF | Williams | done
2011-10-03 | 2011-10-04 |  | FM1 S-BEB parylene (Sweden) | ASSY | KTH |  | King | done
2011-10-03 | 2011-10-05 |  | FM1 SCM Sensor and Preamp | DEL/TST | LPP | UNH | Leroy | done
2011-10-03 |  |  | ADP Simulator | DEL | LASP | UNH | Westfall | done
2011-10-03 |  |  | Connector brackets for DSPs 4-7 | DEL | UNH | LASP | Nolin | done
2011-10-03 |  |  | EIDP Review: FM1 SCM | EIDP |  |  | Macri | done
2011-10-06 | 2011-10-21 |  | Final definition: FM motors & harnesses | MILE | UNH |  | King | done
2011-10-06 |  |  | FM1 CEB FFT | TST | UNH |  | Rau | done
2011-10-06 |  |  | FM1 SDP Probes (4) | DEL | KTH | UNH | King | done
2011-10-06 |  |  | FM1 S-BEB | DEL | KTH | UNH | King | done
2011-10-07 |  |  | EM4 SCM Sensor and BB Preamp (receive @ UNH) | DEL | LPP | UNH | Williams | done
2011-10-07 |  |  | FM1 AEB functional test | TST | UNH |  | Rau | done
2011-10-07 |  |  | TRR: FM1 CEB (AEB & SCM) EMI/EMC test | TRR | UNH |  | Myers | done
2011-10-10 | 2011-10-27 |  | TV chamber characterization for outgassing certification measurements | TST | UNH |  | Turco | done
2011-10-11 | 2011-10-20 |  | FM1 CEB (AEB & SCM) EMI/EMC testing @ Retlif | TST | UNH |  | Dors | done
2011-10-14 | 2011-10-21 |  | Review TV chamber data and readinesss for outgassing certificaiton with Jack Sanders | TRR | UNH |  | Turco | done
2011-10-14 |  |  | Distribute materials for EDI SW TRR | TRR | UNH |  | Briggs | done
2011-10-17 | 2011-10-18 |  | FM1-1 EDI Gun inspection (Granoff, Macri) | INS | UNH | IWF | Macri | done
2011-10-17 | 2011-11-02 |  | FM1 SCM harness bakeout and certification | TST | UNH |  | Turco | done
2011-10-17 |  |  | Connector brackets for DSPs 8-9 | DEL | UNH | LASP | Nolin | done
2011-10-24 |  |  | FG nulling coil GSE (1st of 4) | DEL | UCLA | UNH | Strangeway | done
2011-10-24 |  |  | FM1 CEB retest planning (DSP FPGA change) | FRB | SwRI |  | Black | done
2011-10-25 | 2011-10-28 |  | FM1 SDP preamp/cable rework, fine wire assy and boom wire marking @ UNH | ASSY | LASP |  | Vermeer | done
2011-10-25 |  |  | CDPU SW acceptance test (post-test review) | REV | UNH |  | Heirtzler | done
2011-10-26 |  |  | EDI FSW TRR | TRR | UNH |  | Briggs | done
2011-10-27 | 2011-11-29 |  | Plan for SDP deployments on S/C decks to GSFC | DOC | UNH | GSFC | Macri | done
2011-10-27 |  |  | ADP FM1 booms (SN01, SN02) delivery to LASP | DEL | ATK | LASP | Westfall | done
2011-10-28 |  |  | FM1 AEB (plus 2 FM1 DSP boards and 1 EM A-BEB) & ADP simulator | DEL | UNH | LASP | Rau | done
2011-10-29 |  |  | FM1-2 EDI beam generation system | DEL | UNH | IWF | Singer | done
2011-10-31 | 2011-11-02 |  | CIDP Road Show at GSFC | TST | UNH |  | Needell | done
2011-10-31 |  |  | FIELDS Simulator (received at SwRI) | DEL | UNH | SwRI | Chutter | done
2011-10-31 |  |  | EM4 SCM Sensor deliver to GSFC for tests with qual boom | DEL | UNH | GSFC | Rau | done
2011-11-02 |  |  | EM4 SCM Sensor installation on QM mag boom (GSFC) | INT | GSFC |  | Sturm | done
2011-11-02 |  |  | ASPOC PER | PER | IIRT |  |  | done
2011-11-03 | 2011-11-09 |  | FM1 SCM Sensor & Preamp bakeout & cert. | TST | UNH |  | Turco | done
2011-11-04 |  |  | Return EM1 AFG board to UNH | DEL | UCLA |  | Strangeway | done
2011-11-07 | 2011-11-30 |  | FM2 A-BEB PWAs | ASSY | Iowa | UNH | Turco | done
2011-11-09 |  |  | PER: FM ship set 3 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-11-10 |  |  | EDI FSW Acceptance test | TST | UNH |  | Briggs | done
2011-11-10 |  |  | TRR: FM1 SDP EMI/EMC testing (1 deployer) | TRR | UNH |  | Dors | done
2011-11-10 |  |  | TRR: FM1-1 EDI Sensor thermal and vacuum tests | TRR | UNH |  | Macri | done
2011-11-14 |  |  | FM1-1 SDP FFT | TST | UNH |  | King | done
2011-11-14 |  |  | Change soldered FPGA on EM DSP board | ASSY | LASP |  | Westfall | done
2011-11-15 | 2011-11-16 |  | FM1-1 EDI Sensor thermal test | ETST | UNH |  | Singer | done
2011-11-15 | 2011-11-18 |  | FM1 SDP EMI/EMC testing (1 deployer) | ETST | UNH |  | Dors | done
2011-11-15 |  |  | PER: FM1 SDP | PER | UNH |  | Myers | done
2011-11-17 | 2011-12-02 |  | Review EM AEB testing at LASP and plan forward | REV |  |  | Macri | done
2011-11-17 | 2011-12-07 |  | SDP preamp thermal test plan prep and review |  |  |  | Nolin | done
2011-11-17 |  |  | DSP & CDPU FPGAs (pre-burn review) | REV |  |  | Macri | done
2011-11-18 |  |  | Beam Gen Syst. Anode and focus weldments (pre- plating, receipt @ UNH) | DEL | VEND | UNH | Nolin | done. Rejected.
2011-11-22 |  |  | FM2 LVPS PWA | DEL | SYN | UNH | Turco | done
2011-11-22 |  |  | TRR: FM1 SDP vibration (1 unit) | TRR |  |  | Macri | done
2011-11-28 | 2011-12-02 |  | FM3 DFG Sensor capacitor installation | ASSY | UCLA |  | Strangeway | done
2011-11-29 | 2011-12-01 |  | FM S/N2 EDI Sensor thermal test | ETST | UNH |  | Singer | done
2011-11-30 | 2011-12-02 |  | FM1 SDP vibration (1 unit) | ETST | UNH |  | Granoff | done
2011-11-30 |  |  | FM2 A-BEB PWAs | DEL | Iowa | UNH |  | done
2011-11-30 |  |  | PER: FM ship set 4 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-12-02 | 2011-12-05 |  | FM S/N3-4 CDPU thermal tests | ETST | UNH |  | Bodet | done
2011-12-02 |  |  | FM1 AEB return to UNH for repair | DEL | LASP | UNH | King | done
2011-12-03 |  |  | FM2 LVPS PWA | DEL | UNH | KTH | Turco | done
2011-12-05 |  |  | FM3 LVPS PWA | DEL | SYN | UNH | Turco | done
2011-12-05 |  |  | Burn 2nd FPGA for FM1 DSP | ASSY | UNH | LASP | Summers | done
2011-12-07 |  |  | Beam Gen Syst. weldments (in process inspection) Done for one set. Okay. Go-ahead for remainder given to vendor | MILE | UNH |  | Salwen | done
2011-12-08 | 2011-12-09 |  | FM SDP preamp TV survival cycle (3 units, S/N2-4) | ETST | UNH |  | Nolin | done
2011-12-08 |  |  | SDP preamp thermal model and test plan review | REV |  |  | Macri | done
2011-12-12 | 2011-12-16 |  | CDPU S/Ns 3&4 parylene coating | ASSY | SCS |  | Turco | done
2011-12-12 | 2011-12-16 |  | EDI Gun Support Collar wiring at UNH. | ASSY | Iowa | UNH |  | done
2011-12-14 | 2011-12-16 |  | SOC peer review and TIM | REV |  |  | Needell | done
2011-12-14 |  |  | FM1 AEBs (modified) to KTH for test | DEL | UNH | KTH | King | done
2011-12-14 |  |  | FM3 LVPS PWA | DEL | UNH | KTH | King | done
2011-12-20 |  |  | Mount thermal HW on FM1 CEB | ASSY | UNH |  | Nolin | done
2011-12-20 |  |  | FM1 AEB (tested) return to UNH | DEL | KTH | UNH | King | done
2011-12-20 |  |  | FM2 LVPS | DEL | KTH | UNH | King | done
2011-12-21 |  |  | FM1 GDE | DEL | RUAG | IWF | Steller | done
2012-01-03 |  |  | FM1 AEB (tested) return to LASP | DEL | UNH | LASP | King | done
2012-01-04 |  |  | FM4&FS LVPS PWAs | DEL | SYN | UNH | Turco | done
2012-01-05 | 2012-01-06 |  | SDP 2 - 4 Preamp TV Retest | ETST | UNH |  |  | done
2012-01-05 | 2012-01-18 |  | Syntech FM2 set SBEB assembly | ASSY | SYN |  | Turco | done
2012-01-05 |  |  | PER: FM3 FG Sensors (Webex) | PER | UCLA |  | Strangeway | done
2012-01-06 |  |  | FM1 DSP boards (return to UNH) | DEL | LASP | UNH | Wesfall | done
2012-01-09 |  |  | TRR: EQM SDP Vibration | TRR | UNH |  | Macri | done
2012-01-09 |  |  | PER: FM2/3 SCM (WebEx) | PER | LPP |  | Leroy | done
2012-01-10 | 2012-01-11 |  | IS SIR | SIR |  |  |  | done
2012-01-10 | 2012-01-11 |  | EQM SDP Vibe | ETST | UNH |  | Granoff | done
2012-01-10 |  |  | FM1 GDE secondary ground isolation problem | PROB | RUAG | IWF | Steller | done
2012-01-10 |  |  | TRR: FG3 vibration and thermal | TRR |  |  |  | done
2012-01-11 |  |  | Discussion of SDP damping test | REV | GSFC |  | Frost | done
2012-01-13 |  |  | TRR: FM SCM sets 2&3 environmental tests | TRR |  |  | Macri | done
2012-01-16 | 2012-02-24 |  | FM2 set SCM environmental tests | ETST | LPP |  | Leroy | done
2012-01-17 | 2012-01-20 |  | SDP S/N 1 and EQM vibration | ETST | UNH |  |  | done
2012-01-17 | 2012-01-20 |  | SDP FM SN2-4 Preamp/Sphere integration | ASSY | UNH |  | King | done
2012-01-17 |  |  | FM2 set SDP Preamps and 5-8 doors | DEL | LASP | UNH | Westfall | done
2012-01-17 |  |  | Prep FM2 set SDP preamps for TV test | ASSY |  |  | King | done
2012-01-18 | 2012-01-20 |  | TV test FM S/N5-8 SDP Preamps | ETST | UNH |  | King | done
2012-01-18 |  |  | EDI beam gen system weldments (remaining anode and focus units) | DEL | VEND | UNH | Salwen | done
2012-01-18 |  |  | PER: FM1 CEB (@UNH) | PER | UNH |  | Myers | done
2012-01-20 |  |  | FM2 S-BEB PWA | DEL | SYN | UNH | Turco | done
2012-01-20 |  |  | TRR: FM1 CEB vibration | TRR |  |  | Macri | done
2012-01-23 |  |  | PER: FM1 pair Receiving Elements (@LASP) | PER | LASP |  | Westfall | done
2012-01-25 | 2012-01-27 |  | FM1 CEB vibration | ETST | UNH |  | Nolin | done
2012-01-30 | 2012-03-15 |  | FM3 set SCM vibration | ETST | LPP |  | Leroy | Done.
2012-01-30 | 2012-03-15 |  | FM3 set SCM vibe | ETST | LPP |  | Leroy | done
2012-01-30 |  |  | TRR: FM1 set Receiving Elements vibration | TRR | LASP |  | Westfall | done
2012-01-31 |  |  | PER: FM1 AEB (WebEx) | PER | LASP |  | Westfall | done
2012-02-01 | 2012-02-03 |  | Baseline outgassing measurements for FM1 CEB | ETST | UNH |  | Turco | done
2012-02-01 | 2012-02-03 |  | FM1 set Receiving Elements vibration | ETST | LASP |  | Westfall | done
2012-02-03 |  |  | SDP deployment problem (update for project) | MTG | UNH |  | Macri | done
2012-02-03 |  |  | TRR: FM1 AEB vibration testing | TRR | LASP |  | Macri | done
2012-02-03 09:00 |  |  | TRR: FM1 CEB TV | TRR |  |  | Macri | done
2012-02-06 |  |  | FM1 AEB vibration testing | ETST | LASP |  | Westfall | done
2012-02-07 |  |  | FM3 DFG Sensor. Return 2nd tuning harness to UNH. | DEL | UCLA | UNH | Rowe | Done.
2012-02-09 | 2012-02-10 |  | SDP vibration investigation | ETST | UNH |  | Granoff | done
2012-02-10 |  |  | TRR: FM1 Receiving Element TV testing | TRR | LASP |  | Westfall | done
2012-02-11 | 2012-02-16 |  | Myers at IWF (schedule work) |  | UNH |  |  | done
2012-02-11 |  |  | FM3 DFG Sensor | DEL | UNH | IWF | Myers | done
2012-02-13 | 2012-03-01 |  | FM1 Receiving Element TV testing | ETST | LASP |  | Westfall | Done.
2012-02-17 | 2012-02-24 |  | FM2 SCM Preamp TV | ETST | LPP |  | Leroy | done
2012-02-17 |  |  | TRR: FM2 AFG/DFG Joint Calibration | TRR |  |  | Magnes | Done.
2012-02-21 |  |  | Deliveries to KTH: FM2 AEB (modified), FM2 set S-BEB (modified) PWAs, FM2 set SDP Preamp/Cable assemblies, and FM4 & FM5 LVPS. | DEL | UNH | KTH | King | Done.
2012-02-21 |  |  | SDP vibration investigation (radial clamp) | ETST | UNH |  | Granoff | Done.
2012-02-22 |  |  | TRR: FM1 CEB vibration (workmanship, 1 axis) | TRR | UNH |  | Macri | Done.
2012-02-23 |  |  | TRR: FM1 AEB TV Test | TRR | LASP |  | Westfall | Done.
2012-02-23 |  |  | FM1 CEB vibration (workmanship, 1 axis) | ETST | UNH |  | Nolin | Done.
2012-02-24 | 2012-03-01 |  | FM1 AEB TV Test | ETST | LASP |  | Westfall | done
2012-02-24 | 2012-03-08 |  | FM1 CEB TV | ETST | UNH |  | Rau | done
2012-02-24 |  |  | TRR: FM1 CEB TV | TRR | UNH |  | Macri | Done.
2012-02-24 |  |  | Submit GFY13 PPBE | DEL | UNH |  | Macri | done
2012-02-24 |  |  | Return EM4 SCM Sensor to UNH | DEL | GSFC | UNH | Sturm | done
2012-02-27 |  |  | SDP deployment problem (update for project) | REV | UNH |  | Granoff | done
2012-02-28 | 2012-03-09 |  | FM2 AFG/DFG Joint Calibration | ETST |  |  | Magnes | done
2012-02-29 |  |  | Update on ADP Boom plan forward | MTG | LASP |  | Westfall | done
2012-03-01 |  |  | ***CANCELLED***. EQM SDP delivery to GSFC for qual deck testing | DEL | UNH | GSFC | King | Done.
2012-03-05 | 2012-03-14 |  | FM1 AEB-RE calibration | TST | LASP |  | Ergun | done
2012-03-05 | 2012-03-15 |  | FM2 SCM Calibration | ETST | LPP |  | Leroy | done
2012-03-10 |  |  | Tested hardware delivery (FM2 AEB, Probes through BEBs S/Ns 5-8) | DEL | KTH | UNH | King | done
2012-03-12 |  |  | EDI Correlator (Xilinx) peer review | REV | UNH |  | Vaith | done
2012-03-14 |  |  | FRR: EDI GDU (internal review) | FRR | UNH |  | Turco | Done.
2012-03-14 |  |  | FRR: EDI GDU (internal review) | FRR | UNH |  | Turco | Done.
2012-03-16 | 2012-03-22 |  | Repeat SCM Preamp S/N4 TV test | ETST | LPP |  | Leroy | done
2012-03-16 | 2012-03-23 |  | Repeat SCM Preamp S/N4 (SCM SS#3) TV test | ETST | LPP |  | Leroy | done
2012-03-16 |  |  | FM1 AEB (and ADP simulators (2 channels)) Delivery | DEL | LASP | UNH | Westfall | done
2012-03-19 |  |  | FM2 CEB housing ready |  |  |  | Nolin | Done.
2012-03-20 | 2012-03-21 |  | MMS SWT (San Antonio) | MTG |  |  | Torbert | done
2012-03-20 | 2012-03-21 |  | MMS SWT (San Antonio) | MTG |  |  | Torbert | Done.
2012-03-20 |  |  | EM4 SCM Sensor delivery to LPP. Thermal test for verification following QM boom deploy (shock) test | DEL | UNH | LPP | Williams | done
2012-03-20 |  |  | SDP ship set #4 boom cables (and spares?) | DEL | UNH | LASP | Beckman | done
2012-03-21 |  |  | S/N3 EDI Beam Gen Syst | DEL | UNH | IWF | Vaith | done
2012-03-22 | 2012-03-23 |  | SDP prototype (SN1 w/ RWC) vibe | ETST | UNH |  | Granoff | done
2012-03-22 |  |  | MMS SWG |  |  |  | Torbert | done
2012-03-22 |  |  | TRR: FIELDS FM1 FIT (timing) testing | TRR | UNH |  | Macri | done
2012-03-22 |  |  | MMS SWG |  |  |  | Torbert | Done.
2012-03-22 |  |  | FM2 CEB housing assembly complete | DEL | UNH | UNH | Nolin | done
2012-03-22 15:00 |  |  | FIELDS data processing meeting (San Antonio) | MTG |  |  | Torbert | done
2012-03-22 15:00 |  |  | FIELDS data processing meeting (San Antonio) | MTG |  |  | Torbert | done
2012-03-23 |  |  | New over-shield material for SCM harnesses | DEL | UNH | LPP | Turco | done
2012-03-23 |  |  | FM2 AEB | DEL | UNH | LASP | Rau | done
2012-03-26 | 2012-03-28 |  | FIELDS FM1 FIT (part 1, magnetometer timing) testing. FM1 CEB, AFG, DFG, SCM | TST | UNH |  | Dors | done
2012-03-26 | 2012-05-25 |  | FM1 FIELDS I&T: CPT, FIT, procedure and script development | TST | UNH |  | Rau | done
2012-03-26 |  |  | FM2 AFG Delivery and acceptance test. | DEL | UCLA | UNH | Strangeway | done
2012-03-26 |  |  | TRR: FIELDS FM1 FIT test part 1 (magnetometer timing) | TRR | UNH |  | Macri | Done.
2012-03-27 | 2012-03-28 |  | SwRI PMs at UNH (schedule review) | MTG | UNH |  | Macri | done
2012-03-27 | 2012-03-30 |  | SDP prototype (SN1 w/ RWC) vibe | ETST | UNH |  | Granoff | Done.
2012-03-27 |  |  | FM2 DFG delivery and acceptance test | DEL | IWF | UNH | Valavanoglou | done
2012-03-29 |  |  | S/N3 & 4 EDI Beam Gen Syst | DEL | UNH | IWF | Valavanoglou | done
2012-03-29 |  |  | FM3 set A-BEB PWA | DEL | SYN | UNH | Turco | Done.
2012-04-03 | 2012-04-03 |  | Integrate first set EDI Optics (S/N2) with Sensor (S/N1) at UNH | ASSY | Iowa | UNH | Dvorsky | Done.
2012-04-05 | 2012-05-09 |  | EM4 SCM Sensor verification following QM boom deploy (shock) test | ETST | LPP |  | Alison | done.
2012-04-10 |  |  | Peer Review: SDP RWC mechanism | REV | UNH |  | Granoff | done
2012-04-11 | 2012-04-18 |  | SNs 3&4 EDI Sensor boards ready for bench testing | ASSY | UNH |  | Tyler | done
2012-04-11 |  |  | FM2 LVPS ready for CEB I&T (incoming functional test wth UNH GSE) | TST | UNH |  | Troop | done
2012-04-12 | 2012-04-20 |  | FM S/N2 EDI Gun & GDE (first unit). IWF support at UNH | ASSY | IWF | UNH | Steller | done
2012-04-12 | 2012-04-24 |  | FM SN2 GDU (1st unit) integration | ASSY | UNH |  | Vaith | done
2012-04-13 |  |  | FM1 and FM2 ship sets ADP booms (S/Ns 1-4) | DEL | ATK | LASP |  | done
2012-04-16 | 2012-04-24 |  | Parylene coating of FM2 CDPU A&B, AFG, DFG, EDI Controller | ASSY | UNH |  | Turco | done
2012-04-17 | 2012-04-19 |  | FM S/N2 GDU integration (Iowa support) | ASSY | Iowa |  | Bounds | Done.
2012-04-17 | 2012-05-15 |  | Revised random environment analyses for SDP | ANA | GSFC | UNH | Dirks | done
2012-04-17 | 2012-05-15 |  | Revised random environment analyses for EDI | ANA | GSFC | UNH | Dirks | done.
2012-04-19 | 2012-04-20 |  | FIELDS FM1 FIT testing (AEB timing) FM1:CEB, AEB | TST | UNH |  | Dors | done
2012-04-20 |  |  | Remaining Gun DFL2 PWBs | DEL | UNH | IWF | Steller | Done.
2012-04-20 |  |  | SDP preamp/cable assemblies (S/Ns 9-12) | DEL | LASP | UNH | Vermeer | done
2012-04-23 |  |  | Return EM AEB to LASP | DEL | UNH | LASP | Rau | Done.
2012-04-23 |  |  | Nulling Coil GSE. UCLA will send 2 with a SW update; return 1 to UCLA for addional coil turns. | DEL | UCLA | UNH | Strangeway | done
2012-04-24 |  |  | FM2 BPM ready for FM2 CEB | DEL | UNH |  | Bodet | done
2012-04-24 |  |  | STP file for AEB interface plate | DEL | LASP | SwRI | Tucker | done
2012-04-25 |  |  | TRR: S/N2 GDU bench test | TRR | UNH |  | Macri | done
2012-04-25 12:00 | 2012-04-26 |  | GDU SN2 bench test | TST | UNH |  | Vaith | done
2012-04-26 |  |  | FM2 CDPU (2) delivery to CEB | DEL | UNH | UNH | Turco | done
2012-04-26 |  |  | Discussion of ADP and SDP deployment test plans at Obs. | MTG |  |  | Pope | done
2012-04-26 |  |  | FM2 DFG Delivery to CEB | DEL | UNH | UNH | Turco | Done.
2012-04-30 | 2012-05-03 |  | FM2 SCM Harness outgassing certification | ETST | LPP |  | Alison | Done.
2012-04-30 |  |  | PER: FM2 set AEB and Receiving Elements | PER |  |  |  | Done.
2012-04-30 |  |  | TRR: FM2 set Receiving Elements vibration | TRR | LASP |  |  | done
2012-05-02 | 2012-05-04 |  | SDP S/N1 vibration (RWC on new outer cylinder) | VIB | UNH |  | Granoff | Done.
2012-05-03 |  |  | FM2 EDI Contrtoller Delivery to CEB | DEL | UNH | UNH | Turco | done
2012-05-03 |  |  | FM2 AFG Delivery to CEB | DEL | UNH | UNH | Turco | done
2012-05-07 | 2012-05-18 |  | FM3 DFG TU-BS calibration |  |  |  |  | Done.
2012-05-07 |  |  | S/N2 GDU FFT (room 145 chamber) | ETST |  |  | Singer | Done.
2012-05-07 |  |  | TRR: FM2 AEB TV test | TRR |  |  |  | done
2012-05-08 | 2012-05-16 |  | S/N2 GDU characterization (room 145 chamber) | ETST | UNH |  | Singer | Done.
2012-05-08 |  |  | TRR: S/N2 GDU vacuum test and characterization | TRR | UNH |  | Macri | done
2012-05-11 |  |  | SDP thermal test plan distribution | RFA |  |  | King | done.
2012-05-15 | 2012-05-24 |  | Repair of FTS (UNH TV) | TV |  |  | Ellis | done
2012-05-17 |  |  | Outer cylinders ready for SDP S/N3 integration | ASSY | UNH |  | Granoff | done
2012-05-17 |  |  | GDU SN2 test with FM1 CEB |  |  |  | Vaith | done.
2012-05-18 | 2012-05-24 |  | FM1 SCM harness bakeout and certification (new overshield). | TV | UNH |  | Turco | done
2012-05-18 | 2012-06-05 |  | Integration SN3 SDP | ASSY | UNH |  | Granoff | done.
2012-05-18 |  |  | FIELDS FM1 FIT testing (EDI timing). FM S/N2 EDI-GDU, EM CEB. | TST | UNH |  | Dors | done.
2012-05-18 |  |  | SDP RWC covers returned from vendor PFE | DEL | VEND | UNH | Granoff | done
2012-05-18 |  |  | SDP pins returned from vendor Tiodize | DEL | VEND | UNH | Granoff | done
2012-05-18 |  |  | SDP boom cable S/Ns 17-18 | DEL | UNH | LASP | Beckman | done
2012-05-18 |  |  | TRR: SN FM2 EDI GDU EMI/EMC Testing (1st unit). | TRR | UNH |  | Macri | done.
2012-05-21 | 2012-05-25 |  | SN FM2 EDI GDU EMI/EMC Testing (1st unit). | ETST |  |  | Dors | done
2012-05-21 |  |  | Fluxgate harness deliveries | DEL | UCLA | UNH |  | done.
2012-05-21 |  |  | PER: S/N2 EDI GDU (1st unit) | PER |  |  | Myers | done.
2012-05-22 | 2012-05-23 |  | PSR: FM1 FIELDS (partial) delivery to IS (includes all except EDI & SDP) | PSR | UNH |  | Myers | done
2012-05-22 |  |  | FM2 set DSP (2) Delivery | DEL | LASP | UNH | Westfall | done
2012-05-23 | 2012-05-24 |  | SDP Sphere/Preamp integration s/ns 3 and 4 and crimping outer guards with probes for 5 and 6. Vermeer support | ASSY | UNH |  | King | done.
2012-05-23 |  |  | Return SN1 Gun Support Collar to UNH | DEL | Iowa | UNH | Bounds | done
2012-05-23 |  |  | FM SDP Doors F/Ms 9-16 | DEL | LASP | UNH | Vermeer | done
2012-05-25 |  |  | Test FM1 AFG/DFG harnesses with FIELDS | TST | UNH |  | Rau | done.
2012-05-29 | 2012-06-01 |  | FM4 DFG Sensor Capacitor installation | ASSY |  |  | Valavanoglou | done.
2012-05-29 | 2012-06-05 |  | Return SN1 and SN3 EDI Gun BGS to UNH for filament swap and short investigation | DEL | IWF | UNH | Steller | done.
2012-05-29 | 2012-06-05 |  | TV survival test: SDP ship set 3 preamp/cable assemblies (S/Ns 9-12). | TV | UNH |  | King | done
2012-05-29 |  |  | TRR: EDI GDU SN2 Vibe | TRR |  |  |  | Done.
2012-05-29 |  |  | EM4 SCM Sensor return to UNH | DEL | LPP | UNH | Alison | Done.
2012-05-30 | 2012-05-31 |  | FM1 FIELDS (partial) Delivery to IS. FM1 CEB, DFG, AFG and SCM and Harnesses, SDPs: (SN1, FIT BEBs w/ motor and HOP load sims) ; | DEL | UNH |  | Rau | done
2012-05-30 | 2012-06-01 |  | S/N 2 EDI GDU Vibration Testing (1st unit) | VIB |  |  | Granoff | done
2012-05-31 | 2012-06-15 |  | FIELDS FM1 IS I&T (except SDP and GDU) | TST | UNH |  | Rau | done.
2012-06-04 | 2012-06-17 |  | Calibration: FM2 set RE & AEB | TST | LASP |  | Tucker | done
2012-06-04 |  |  | ADP Simulator and test harness for IS | DEL | LASP | UNH | Tucker | Done.
2012-06-06 |  |  | BGS S/N5 | DEL | UNH | IWF | Singer | done
2012-06-06 |  |  | TRR: S/N2 EDI GDU TV Testing | TRR |  |  | Macri | Done.
2012-06-07 | 2012-06-28 |  | S/N2 EDI GDU TV Testing | TV |  |  | Vaith | done
2012-06-07 |  |  | FM3 set S-BEB PWAs | DEL | SYN | UNH | Turco | Done.
2012-06-07 |  |  | FM2 DSP boards acceptance test | TST | UNH |  | Dors | done
2012-06-11 |  |  | Delta PER: SDP S/sN 3&4 (WebEx agreed) | PER | UNH |  | Myers | done
2012-06-11 |  |  | TRR: SDP S/N3 & 4 vibration | TRR | UNH |  | Granoff | done
2012-06-12 | 2012-06-15 |  | FM SDP SN3-4 Vibration Testing | VIB |  |  | Granoff | done
2012-06-12 |  |  | FM3 AEB | DEL | UNH | KTH | King | done
2012-06-15 |  |  | FM2 CEB mehanical assemby complete | ASSY | UNH |  | Nolin | done
2012-06-20 | 2012-06-21 |  | FM SDP S/N 3 EMI/EMC CE and magnetics test (@UNH) | ETST | UNH |  | Dors | Done.
2012-06-20 |  |  | FM2 AEB | DEL | LASP | UNH | Tucker | done
2012-06-20 |  |  | TRR: FM SDP S/Ns 3&4 EMI/EMC tests (@UNH) | TRR | UNH |  | Dors | done
2012-06-22 |  |  | FM4&5 AEB boards | DEL | SYN | UNH | Turco | done
2012-06-25 | 2012-06-26 |  | FM2 CEB 1st FFT | TST | UNH |  | Dors | done
2012-06-26 |  |  | PER: FM4 AFG/DFG Sensors | PER | UCLA |  | Strangeway | done
2012-06-26 |  |  | TRR: FM4 AFG/DFG Sensors (all env tests) | TRR | UCLA |  | Strangeway | done
2012-06-28 | 2012-06-29 |  | FM SDP S/N 4 EMI/EMC test (@UNH) | ETST | UNH |  | Dors | done
2012-06-28 |  |  | SDP TV test procedure for review. | REV |  |  | Beckman | done
2012-06-29 |  |  | Outgassing certification of SS#1 ADP booms | TST | LASP |  | Tucker | done
2012-06-29 |  |  | TRR: FM SDP SN3-4 TV Testing | TRR | UNH |  | Macri | done
2012-06-29 |  |  | AFG tuning harness | DEL | UNH | UCLA | Rau | done
2012-07-03 | 2012-07-20 |  | FM SDP SN3-4 TV Testing | TV | UNH |  | King | done
2012-07-09 |  |  | FIELDS ADP Simulator | DEL | LASP | UNH | Tucker | done
2012-07-09 |  |  | Fluxgate Sensor labels for bakeout | DEL | UCLA | SwRI | Strangeway | done.
2012-07-11 | 2012-07-12 |  | PER: FM2 CEB | PER | UNH |  | Myers | done.
2012-07-11 |  |  | TRR: FM2 CEB EMI/EMC CE testing @UNH | TRR | UNH |  | Dors | done
2012-07-13 | 2012-07-13 |  | FM2 CEB EMI/EMC CE testing @UNH | EMI | UNH |  | Dors | done
2012-07-16 | 2012-08-22 | CEB | FM3 set CDPU boards assembly | ASSY | UNH |  | Googins/Jones | done
2012-07-16 |  | CEB | TRR: CEB FM2 vibration | TRR | UNH |  | Macri | done
2012-07-17 | 2012-07-18 | CEB | CEB FM2 vibration | VIB | UNH |  | Nolin | done.
2012-07-23 | 2012-07-26 | FIELDS | Magnetometer acceptance testing at UNH ( AFG FM3 AT, DFG FM3 AT, SCM FM2 AT, SCM FM3 AT) | TST | UNH |  | Rau | done
2012-07-23 |  | AFG | FM3 AFG (and test harnesses) | DEL | UCLA | UNH | Rowe | done
2012-07-23 |  | DFG | FM4 DFG Sensor | DEL | UCLA | UNH | Rowe | done
2012-07-24 |  | DFG | FM3 DFG | DEL | IWF | UNH | Valavanoglou | done
2012-07-25 | 2012-07-26 | SCM | FM2 SCM (Sensor, Preamp and harness) and FM3 SCM (Sensor and Preamp only) | DEL | LPP | UNH | Leroy | done
2012-07-26 |  | DFG | FM4 DFG Sensor | DEL | UNH | IWF | Valavanoglou | done.
2012-07-27 | 2012-08-09 | CEB | FM2 CEB TV | TV | UNH |  | Rau | done
2012-07-27 |  | CEB | TRR: FM2 CEB TV | TRR | UNH |  | Macri | done
2012-07-30 | 2012-08-28 | SDP | S-BEB boards (SNs 13-18) assembly | ASSY | SYN |  | Turco | done
2012-07-31 | 2012-08-03 | EDI | Study Inductor placement on HV-FIL Bd SN5 |  | UNH |  | Turco | done
2012-07-31 |  | EDI | EDI GDU S/N2 Magnetics testing | TST | UNH |  | Dors | done.
2012-08-01 | 2012-08-03 | SDP | SDP SNs 5&6 FFT | TST | UNH |  | King | done
2012-08-02 | 2012-08-03 | SDP | SDP 3&4 FIT testing (with EM CEB) | TST | UNH |  | Dors | done
2012-08-07 |  | SDP | PER: SDP SNs 5&6 | PER |  |  | Myers | done
2012-08-07 |  | SDP | TRR: SDP SNs 5&6 Vibration | TRR | UNH |  | Macri | done
2012-08-07 |  | ADP | FM2 AEB acceptance test | TST | UNH |  | Rau | done.
2012-08-07 |  | AFG | 2 more AFG/DFG Nulling Coils | DEL-U | UCLA | UNH | Rowe | done
2012-08-08 | 2012-08-10 | EDI | SN1&3 BeamGenSys Disassembly&Inspection |  | UNH |  | Singer | done
2012-08-08 | 2012-08-10 | SDP | SDP SNs 5&6 Vibration | VIB | UNH |  | Granoff | done
2012-08-08 | 2012-08-22 | CEB | FM3 BPM assembly | ASSY | UNH |  | Googins | done
2012-08-08 |  | EDI | GDU SN2 Cleaning and Bagging for Shipment |  | UNH |  | Singer | done
2012-08-10 | 2012-08-24 | EDI | Sensor SN4 Board Parylening | ASSY | UNH |  | Singer | done.
2012-08-10 |  | SDP | FM9-12 SDP preamp /cables assemblies. FM9-12 SDP BEB. FM4-5 AEB. | DEL | UNH | KTH | King | done
2012-08-10 |  | ADP | FM4-5 AEB. | DEL | UNH | KTH | King | done
2012-08-12 |  | EDI | GDU S/N2 & SDP S/Ns 3&4 (EM CEB-SDP supports testing) | DEL-G | UNH | GSFC | Needell | done
2012-08-13 | 2012-08-14 | SDP | SDP S/N3&4 bench test, inspection, I&T | PDS | UNH |  | Needell | done
2012-08-13 | 2012-08-17 | IS | GDU SN2 bench test, inspection integration with IS#1 | PDS | UNH |  | Vaith | done
2012-08-13 | 2012-08-20 | SDP | SDP SN5-6 EMI/EMC testing | EMI | UNH |  | Dors | done
2012-08-13 | 2012-08-24 | FIELDS | FM2 FIELDS I&T and Magnetometer FIT (CEB, AEB, SCM, Mags, SDP 5/6, SDP01/QM) | TST | UNH |  | Rau | done
2012-08-17 |  | CEB | FM3-5 LVPS | DEL-U | KTH | UNH | King | done
2012-08-17 |  | ADP | FM3 AEB | DEL-U | KTH | UNH | King | done
2012-08-17 |  | SDP | 5 SDP Probes (C1, C2, D1, D2, D4) | DEL-U | KTH | UNH | King | done
2012-08-20 | 2012-10-10 | ADP | FM4-5 AEB testing | TST | KTH |  | King | FM4 ready / need dates at LASP: 23 Oct / 6 Nov.
2012-08-21 |  | AFG | FM2 Fluxgate Harnesses | DEL-U | UCLA | UNH |  | done.
2012-08-21 |  | ADP | FM3 AEB | DEL | UNH | LASP | King | done.
2012-08-22 | 2012-08-23 | SDP | SDP SNs 5&6 Penalty Vibration (microswitch issue) | VIB | UNH |  | Granoff | done
2012-08-22 | 2012-09-13 | CEB | FM3 set CDPU boards testing & final assembly | TST | UNH |  | Bodet/ Googins | done
2012-08-22 | 2012-09-21 | CEB | FM3 EDI Controller board testing & final assembly | TST | UNH |  | Gaidos/ Googins | done
2012-08-22 |  | FIELDS | FM2 AEB FIT | TST | UNH |  | Dors | done
2012-08-23 |  | FIELDS | TRR: IS#1 CPT | TRR | SwRI |  | Henry | done
2012-08-24 | 2012-08-30 | EDI | Sensor SN3 MCP module assembly | ASSY | UNH |  | Granoff/Singer | done
2012-08-24 |  | AFG | fluxgate harness segment material (10 ft., no connectors) for GSFC | DEL | UCLA | GSFC | Strangeway | done.
2012-08-24 |  | SDP | TRR: FM SDP SN5&6 TV Testing | TRR | UNH |  | Macri | done
2012-08-24 17:00 | 2012-09-07 | SDP | FM SDP SN5&6 TV Testing | TV | UNH |  | King | done
2012-08-27 | 2012-08-30 | PM | Mission SIR | MTG | GSFC |  | Torbert/Macri | done.
2012-08-27 | 2012-08-31 | EDI | Sensor SN3 final assy/staking w/o MCP module | ASSY | UNH |  | Granoff/Singer | done
2012-08-27 | 2012-08-31 | EDI | Sensor SN3 assembly with MCP module | ASSY | UNH |  | Granoff/Singer | done
2012-08-28 | 2012-08-29 | SDP | SDP SN1 and QM BEB (for IS#1 CPT) | DEL-G | UNH | GSFC | Rau/King | done.
2012-08-29 | 2012-10-05 | SDP | S-BEB boards (SNs 13-16) complete assembly | ASSY | UNH |  | Googins | done
2012-08-29 |  | CEB | FM2 CEB EMI/EMC Magnetics testing | EMI | UNH |  | Dors | done.
2012-08-30 | 2012-08-31 | SDP | SDP SN1 and QM BEB I&T (for IS#1 CPT) | PDS | UNH | GSFC | Rau/Needell | done
2012-09-04 | 2012-09-06 | ADP | QM ADP Boom and Receiving Element delivery to GSFC | DEL-G | LASP | GSFC | Tucker/ Henry | done
2012-09-05 | 2012-09-12 | IS | IS#1 CPT (with FIELDS Support @GSFC) | PDS | UNH |  | Rau/Needell | done
2012-09-05 |  | ADP | ADP Simulator and test harness for S/C | DEL | LASP | UNH | Tucker | done
2012-09-07 |  | ADP | PER: FM3 set ADP RE and AEB; FM4 set RE? [chair: Dirks] | PER | LASP |  | Tucker | done
2012-09-08 |  | FIELDS | Mount thermistors on FM2 set AEB and SCM Preamp | ASSY | UNH |  | Salwen / Nolin | done
2012-09-10 |  | FIELDS | PSR (WebEx): FM2 FIELDS (partial) delivery to IS (includes all except EDI & SDP) [chair: Stone] | PSR | UNH |  | Myers | done
2012-09-11 | 2012-09-13 | Sci | MMS SWT @GSFC | MTG |  | GSFC | Torbert | done
2012-09-11 | 2012-09-14 | EDI | SN1 Sensor/Optics pre-integration | ASSY | Iowa |  | Dvorsky | done
2012-09-11 |  | EDI | Shipment of GDE/Gun SN1 | DEL-U | IWF | UNH | Steller | done
2012-09-11 |  | FIELDS | Current Generator return to IWF (Carnet expires end of Sep) | DEL | UNH | IWF | Chutter | done
2012-09-12 | 2012-09-14 | Sci | MMS SDWT & Data Processing TIM (Riesberg) @GSFC | MTG |  | GSFC | Torbert/ Chutter | done
2012-09-13 | 2012-09-19 | EDI | GDU SN1 Assembly | ASSY | UNH |  | Granoff | done
2012-09-13 |  | SDP | SDP SN5-6 Magnetics testing | EMI | UNH |  | Dors/ King | done
2012-09-13 |  | DFG | Return current generator to IWF | DEL | UNH | IWF | Magnes | done
2012-09-17 | 2012-09-20 | ADP | Integration of QM ADP Boom and Receiving Element on qual S/C deck | PDS | LASP |  | Tucker/ Mack | done
2012-09-17 | 2012-09-28 | FIELDS | FM2 FIELDS (partial) I&T (incl SDP SN1 and QM BEB) | PDS | UNH |  | Bodet/ Dors (Needell untill 22 Sep) | done
2012-09-17 |  | SCM | PER: FM4 set SCM [chair: Dirks] | PER | LPP |  | Alison | done
2012-09-17 |  | FIELDS | FM2 FIELDS (partial) delivery/I&T | DEL-G | UNH | GSFC | Dors/ Bodet | done
2012-09-18 | 2012-09-28 | IS | IS#1 burst and FDC tests | PDS | UNH |  | Needell | done
2012-09-19 | 2012-09-21 | SDP | SDP 7-10 probe to preamp assembly and remaining preamp cable deliveries | ASSY |  |  | King | done
2012-09-19 |  | CEB | FM1 CEB CDPUA C-RAM test on IS#1 (NCR investigation) | TST | UNH |  | Bodet/ Needell | done
2012-09-19 |  | SDP | SDP preamp/cable assemblies (S/Ns 13-16) | DEL-U | LASP | UNH | Tucker | done
2012-09-19 |  | SDP | SDP preamp/cable assemblies (S/Ns 17-18) | DEL-U | LASP | UNH | Tucker | done
2012-09-19 |  | SDP | SDP Doors SN17 - SN18 | DEL-U | LASP | UNH | Tucker | done
2012-09-19 |  | EDI | 20 HV Opto-Couplers for partial discharge testing | DEL-U | IWF | UNH | Steller | done
2012-09-24 | 2012-10-08 | EDI | 20 HVOCs partial discharge tests (round 1) | TST | UNH |  | Widholm
2012-09-21 | 2012-09-26 | EDI | GDU SN1 Baseline Vacuum FFT | VAC | UNH |  | Vaith | done
2012-09-21 |  | EDI | BGS S/N 6&8. | DEL | UNH | IWF | Myers/ Steller | done.
2012-09-21 |  | EDI | SN5&6 HV&FIL board | DEL | UNH | IWF | Myers/ Steller | done.
2012-09-25 |  | AFG | FM1 Mag Boom alignment test and verification | TST | GSFC |  | Sturm | Status?
2012-09-26 | 2012-10-12 | EDI | SNs 7, 8 & 9 Sensor Digital boards - partial assembly | ASSY | Iowa |  | Bounds/ Kutcher | underway
2012-09-27 | 2012-10-08 | CEB | Stake and coat FM3 set CDPU, EDI Controlller, DFG, AFG boards | ASSY | UNH |  | Turco/ Specialty Coatings | Ready date confirmed by Turco
2012-09-26 |  | EDI | SNs 5&6 Sensor Digital board kits to Iowa | DEL | UNH | Iowa | Turco | done.
2012-10-01 | 2012-10-08 | EDI | Sensor SN4 final assy/staking w/o MCP module | ASSY | UNH |  | Singer/ Granoff | likely delayed by gdu1 vibe testing
2012-09-27 |  | FIELDS | IS#1 Acceptance Review with Project (Part-1, mechanical) | REV | UNH |  | Macri/ Rau | done
2012-09-27 |  | FIELDS | TRR: Obs. Risk Reduction EMI/EMC Test (Obs) | TRR | GSFC |  | Won/ Dors/ Rau | done
2012-09-28 |  | EDI | GDU SN1 PER [Chair: Stone] | PER | UNH |  | Myers/ Vaith, Steller | done.
2012-09-28 | 2012-10-02 | EDI | Sensor SN3 Vacuum Test | VAC | UNH |  | Singer | done
2012-10-02 | 2012-10-04 | SDP | SDP preamp workmanship (SNs 13-16) | TV | UNH |  | King/ Troop, Frost | underway
2012-10-01 |  | EDI | Sensor SN3 Electrical Test | TST | UNH |  | Singer | done.
2012-10-03 |  | EDI | GDU SN1 EMI test | EMI | UNH |  | Dors/ Vaith | done
2012-10-03 |  | EDI | TRR: GDU SN1 vibration test | TRR | UNH |  | Granoff/ Macri
2012-10-04 |  | SDP | PSR (IIRT @UNH): FM1 set SDP (4 units) (SNs 3, 4, 5, &6) [chair: Phan] | PSR | UNH |  | Myers | 8 a.m. EDT start.
2012-10-08 | 2012-10-19 | SCM | TQCM measurement FM3 SCM harness | TST | LPP |  |  | Date from Alison, 02 Oct
2012-10-08 |  | FIELDS | IS#1 Acceptance Review with Project (Part-2) | REV | UNH |  | Macri/ Rau, Needell, Chutter | Report on FIELDS IS CPT and burst test, incl. post-test data analysis.
2012-10-09 | 2012-10-11 | EDI | GDU SN1 vibration | VIB | UNH |  | Granoff | BAE reservation in place.
2012-10-09 | 2012-10-15 | EDI | Sensor SN4 assembly with MCP module | ASSY | UNH |  | Granoff/ Singer
2012-10-09 |  | DSP | FM3 set DSP boards (SNs 5&11) | DEL-U | LASP | UNH | Tucker | SN11 received
2012-10-10 |  | FIELDS | FM2 FIELDS trend data | REV | UNH | SwRI | Rau | Open work from PSR
2012-10-10 |  | SDP | S-BEB boards (SNs 13-16), preamp/cable assemblies (13-16). | DEL | UNH | KTH | King | Date is next planned King trip to KTH.
2012-10-12 | 2012-10-26 | EDI | GDU SN1 TV | TV | UNH |  | Vaith
2012-10-12 |  | EDI | 20 HVOCs first return to IWF for screening | DEL | UNH | IWF
2012-10-12 |  | FIELDS | SCM Preamp install on S/C#1 | PDS |  |  | Rau | Date from Ron Black's 21 Sep SMART telecon. FIELDS support?
2012-10-12 |  |  | Mag harness integration on S/C#1 | PDS |  |  | Rau | Date?
2012-10-15 | 2012-10-19 | CEB | FM3 CEB assembly | ASSY | UNH |  | Rau/ Nolin | Date from Rau, 26 Sep
2012-10-15 | 2012-10-19 | EDI | BeamGenSys SN1&3 refurbishment & testing | TST | UNH |  | Singer
2012-10-15 | 2012-10-19 | ADP | Qual deck vibe testing (LASP support remotely) | PDS | LASP |  | Tucker
2012-10-15 |  | FIELDS | SOC real-time telemetry flow to Instrument Team Facilities | TST | SOC |  | Pankratz/ Needell? / Mello | Date?
2012-10-15 |  | SDP | SDP (1-unit) calibration in Faraday cage at LASP. Ergun: Goal is directly comparable ADP and SDP calibrations. Can be FM or fully representative EM. | TST | UNH | LASP | King | Do this? If so, when? Test in Uppsala should preclude the test Ergun is suggesting. Could be done later. Discuss again after SDP PSR.
2012-10-15 |  | ADP | Fit check ADP Booms and REs (ship sets 1&2) | TST | LASP |  | Tucker | Status?
2012-10-15 |  | SDP | SDP damping test at GSFC | TST | GSFC |  | Frost | Date? Requested Minh Phan's support.
2012-10-15 |  | SDP | SDP7-8 emi/emc test | EMI | UNH |  | Dors | Date is Macri's WAG.
2012-10-16 | 2012-10-18 | SDP | SDP 7 & 8 Vibe | VIB | UNH |  | Granoff | BAE reservation in place. Earlier?
2012-10-16 | 2012-10-19 | SCM | Calibration FM4 set | TST | LPP |  | Alison
2012-10-16 |  | EDI | Sensor SN4 Electrical Test | TST | UNH |  | Singer
2012-10-17 | 2012-10-24 | EDI | Sensor SN4 Vacuum Test | VAC | UNH |  | Singer
2012-10-19 |  | SDP | AEB 4&5, probes, S-BEBs and preamps | DEL-U | KTH | UNH | King | Hand carry, King. Date is Macri's WAG.
2012-10-19 |  | ADP | FM4 AEB | DEL | UNH | LASP | King | Ready to begin date @LASP (Tucker): 23 Oct
2012-10-19 |  | ADP | FM3 AEB | DEL-U | LASP | UNH | Tucker | Date from Tucker
2012-10-22 |  | ADP | EM AEB (UNH/LASP shared item) | DEL | LASP | UNH |  | Currently at LASP for verifying simulator box functionality.
2012-10-22 |  | CEB | FM3 CEB FFT | TST | UNH |  | Rau | Date from Rau, 26 Sep
2012-10-23 |  | SCM | PER: FM Spare? |  |  |  |  | Ask Ron
2012-10-24 | 2012-10-25 | ADP | Post test deployment, QM boom and RE | PDS | LASP |  | Tucker | Date?
2012-10-25 |  | CEB | FM3 CEB PER | PER | UNH |  | Myers | Date from Rau, 26 Sep
2012-10-25 |  | SCM | FM3 SCM harness | DEL-U | LPP | UNH | Alison | Date from Alison, 02 Oct
2012-10-29 | 2012-10-31 | EDI | Sensor SN4 MCP module assembly | ASSY | UNH |  | Granoff/Singer
2012-10-29 | 2012-11-12 | SDP | SDP SN7&8 TV Testing | TV | UNH |  | King | After GDU
2012-10-30 | 2012-10-31 | CEB | FM3 CEB Vibration Test | VIB | UNH |  | Rau/ Nolin | Date from Rau, 26 Sep. BAE reservation in place.
2012-10-31 |  | EDI | Shipment of GDE/Gun SN3 | DEL-U | IWF | UNH | Steller/ Myers | Vaith estimate 3 Oct
2012-11-01 |  | SCM | Document SCM configurations. Assembly drawing. |  |  |  | Alison | Open work from NCR PFR-10160.53-64-CL. Action item from FM4 set PER.
2012-11-01 |  | EDI | 20 HVOCs return to UNH for repeat of partial discharge tests after screening | DEL | IWF | UNH
2012-11-05 | 2012-11-07 | FIELDS | GDU SN1 FIT (timing - using EM-Full CEB) | TST | UNH |  | Rau/ Dors
2012-11-05 | 2012-11-09 | S/C | Observatory Risk Reduction EMI test | PDS | UNH |  | Dors/ Needell, Rau | Confirm dates
2012-11-05 | 2012-11-09 | EDI | GDU SN1 I&T with IS#1 @ GSFC | PDS | UNH |  |  | IS requesting GDU deliveries as ready (not as pairs).
2012-11-05 | 2012-11-16 | EDI | 20 HVOCs partial discharge tests (round 2) | TST | UNH |  | Widholm
2012-11-05 | 2012-11-19 | SDP | SDP SNs 5&6 I&T w/ IS#1 (installed upside down) | PDS | UNH |  | Dors/Bodet | Date? After deck EMI test?
2012-11-08 | 2012-11-09 | EDI | GDU SN1 magnetics testing | EMI | UNH |  | Dors
2012-11-09 | 2012-11-21 | CEB | FM3 CEB TV | TV | UNH |  | Rau | After SDP 7&8
2012-11-14 | 2012-11-29 | ADP | FM1 set ADP Booms install | PDS | LASP | GSFC | Tucker | Dates from Harbaugh, 18 Jul 2012
2012-11-14 |  | SDP | SDP SNs 5&6 delivery | DEL-G | UNH | GSFC | Dors/Bodet | Not needed on deck until after EMI testing (end of Oct). Log additional operating hours at UNH
2012-11-14 |  | EDI | SN1 GDU to IS#1 | DEL-G | UNH | GSFC |  | After FIT and magnetics tests
2012-11-14 |  | ADP | FM1 set ADP Booms delivery | DEL-G | LASP | GSFC | Tucker | Dates from Harbaugh, 18 Jul 2012
2012-11-15 |  | SDP | SDP 7 & 8 magnetics test | EMI | UNH |  | Dors | Date is Macri's WAG.
2012-11-16 |  | EDI | GDU SN3 PER | PER | UNH |  |  | Assumes 3 weeks after Gun/GDE delivery
2012-11-19 | 2012-11-23 | SCM | FM4 set SCM calibration | TST | LPP |  | Alison | Date from Alison, 7 Sep
2012-11-19 |  | SDP | SDP SNs 7&8 delivery | DEL-G | UNH | GSFC |  | Date is Macri's WAG
2012-11-26 | 2012-11-30 | FIELDS | FM3 FIELDS I&T | TST | UNH |  | Rau | Date from Rau, 26 Sep
2012-11-26 |  | FIELDS | Current Generator return to UNH | DEL | IWF | UNH | Magnes | Need date at UNH: 1 week after FM3 CEB TV Coordinate with FM4 DFG delivery?
2012-11-26 |  | SDP | SDP SNs 9&10 delivery | DEL-G | UNH | GSFC |  | Date is Macri's WAG. IS requesting SDP deliveries in pairs.
2012-11-26 |  | SDP | SN9 & 10 to IS#2 | DEL-G | UNH | GSFC
2012-11-29 |  | AFG | FM3 set fluxgate harness delivery | DEL-U | UCLA | UNH | Strangeway | Need date
2012-11-30 |  | EDI | 20 HVOCs second return to IWF for FM Gun assembly | DEL | UNH | IWF
2012-12-03 |  | AFG | FM4 AFG | DEL-U | UCLA | UNH | Strangeway | December.
2012-12-03 |  | DFG | FM4 DFG | DEL-U | IWF | UNH | Magnes | Coordinate with AFG delivery
2012-12-03 |  | SCM | FM4 SCM | DEL-U | LPP | UNH | Alison | Coordinate with Fluxgate deliveries. TV chamber not avail until Nov.
2012-12-07 |  | FIELDS | PSR: FM3 FIELDS | PSR | UNH |  | Myers | Date from Rau, 26 Sep
2012-12-11 |  | FIELDS | FM3 FIELDS (partial) | DEL-G | UNH | GSFC | Rau | Date from Rau, 26 Sep
2012-12-14 |  | EDI | SN3 GDU toIS#1 | DEL-G | UNH | GSFC |  | IS requesting GDU deliveries as ready (not as pairs).
2012-12-19 |  | EDI | GDU SN3 environmental testing complete |  |  |  |  | Vaith estimate 3 Oct
2012-12-28 |  | ADP | FM4 AEB | DEL-U | LASP | UNH | Tucker | Date from Tyler
2013-01-09 |  | EDI | PSR: FM1 set GDUs (SNs 1&3) | PSR | UNH |  |  | Vaith estimate 3 Oct
2013-01-14 |  | EDI | SN4 GDU to IS#2 | DEL-G | UNH | GSFC |  | Assumes Gun/GDE delivery: 23 Nov and 5-week pace for GDU I&T.
2013-01-14 |  | SDP | SN11 & 12 to IS#3 | DEL-G | UNH | GSFC
2013-02-01 | 2013-02-10 | SCM | TQCM measurement FM4 SCM harness | TST | LPP |  |  | Date from Alison, 02 Oct
2013-02-15 |  | SCM | FM4 SCM harness | DEL-U | LPP | UNH |  | Date from Alison, 02 Oct
2013-02-18 |  | EDI | SN5 GDU to IS#2 | DEL-G | UNH | GSFC |  | Assumes 5-week pace for GDU I&T
2013-02-21 |  | AFG | FM4 set fluxgate harness delivery | DEL-U | UCLA | UNH | Strangeway | Need date
2013-02-25 |  | SDP | SN13 & 14 to IS#3 | DEL-G | UNH | GSFC
2013-03-18 | 2013-03-22 | Sci | SWT & FIELDS Science Data Processing Working Group | MTG |  |  | Torbert | At LASP. Dates TBD
2013-03-25 |  | EDI | SN6 GDU to IS#3 | DEL-G | UNH | GSFC |  | Assumes 5-week pace for GDU I&T
2013-04-08 |  | SDP | SN15 & 16 to IS#4 | DEL-G | UNH | GSFC
2013-04-29 |  | EDI | SN7 GDU to IS#3 | DEL-G | UNH | GSFC |  | Assumes 5-week pace for GDU I&T
2013-05-20 |  | SDP | SN2 & 17 to IS#4 | DEL-G | UNH | GSFC
2013-06-03 |  | EDI | SN8 GDU to IS#4 | DEL-G | UNH | GSFC |  | Assumes 5-week pace for GDU I&T
2013-07-24 |  | EDI | SN2 GDU to IS#4 | DEL-G | UNH | GSFC |  | Assumes 5-week pace for GDU I&T