## NearTerm
FIELDS Near-Term Activites, J. Macri
from date | to date | Subs. | SNs | item | category | from | to | Lead/ participants | status/note
2013-01-31 | 2013-03-29 | SDP | 11, 12 | Assembly of SDP SNs 11 & 12 | ASSY | UNH |  | Granoff | done
2013-02-06 | 2013-02-07 | CEB |  | Ship set 4 DSP boards | DEL-U | LASP | UNH |  | done
2013-02-06 | 2013-02-13 | SDP |  | Workamanship TV cycle SDP preamps SNs 17-18 | TV | UNH |  | King | done
2013-02-07 | 2013-03-01 | SDP | 9, 10 | SDP 9&10 acceptance testing, FIT, magnetics and FIELDS-level CPT with EM by FIELDS SE team | TST | UNH |  | Rau | done
2013-02-11 | 2013-02-15 | ADP |  | Obs-1 +Z , Obs-2 -Z | PDS | LASP |  | Tucker | done
2013-02-11 |  | SDP | 11,12 | SDP probes for SDP SNs 11, 12 | DEL-U | KTH | UNH | King/ Lindqvist | done
2013-02-12 |  | SDP |  | PSR: SDP 7, 8, 9, 10 (Chair: Dirks) | PSR | UNH |  | King | done
2013-02-13 | 2013-02-14 |  |  | IMSA SCOPE site visit at UNH | Constraint | UNH |  | Myers, others | done
2013-02-13 | 2013-02-21 | EDI |  | SN5 Gun/GDE calibration (2 energies) | TST | IWF |  | Steller | done
2013-02-14 | 2013-02-20 | FIELDS |  | TV chamber maintenance | TV |  |  | Ellis | done
2013-02-19 | 2013-02-20 | SDP | 5, 6 | Remove SDP SNs 5&6 from Obs-2, return to UNH | PDS | GSFC | UNH | Rau | done
2013-02-19 | 2013-02-25 | SCM |  | Bake-out FM4 SCM harness | TST | LPP |  |  | done.
2013-02-19 | 2013-03-06 | CEB | 4 | Parylene coating for FM4 set CDPU, EDI Controller AFG and DFG boards | ASSY | UNH |  | Turco | done
2013-02-20 |  | AFG |  | FM4 set fluxgate harness delivery | DEL-U | UCLA | UNH | Rau | done
2013-02-21 |  | AFG |  | Incoming inspection FM4 set fluxgate harness | TST | UNH |  | Turco/ Rau | done
2013-02-21 |  | SDP |  | FRB: spare motor inspections | FRB | UNH |  | Granoff | done
2013-02-25 | 2013-02-28 | EDI | 5 | SN5 Sensor characterization in vacuum | VAC | UNH |  | Singer | done
2013-02-25 | 2013-03-01 | ADP | 1 | RE SN01 (SS#3) post rework FFT | TST | LASP |  | Tucker | done
2013-02-26 |  | ADP |  | FRB: SN8 RE launch latch open in vibe | FRB | LASP |  | Tucker | done
2013-02-27 |  | Deck4 |  | TRR: IS#4 CPT |  |  |  | Needell | done
2013-02-27 |  | SCM |  | FM4 ship set SCM (Sensor, Preamp & Harness) | DEL-U | LPP | UNH | Leroy | done
2013-02-27 |  | SCM |  | Acceptance test FM4 ship set SCM | TST | UNH | UNH | Rau/ Leroy | done
2013-03-01 | 2013-03-07 | EDI | HVOCs | Return selected IWF optocouplers to IWF for use with Guns 4, 6 (qty 9) | DEL | UNH | IWF | Vaith/ Widholm | done
2013-03-01 |  | SDP | 5, 6 | Incoming inspection SDP SNs 5&6 | TST | UNH |  | Turco/ Granoff | done
2013-03-01 |  | SDP | 11, 12 | SDP 11, 12 fine wire crimping (LASP support) | ASSY | LASP |  | Vermeer/ Frost | done
2013-03-04 | 2013-03-18 | EDI |  | Test 1 refurbished BGS, incl. burn in. | TST | UNH |  | Singer | done
2013-03-05 | 2013-03-06 | AEB | 5 | Acceptance test FM5 AEB (flight spare) | TST | UNH |  | Dors | done
2013-03-05 | 2013-03-08 | ADP |  | FM4 AEB | DEL-U | LASP | UNH | Tucker | done.
2013-03-06 |  | FIELDS |  | FIELDS Users manual | DOC | UNH |  | Needell | done
2013-03-08 | 2013-03-15 | CEB | 4 | FM4 CEB final asembly | ASSY | UNH |  | Nolin | done
2013-03-08 |  | SDP | 5, 6 | SDP 5&6 EMI retest | EMI | UNH |  | Dors | done
2013-03-11 | 2013-03-14 | EDI | 5 | SN5 Optics delivery, Sensor-Optics integration, GDU integration support. | DEL-U | Iowa | UNH | Bounds | done
2013-03-11 | 2013-03-22 | FIELDS |  | IS#4 Burst & FDC testing & dry runs | PDS | UNH |  | Needell | done
2013-03-12 |  | EDI | 5 | Shipment of GDE/Gun SN5 | DEL-U | IWF | UNH | Steller | done
2013-03-12 |  | CEB |  | FRB: CRAM multibit errors (FM4 CDPU-B) | FRB | UNH |  | Needell/ Bodet | done
2013-03-12 |  | EDI | HVOCs | Partially populated Gun board (2 channels) for UNH HVOC evaluation | DEL-U | IWF | UNH | Steller/ Widholm | done
2013-03-14 | 2013-03-15 | SDP | 5, 6 | Remove probe/yo-yo assemblies from SNs 5 & 6. Return to KTH/Oulu for rework | ASSY | UNH |  | King/ Macri | done
2013-03-15 |  | FIELDS |  | Draft inputs to MMS Data Products Guide (AFG/DFG. SCM. SDP, EDI) | CDRL | UNH |  | Chutter | done
2013-03-18 | 2013-03-22 | Sci |  | SWT & FIELDS Science Data Processing Working Group @LASP | MTG |  |  | Torbert | done
2013-03-18 |  | SDP | 5, 6 | Provide probes A3 and A4 removed from SDPs 5&6 to KTH for rework. | DEL | UNH | KTH | Macri/ Lindqvist | done
2013-03-19 |  | Sci |  | MMS Ops and/or Commissioning TIM @LASP | MTG |  |  | Needell | done
2013-03-20 |  | CEB | 4 | PER: FM4 CEB | PER | UNH |  | Myers, others | done
2013-03-21 | 2013-03-22 | CEB | 4 | FM4 CEB vibration | VIB | UNH |  | Nolin | done
2013-03-22 | 2013-03-28 | EDI | HVOCs | TV test prototype HVOCs | TV |  |  | King | done
2013-03-22 |  | ADP |  | FRB: RE launch latches | FRB | LASP |  | Tucker | done
2013-03-25 | 2013-04-02 | ADP |  | Obs-1 and Obs-2 ADP work at GSFC. Integrate +Z ADP Boom on Obs1. Swap connector brackets on -Z ADP Boom on Obs 2. | PDS | LASP |  | Tucker | done
2013-03-26 |  | CEB | 4 | FM4 CEB EMI/EMC | EMI | UNH |  | Dors | done
2013-03-26 |  | EDI | 5 | PER: GDU SN5 (chair: Stone?) | PER | UNH |  | Vaith | done
2013-03-27 | 2013-03-28 | EDI | 5 | GDU SN5 vibration | VIB | UNH |  | Granoff/ Singer | done
2013-03-27 |  | Boom |  | Obs-1 Mag boom first motion test | PDS |  |  | Needell | done
2013-03-27 |  | EDI |  | EDI Users manual | DOC | UNH |  | Vaith | done
2013-03-29 | 2013-04-12 | CEB | 4 | FM4 CEB TV | TV | UNH |  | Rau | done
2013-04-01 | 2013-04-02 | SDP | 11, 12 | SDP SNs 11&12 FFT | TST | UNH |  | King | done
2013-04-01 | 2013-04-05 | AEB | 3 | Thermal testing at LASP. DAC channel noise investigation | TST | LASP |  | Tucker | done
2013-04-08 |  | EDI | HVOCs | UNH HVOC Review | EPR | UNH |  | King | done
2013-04-09 |  | FIELDS |  | Mag Boom#2 1st motion test | PDS | UNH |  | Rau? | done
2013-04-09 |  | AFG |  | Report of FM1 Mag Boom alignment test and verification | TST | GSFC |  | Sturm | done
2013-04-10 | 2013-04-05 | SDP | 11, 12 | SDP SNs 11&12 vibration | VIB | UNH |  | Frost | done
2013-04-10 |  | EDI |  | Delivery 1 refurbished BGSs to IWF - SN 1 | DEL | UNH | IWF |  | done.
2013-04-10 |  | Deck4 |  | Delivery of IS#4 to Obs#4 |  |  |  |  | done
2013-04-10 |  | SDP | 11, 12 | PER: SDP SNs 11&12 | PER | UNH |  | Myers, others | done
2013-04-10 |  | SCM |  | PER: spare SCM Sensor (SN FM4) | PER | LPP |  | Macri/ Alison | done
2013-04-10 |  | Deck4 |  | Acceptance Review | PDS | UNH |  | Needell | done
2013-04-11 |  | EDI | 5 | GDU SN5 EMI/EMC | EMI | UNH |  | Dors | done
2013-04-12 | 2013-04-26 | SDP | 11, 12 | SDP SNs 11&12 TV | TV | UNH |  | King | done
2013-04-12 |  | CEB | 4 | CEB acceptance test |  |  |  |  | done
2013-04-13 |  | EDI |  | Delivery 2 (qty.?) HV&Fil boards to IWF. | DEL | UNH | IWF |  | done.
2013-04-15 | 2013-04-17 | FIELDS | 4 | FM4 FIELDS CPT and operating hours | TST | UNH |  | Rau | done
2013-04-17 |  | SDP |  | Probes from SNs 1&2 for rework (B1 & B2), peamp/cable assemblies 17&18, SBEBs 17&18 | DEL | UNH | KTH | King | done.
2013-04-18 |  | FIELDS |  | Prep HW for delivery: SS#4 CEB, AEB, SCM-PA; GDU3, SDPs 9&10 | CLEAN |  |  | Turco | done
2013-04-19 |  | FIELDS | 4 | PSR: FM4 FIELDS (Chair: Stone) | PSR | UNH |  | Rau | done
2013-04-19 |  | EDI | 3 | Acceptance Review:GDU SN3 | PSR (AR) | UNH |  | Vaith | done
2013-04-21 |  | FIELDS |  | Travel day to GSFC: FIELDS4 (partial), GDU3, (SDP 9&10) | DEL-G | UNH |  | Needell, Bodet | done
2013-04-22 | 2013-04-26 | ADP |  | Obs-1 ADP RE install, S2M, and deploy at GSFC | PDS | LASP |  | Tucker | done
2013-04-22 | 2013-04-26 | ADP |  | Obs-2 +Z ADP Boom install at GSFC | PDS | LASP |  | Tucker | done
2013-04-22 | 2013-04-26 | FIELDS | 4 | I&T with Obs3 | PDS | UNH |  | Rau, Needell, Bodet | done
2013-04-22 |  | ADP |  | ADP (IS) Sim SN001 Retrofited with new switches | DEL-G | LASP | GSFC | Tucker | done
2013-04-22 |  | SDP | 9, 10 | SDP SN 9 & 10 delivery to GSFC | DEL-G | UNH | GSFC |  | done
2013-04-23 | 2013-04-24 | ADP |  | ADP RE SN08 repeat vibration test | TST | LASP |  | Yehle | done
2013-04-23 | 2013-04-26 | Obs4 |  | Obs-4 functional test- 2 shifts | PDS | UNH |  | Chutter/ Melllo | done
2013-04-24 |  | SDP |  | Probes B3&B4 (for SDPs 5&6); Probes A3&A4 (for SDPs 13&14);Probes E2, E3, E4; preamp-cable assemblies 13, 14, 15, 16; S-BEBs 13, 14 | DEL-U | KTH | UNH | King | done.
2013-04-25 |  | ADP |  | Latch penalty vibration test (SS#2 latches) | TST | LASP |  | Yehle | done.
2013-04-25 |  | SDP | 5, 6 | Receive SDP 5&6 replacement probes from KTH (SNs B3 & B4). | DEL-U | KTH | UNH | King/ Lindqvist | done
2013-04-26 | 2013-05-01 | SDP | 5, 6 | SDP 5&6 replacement probe install & test (B3 & B4) | ASSY | UNH |  | King | done
2013-04-29 | 2013-05-03 | FIELDS |  | Obs-1 Mag boom #1 & #2, 2nd and 3rd motions test | PDS | UNH |  | Rau | done
2013-04-29 | 2013-05-08 | EDI | 5 | GDU SN5 TV | TV | UNH |  | Vaith | done
2013-04-29 | 2013-05-29 | SDP | 13, 14 | Final assembly SDP SNs 13 & 14 | ASSY | UNH |  | Granoff
2013-05-01 | 2013-05-06 | FIELDS | 4 | IS#3 CPT & Burst test | PDS |  |  |  | done
2013-05-01 |  | SDP | 11, 12 | SDP SNs 11&12 FIELDS Acceptance Test | TST | UNH |  | Rau | done
2013-05-02 | 2013-05-03 | SDP | 11, 12 | SDP SNs 11&12 EMI/EMC | EMI | UNH |  | Dors | done
2013-05-03 | 2013-05-06 | SDP | 11, 12 | SDP SNs 11&12 Magnetics Testing | TST | UNH |  | Dors | done
2013-05-06 | 2013-05-08 | SDP | 11, 12 | FIELDS FIT | TST |  |  | Dors | done
2013-05-07 |  | DFG |  | Review and remote "delivery" of DFG Flight Spare Sensor | DEL-U | UCLA | UNH | Macri/ Rau, Turco, Magnes | done
2013-05-07 |  | ADP |  | Obs #1: -Z ADP Boom: connector bracket swap, reinstall | PDS | LASP | GSFC | Yehle | done
2013-05-08 |  | ADP |  | Delivery: SS3 ADP Booms, SS2 ADP Launch Latches, SS3 ADP Launch Latches | DEL-G | LASP | GSFC | Tucker/ Yehle | done
2013-05-08 |  | AEB | 3 | FRB: AEB3 rework and retest plan | FRB | UNH |  | Turco | done
2013-05-09 | 2013-05-10 | SDP | 11, 12, 5, 6 | SDP SNs 11&12, 5&6 clean, inspect, pack | CLEAN | UNH |  | Turco | done
2013-05-09 | 2013-05-10 | EDI | 5 | GDU SN 5 clean, inspect, pack | CLEAN | UNH |  | Turco | done
2013-05-09 | 2013-05-21 | AEB | 3 | AEB3 Parylene removal for rework | ASSY | KTH |  | King/ Lindqvist | done
2013-05-09 |  | ADP |  | Obs #4: -Z ADP Boom: receiving inspection, S2M, temp sensor bonding, integrate to obs | PDS | LASP | GSFC | Yehle | done
2013-05-10 |  | SDP | 11, 12 | Acceptance Review: SDP 11 & 12 (incl. 5&6 rework) | PSR (AR) | UNH |  | King | done
2013-05-10 |  | EDI | 3 | Acceptance Review:GDU SN5 | PSR (AR) | UNH |  | Vaith | done
2013-05-12 |  | DFG |  | DFG Flight Spare Sensor | DEL | UCLA | IWF | Ferdinand Plaschke | done
2013-05-13 |  | EDI | 5 | GDU SN 5 deliver to GSFC | DEL-G | UNH | GSFC |  | done
2013-05-13 |  | SDP | 11, 12, 5, 6 | Delivery: SDPs 5&6, 11&12 | DEL-G | UNH | GSFC |  | done
2013-05-16 |  | ADP |  | Provide missing RE data to FM4 PSR presentation | DOC | LASP |  | Tucker | ADP RE trend data; verifications
2013-05-20 |  | SDP |  | Return SDP EM BEB and QM BEB to UNH | DEL-U | GSFC | UNH | Rau | done
2013-05-20 |  | AFG | 11 | Return SN11 AFG Sensor to UNH for thermal testing | DEL-U | GSFC | UNH | Rau | done
2013-05-21 |  | AFG | 11 | AFG4 Sensor (SN11) thermal cycle test | TST | UNH |  | Dors | done
2013-05-22 |  | FIELDS | 4 | IS Deck #3 Acceptance Review Part 2 | PDS | UNH |  | Needell | done.
2013-05-24 |  | AEB | 5 | PER: SN5 AEB (chair: Dirks) | PER | LASP |  | Tucker | done
2013-05-28 |  | ADP |  | Obs #2 +Z RE install / STM / LPT | PDS | LASP |  | Tucker/ Yehle | done
2013-05-29 |  | FIELDS |  | Provide missing CEB & FIELDS data to FM4 PSR presentation. EB trend data; Operating Hours (CEB, AEB); verirfications | DOC | UNH |  | Rau | done
2013-05-29 |  | ADP |  | Obs #2 +Z RE deploy / functional | PDS | LASP |  | Tucker/ Yehle | done
2013-05-30 |  | ADP |  | Obs #1 -Z RE install / STM / LPT | PDS | LASP |  | Tucker/ Yehle | done
2013-05-31 |  | ADP |  | Obs #1 -Z LL release / functional | PDS | LASP |  | Tucker/ Yehle | done
2013-06-03 | 2013-06-04 | FIELDS |  | EM Full CEB test with IS FlatSat | PDS | UNH |  | Rau | done
2013-06-03 |  | AFG | 11 | Return SN11 AFG Sensor to GSFC | DEL-G | UNH | GSFC | Rau | done
2013-06-03 |  | SDP | 14 | FRB: faulty thermal sensor on motor | FRB | UNH |  | Macri | done
2013-06-05 | 2013-06-10 | FIELDS | 1 | Obs-1 CPT | PDS | UNH |  | Needell/ Bodet, Rau, Chutter, Mello, Dors | done
2013-06-05 | 2013-07-08 | EDI | HVOCs | Screening tests, first batch | TST | UNH |  | King | underway
2013-06-06 | 2013-06-07 | SDP | 13, 14 | SDP SNs 13&14 EMI test | EMI | UNH |  | Dors | done.
2013-06-10 | 2013-06-14 | SCM | Spare | SCM flight spare calibration | TST | LPP |  | Le Contel
2013-06-10 |  | SDP | 13, 14 | PER: SDP SNs 13&14 | PER | UNH |  | Myers/ King | done
2013-06-10 |  | EDI | HVOCs | HVOC test board and procedure review | REV | UNH |  | King | done
2013-06-12 | 2013-06-13 | SDP | 13, 14 | SDP SNs 13&14 vibration | VIB | UNH |  | Frost | underway
2013-06-16 | 2013-06-21 | SDP |  | SDP (1 unit, SN17) calibration at IRF-U | TST | KTH |  | King | King will distribute updated test plan.
2013-06-17 | 2013-06-19 | ADP |  | Ship remaining ADP hardware to GSFC (items?) | DEL-G | LASP | GSFC | Tucker
2013-06-17 | 2013-06-20 | FIELDS |  | Mission PER | PER | UNH |  | Macri/ Rau, Vaith, Torbert | HVOC presentation on 17 Jun. FIELDS presentation on 18 Jun.
2013-06-17 | 2013-06-28 | SDP | 13, 14 | SDP SNs 13&14 TV | TV | UNH |  | King
2013-06-18 | 2013-06-28 | EDI | 6 | UNH suport for Gun testing at IWF | TST | UNH | IWF | Singer | Extend to 2 Jul?
2013-06-18 |  | EDI |  | HV&Fil board SN8 delivery to IWF | DEL | UNH | IWF | Myers
2013-06-19 | 2013-06-20 | EDI | 6 | EDI Sensor SN6 integration with Optics. Deliver SN7 Optics. | DEL-U | Iowa | UNH | Granoff/ Singer? (Dvorsky) | Iowa support.
2013-06-20 |  | SCM |  | Document SCM configurations. Assembly drawing. |  | LPP |  | Alison | Open work from NCR PFR-10160.53-64-CL. Action item from FM4 set PER. Awaiting addition of difference in pigtails.
2013-06-22 |  | SDP | 15, 16 | S-BEBs SNs 15&16, probes B1&B2, AEB SN3 | DEL-U | KTH | UNH | King
2013-06-24 |  | EDI | HVOCs | Receipt of screened HV diodes | DEL-U | ATC | UNH | Turco
2013-06-26 | 2013-06-29 | OBS | 3 | Obs-3 CPT | PDS | UNH |  | Rau/ Needell
2013-06-26 |  | AEB | 5 | Return AEB SN5 to UNH for FIELDS-level testing | DEL-U | LASP | UNH | Tucker
2013-07-01 | 2013-07-02 | SDP | 13, 14 | SDP SNs 13&14 Magnetics, FIT, FIELDS acceptance | TST | UNH |  | Dors
2013-07-01 | 2013-07-02 | AEB | 5 | SN5 AEB FIELDS-level testing: FIT, Magnetics | TST | UNH |  | Dors
2013-07-01 |  | AEB |  | EM AEB (UNH/LASP shared item) | DEL | LASP | UNH |  | Needed at UNH?
2013-07-01 |  | SCM | Spare | Delivery of SCM flight spare Sensor and Preamp to UNH | DEL-U | LPP | UNH | Alison | Date to be discussed.
2013-07-03 |  | SDP | 11, 12, 13, 14 | PSR: SDP 11, 12, 13, 14 (Chair: Dirks) | PSR | UNH |  | Myers/ King | Date is Macri's WAG
2013-07-08 |  | SDP | 13, 14 | SDP 13&14 Delivery | DEL-G | UNH |  |  | Date is Macri's WAG
2013-07-08 |  | EDI |  | Shipment of GDE/Gun SN6 | DEL-U | IWF | UNH | Steller | Date is Macri's WAG.
2013-07-08 |  | AEB | 5 | Needed for RE inatall on Obs-4 | DEL-G | UNH | GSFC |  | Need date,11 Jul, from Harbaugh 23 Apr
2013-07-09 | 2013-07-10 | EDI | 4 | GDU SN4 vibration | VIB | UNH |  | Granoff | Date is Macri's WAG
2013-07-11 |  | AFG |  | LM6142 DPA follow-up | TST |  |  | Turco
2013-07-15 |  | ADP |  | Draft inputs to MMS Data Products Guide (ADP) | CDRL | UNH |  | Chutter | Status?
2013-07-15 |  | SDP | 17. 18 | S-BEBs SNs 17&18 | DEL-U | KTH | UNH | King | Date?
2013-07-15 |  | SDP | 17. 18 | Preamp/Cable assemblies 17, 18 | DEL-U | KTH | UNH | King | Date?
2013-07-15 |  | OBS | 1 | Obs-1 EMI test (LPP SCM support of low freq noise investigation?) | PDS | LPP |  | Rau/ Dors, Le Contel | Test date currently Oct, but may be moved forward to July.
2013-07-17 |  | AEB | 3 | Results from DPA of AEB SN3 LM124 device | TST | ATC | UNH | Turco | Part submitted 4 June
2013-07-22 |  | EDI | HVOCs | Receipt of screened LEDs | DEL-U | ATC | UNH | Turco
2013-08-01 | 2013-08-30 | OBS | 2 | Obs-2 TV | PDS | UNH |  | Rau/ Needell | Dates?
2013-09-16 | 2013-09-20 | FIELDS |  | MRT-8: SDP boom deployment rehearsal | SOC | UNH |  | Needell | at SOC, FIELDS simulator
2014-01-15 |  | ADP |  | ADP/SDP cross calibration at LASP. SDP (1-unit, QM?) calibration in Faraday cage at LASP. Ergun: Goal is directly comparable ADP and SDP calibrations. Can be FM or fully representative EM. | TST | UNH | LASP | Ergun | Ergun to propose earlier date
2013-10-01 |  | OBS | 2 | Obs-2 EMI test | PDS

## Previous
Previous activities, from dates through Sep 2012
from date | to date | Subs. | SNs | item | category | from | to | Lead/ participants | status/note
2011-09-08 |  |  |  | MIP of FM1 Gun boards at IWF | MIP | SwRI |  | SwRI | done
2011-09-09 |  |  |  | FRR: EDI beam gen system | FRR | UNH |  | Turco | done
2011-09-11 |  |  |  | FM1 AEB | DEL | UNH | KTH | King | done
2011-09-12 |  |  |  | FM1 A-BEB bench test | TST | KTH |  | Olsson | done
2011-09-12 |  |  |  | Receipt of EM Gun and GDE | DEL | UNH | IWF | Williams | done
2011-09-12 |  |  |  | FM1 SDP Probe assemblies | DEL | Oulu | KTH | Lindqvist | done
2011-09-12 |  |  |  | TRR | TRR | UCLA |  | Strangeway | done
2011-09-13 | 2011-09-14 |  |  | FM2 FG Sensor vibe | TST | UCLA | ` | Strangeway | done
2011-09-14 | 2011-09-16 |  |  | Acceptance test FM1 DSP boards (2) | TST | LASP | UNH | Rau | done
2011-09-14 | 2011-10-04 |  |  | Assembly of FM1 CEB (box and electronics) | ASSY | UNH |  | Nolin | done
2011-09-15 | 2011-09-19 |  |  | FM1 AEB testing (IRFU) | TST | IRFU |  | King | done
2011-09-15 |  |  |  | FRR: CEB assembly | FRR | UNH |  | Turco | done
2011-09-16 | 2011-09-28 |  |  | FM2 FG Sensors thermal and bakeout | TST | UCLA |  | Strangeway | done
2011-09-16 |  |  |  | FM1-1 HV Filament Board (ship) | DEL | UNH | IWF | Williams | done
2011-09-16 |  |  |  | FM1 ADP Ext. Booms (EIDP review) | DEL | ATK | LASP | Westfall | done
2011-09-16 |  |  |  | EDI Gun CDR follow-up (9 a.m. EDT) | CDR | UNH |  | Macri | done
2011-09-19 | 2011-09-21 |  |  | FM1-1 beam generation system test | TST | UNH |  | Singer | done
2011-09-20 | 2011-09-23 |  |  | Parylene coating of FM1 AEB boards (Sweden) | ASSY | KTH |  | King | done
2011-09-20 |  |  |  | FRR: EDI Sensor assembly | FRR | UNH |  | Turco | done
2011-09-20 |  |  |  | LVPS, AFG, DFG parylene coating complete | MILE | UNH |  | Turco | done
2011-09-21 | 2011-09-26 |  |  | FM1 S-BEB testing (IRFU) | TST | IRFU |  | King | done
2011-09-22 |  |  |  | FM1 S-BEB testing (IRFU) | TRR |  |  | King | done
2011-09-22 12:00 | 2011-09-23 |  |  | CDPU SW acceptance test (Needell) | TST | UNH |  | Needell | done
2011-09-23 |  |  |  | FM1-1 HV Filament Board (received) | DEL | UNH | IWF | Steller | done
2011-09-23 11:30 | 2011-09-23 15:00 |  |  | PER: FM2 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-09-26 | 2011-09-27 |  |  | MMS SWT | MTG | UNH |  | Torbert | done
2011-09-26 |  |  |  | FM1 AEB | DEL | KTH | UNH | Lindqvist | done
2011-09-26 |  |  |  | Current generator (GSE) | DEL | IWF | UNH | Magnes | done
2011-09-26 12:00 | 2011-09-27 |  |  | EM FIT testing at UNH | TST | UNH |  | Dors | done
2011-09-28 | 2011-10-03 |  |  | FM1 S-BEB parylene coating | ASSY | KTH |  | King | done
2011-09-28 |  |  |  | FM1 AEB receiving inspection (morning) |  | UNH |  | Turco | done
2011-09-28 |  |  |  | FRR for mag harnesses | FRR | UNH |  | Turco | done
2011-09-28 |  |  |  | Reynolds HV cable received at IWF | DEL | VEND | IWF | Steller | done
2011-09-28 |  |  |  | PRODEX/ESA approval of GDE circuit modification | DES | IWF |  | Steller | done
2011-09-28 |  |  |  | MMS SWG (PIs, Wed morning) | MTG | UNH |  | Torbert | done
2011-09-28 13:00 | 2011-09-29 |  |  | FIELDS Science Data Processing Working Group | MTG | UNH |  | Chutter | done
2011-09-29 |  |  |  | FM1-1 beam generation system | DEL | UNH | IWF | Singer | done
2011-09-29 |  |  |  | FM2 DFG Sensor | DEL | UCLA | UNH | Strangeway | done
2011-09-29 |  |  |  | FM1-2 HV Filament Board | DEL | UNH | IWF | Turco | done
2011-09-30 | 2011-10-03 |  |  | FM1 SDP Probes TV testing | TST | KTH |  | Lindqvist | done
2011-09-30 |  |  |  | FM2 DFG receiving inspection and EIDP review | EIDP | UNH |  | Turco | done
2011-09-30 |  |  |  | FM4 & FS DFG boards | DEL | UNH | IWF | Williams | done
2011-09-30 |  |  |  | FM2 DFG Sensor | DEL | UNH | IWF | Williams | done
2011-10-03 | 2011-10-04 |  |  | FM1 S-BEB parylene (Sweden) | ASSY | KTH |  | King | done
2011-10-03 | 2011-10-05 |  |  | FM1 SCM Sensor and Preamp | DEL/TST | LPP | UNH | Leroy | done
2011-10-03 |  |  |  | ADP Simulator | DEL | LASP | UNH | Westfall | done
2011-10-03 |  |  |  | Connector brackets for DSPs 4-7 | DEL | UNH | LASP | Nolin | done
2011-10-03 |  |  |  | EIDP Review: FM1 SCM | EIDP |  |  | Macri | done
2011-10-06 | 2011-10-21 |  |  | Final definition: FM motors & harnesses | MILE | UNH |  | King | done
2011-10-06 |  |  |  | FM1 CEB FFT | TST | UNH |  | Rau | done
2011-10-06 |  |  |  | FM1 SDP Probes (4) | DEL | KTH | UNH | King | done
2011-10-06 |  |  |  | FM1 S-BEB | DEL | KTH | UNH | King | done
2011-10-07 |  |  |  | EM4 SCM Sensor and BB Preamp (receive @ UNH) | DEL | LPP | UNH | Williams | done
2011-10-07 |  |  |  | FM1 AEB functional test | TST | UNH |  | Rau | done
2011-10-07 |  |  |  | TRR: FM1 CEB (AEB & SCM) EMI/EMC test | TRR | UNH |  | Myers | done
2011-10-10 | 2011-10-27 |  |  | TV chamber characterization for outgassing certification measurements | TST | UNH |  | Turco | done
2011-10-11 | 2011-10-20 |  |  | FM1 CEB (AEB & SCM) EMI/EMC testing @ Retlif | TST | UNH |  | Dors | done
2011-10-14 | 2011-10-21 |  |  | Review TV chamber data and readinesss for outgassing certificaiton with Jack Sanders | TRR | UNH |  | Turco | done
2011-10-14 |  |  |  | Distribute materials for EDI SW TRR | TRR | UNH |  | Briggs | done
2011-10-17 | 2011-10-18 |  |  | FM1-1 EDI Gun inspection (Granoff, Macri) | INS | UNH | IWF | Macri | done
2011-10-17 | 2011-11-02 |  |  | FM1 SCM harness bakeout and certification | TST | UNH |  | Turco | done
2011-10-17 |  |  |  | Connector brackets for DSPs 8-9 | DEL | UNH | LASP | Nolin | done
2011-10-24 |  |  |  | FG nulling coil GSE (1st of 4) | DEL | UCLA | UNH | Strangeway | done
2011-10-24 |  |  |  | FM1 CEB retest planning (DSP FPGA change) | FRB | SwRI |  | Black | done
2011-10-25 | 2011-10-28 |  |  | FM1 SDP preamp/cable rework, fine wire assy and boom wire marking @ UNH | ASSY | LASP |  | Vermeer | done
2011-10-25 |  |  |  | CDPU SW acceptance test (post-test review) | REV | UNH |  | Heirtzler | done
2011-10-26 |  |  |  | EDI FSW TRR | TRR | UNH |  | Briggs | done
2011-10-27 | 2011-11-29 |  |  | Plan for SDP deployments on S/C decks to GSFC | DOC | UNH | GSFC | Macri | done
2011-10-27 |  |  |  | ADP FM1 booms (SN01, SN02) delivery to LASP | DEL | ATK | LASP | Westfall | done
2011-10-28 |  |  |  | FM1 AEB (plus 2 FM1 DSP boards and 1 EM A-BEB) & ADP simulator | DEL | UNH | LASP | Rau | done
2011-10-29 |  |  |  | FM1-2 EDI beam generation system | DEL | UNH | IWF | Singer | done
2011-10-31 | 2011-11-02 |  |  | CIDP Road Show at GSFC | TST | UNH |  | Needell | done
2011-10-31 |  |  |  | FIELDS Simulator (received at SwRI) | DEL | UNH | SwRI | Chutter | done
2011-10-31 |  |  |  | EM4 SCM Sensor deliver to GSFC for tests with qual boom | DEL | UNH | GSFC | Rau | done
2011-11-02 |  |  |  | EM4 SCM Sensor installation on QM mag boom (GSFC) | INT | GSFC |  | Sturm | done
2011-11-02 |  |  |  | ASPOC PER | PER | IIRT |  |  | done
2011-11-03 | 2011-11-09 |  |  | FM1 SCM Sensor & Preamp bakeout & cert. | TST | UNH |  | Turco | done
2011-11-04 |  |  |  | Return EM1 AFG board to UNH | DEL | UCLA |  | Strangeway | done
2011-11-07 | 2011-11-30 |  |  | FM2 A-BEB PWAs | ASSY | Iowa | UNH | Turco | done
2011-11-09 |  |  |  | PER: FM ship set 3 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-11-10 |  |  |  | EDI FSW Acceptance test | TST | UNH |  | Briggs | done
2011-11-10 |  |  |  | TRR: FM1 SDP EMI/EMC testing (1 deployer) | TRR | UNH |  | Dors | done
2011-11-10 |  |  |  | TRR: FM1-1 EDI Sensor thermal and vacuum tests | TRR | UNH |  | Macri | done
2011-11-14 |  |  |  | FM1-1 SDP FFT | TST | UNH |  | King | done
2011-11-14 |  |  |  | Change soldered FPGA on EM DSP board | ASSY | LASP |  | Westfall | done
2011-11-15 | 2011-11-16 |  |  | FM1-1 EDI Sensor thermal test | ETST | UNH |  | Singer | done
2011-11-15 | 2011-11-18 |  |  | FM1 SDP EMI/EMC testing (1 deployer) | ETST | UNH |  | Dors | done
2011-11-15 |  |  |  | PER: FM1 SDP | PER | UNH |  | Myers | done
2011-11-17 | 2011-12-02 |  |  | Review EM AEB testing at LASP and plan forward | REV |  |  | Macri | done
2011-11-17 | 2011-12-07 |  |  | SDP preamp thermal test plan prep and review |  |  |  | Nolin | done
2011-11-17 |  |  |  | DSP & CDPU FPGAs (pre-burn review) | REV |  |  | Macri | done
2011-11-18 |  |  |  | Beam Gen Syst. Anode and focus weldments (pre- plating, receipt @ UNH) | DEL | VEND | UNH | Nolin | done. Rejected.
2011-11-22 |  |  |  | FM2 LVPS PWA | DEL | SYN | UNH | Turco | done
2011-11-22 |  |  |  | TRR: FM1 SDP vibration (1 unit) | TRR |  |  | Macri | done
2011-11-28 | 2011-12-02 |  |  | FM3 DFG Sensor capacitor installation | ASSY | UCLA |  | Strangeway | done
2011-11-29 | 2011-12-01 |  |  | FM S/N2 EDI Sensor thermal test | ETST | UNH |  | Singer | done
2011-11-30 | 2011-12-02 |  |  | FM1 SDP vibration (1 unit) | ETST | UNH |  | Granoff | done
2011-11-30 |  |  |  | FM2 A-BEB PWAs | DEL | Iowa | UNH |  | done
2011-11-30 |  |  |  | PER: FM ship set 4 ADP booms (WebEx) | PER | LASP |  | Myers | done
2011-12-02 | 2011-12-05 |  |  | FM S/N3-4 CDPU thermal tests | ETST | UNH |  | Bodet | done
2011-12-02 |  |  |  | FM1 AEB return to UNH for repair | DEL | LASP | UNH | King | done
2011-12-03 |  |  |  | FM2 LVPS PWA | DEL | UNH | KTH | Turco | done
2011-12-05 |  |  |  | FM3 LVPS PWA | DEL | SYN | UNH | Turco | done
2011-12-05 |  |  |  | Burn 2nd FPGA for FM1 DSP | ASSY | UNH | LASP | Summers | done
2011-12-07 |  |  |  | Beam Gen Syst. weldments (in process inspection) Done for one set. Okay. Go-ahead for remainder given to vendor | MILE | UNH |  | Salwen | done
2011-12-08 | 2011-12-09 |  |  | FM SDP preamp TV survival cycle (3 units, S/N2-4) | ETST | UNH |  | Nolin | done
2011-12-08 |  |  |  | SDP preamp thermal model and test plan review | REV |  |  | Macri | done
2011-12-12 | 2011-12-16 |  |  | CDPU S/Ns 3&4 parylene coating | ASSY | SCS |  | Turco | done
2011-12-12 | 2011-12-16 |  |  | EDI Gun Support Collar wiring at UNH. | ASSY | Iowa | UNH |  | done
2011-12-14 | 2011-12-16 |  |  | SOC peer review and TIM | REV |  |  | Needell | done
2011-12-14 |  |  |  | FM1 AEBs (modified) to KTH for test | DEL | UNH | KTH | King | done
2011-12-14 |  |  |  | FM3 LVPS PWA | DEL | UNH | KTH | King | done
2011-12-20 |  |  |  | Mount thermal HW on FM1 CEB | ASSY | UNH |  | Nolin | done
2011-12-20 |  |  |  | FM1 AEB (tested) return to UNH | DEL | KTH | UNH | King | done
2011-12-20 |  |  |  | FM2 LVPS | DEL | KTH | UNH | King | done
2011-12-21 |  |  |  | FM1 GDE | DEL | RUAG | IWF | Steller | done
2012-01-03 |  |  |  | FM1 AEB (tested) return to LASP | DEL | UNH | LASP | King | done
2012-01-04 |  |  |  | FM4&FS LVPS PWAs | DEL | SYN | UNH | Turco | done
2012-01-05 | 2012-01-06 |  |  | SDP 2 - 4 Preamp TV Retest | ETST | UNH |  |  | done
2012-01-05 | 2012-01-18 |  |  | Syntech FM2 set SBEB assembly | ASSY | SYN |  | Turco | done
2012-01-05 |  |  |  | PER: FM3 FG Sensors (Webex) | PER | UCLA |  | Strangeway | done
2012-01-06 |  |  |  | FM1 DSP boards (return to UNH) | DEL | LASP | UNH | Wesfall | done
2012-01-09 |  |  |  | TRR: EQM SDP Vibration | TRR | UNH |  | Macri | done
2012-01-09 |  |  |  | PER: FM2/3 SCM (WebEx) | PER | LPP |  | Leroy | done
2012-01-10 | 2012-01-11 |  |  | IS SIR | SIR |  |  |  | done
2012-01-10 | 2012-01-11 |  |  | EQM SDP Vibe | ETST | UNH |  | Granoff | done
2012-01-10 |  |  |  | FM1 GDE secondary ground isolation problem | PROB | RUAG | IWF | Steller | done
2012-01-10 |  |  |  | TRR: FG3 vibration and thermal | TRR |  |  |  | done
2012-01-11 |  |  |  | Discussion of SDP damping test | REV | GSFC |  | Frost | done
2012-01-13 |  |  |  | TRR: FM SCM sets 2&3 environmental tests | TRR |  |  | Macri | done
2012-01-16 | 2012-02-24 |  |  | FM2 set SCM environmental tests | ETST | LPP |  | Leroy | done
2012-01-17 | 2012-01-20 |  |  | SDP S/N 1 and EQM vibration | ETST | UNH |  |  | done
2012-01-17 | 2012-01-20 |  |  | SDP FM SN2-4 Preamp/Sphere integration | ASSY | UNH |  | King | done
2012-01-17 |  |  |  | FM2 set SDP Preamps and 5-8 doors | DEL | LASP | UNH | Westfall | done
2012-01-17 |  |  |  | Prep FM2 set SDP preamps for TV test | ASSY |  |  | King | done
2012-01-18 | 2012-01-20 |  |  | TV test FM S/N5-8 SDP Preamps | ETST | UNH |  | King | done
2012-01-18 |  |  |  | EDI beam gen system weldments (remaining anode and focus units) | DEL | VEND | UNH | Salwen | done
2012-01-18 |  |  |  | PER: FM1 CEB (@UNH) | PER | UNH |  | Myers | done
2012-01-20 |  |  |  | FM2 S-BEB PWA | DEL | SYN | UNH | Turco | done
2012-01-20 |  |  |  | TRR: FM1 CEB vibration | TRR |  |  | Macri | done
2012-01-23 |  |  |  | PER: FM1 pair Receiving Elements (@LASP) | PER | LASP |  | Westfall | done
2012-01-25 | 2012-01-27 |  |  | FM1 CEB vibration | ETST | UNH |  | Nolin | done
2012-01-30 | 2012-03-15 |  |  | FM3 set SCM vibration | ETST | LPP |  | Leroy | Done.
2012-01-30 | 2012-03-15 |  |  | FM3 set SCM vibe | ETST | LPP |  | Leroy | done
2012-01-30 |  |  |  | TRR: FM1 set Receiving Elements vibration | TRR | LASP |  | Westfall | done
2012-01-31 |  |  |  | PER: FM1 AEB (WebEx) | PER | LASP |  | Westfall | done
2012-02-01 | 2012-02-03 |  |  | Baseline outgassing measurements for FM1 CEB | ETST | UNH |  | Turco | done
2012-02-01 | 2012-02-03 |  |  | FM1 set Receiving Elements vibration | ETST | LASP |  | Westfall | done
2012-02-03 |  |  |  | SDP deployment problem (update for project) | MTG | UNH |  | Macri | done
2012-02-03 |  |  |  | TRR: FM1 AEB vibration testing | TRR | LASP |  | Macri | done
2012-02-03 09:00 |  |  |  | TRR: FM1 CEB TV | TRR |  |  | Macri | done
2012-02-06 |  |  |  | FM1 AEB vibration testing | ETST | LASP |  | Westfall | done
2012-02-07 |  |  |  | FM3 DFG Sensor. Return 2nd tuning harness to UNH. | DEL | UCLA | UNH | Rowe | Done.
2012-02-09 | 2012-02-10 |  |  | SDP vibration investigation | ETST | UNH |  | Granoff | done
2012-02-10 |  |  |  | TRR: FM1 Receiving Element TV testing | TRR | LASP |  | Westfall | done
2012-02-11 | 2012-02-16 |  |  | Myers at IWF (schedule work) |  | UNH |  |  | done
2012-02-11 |  |  |  | FM3 DFG Sensor | DEL | UNH | IWF | Myers | done
2012-02-13 | 2012-03-01 |  |  | FM1 Receiving Element TV testing | ETST | LASP |  | Westfall | Done.
2012-02-17 | 2012-02-24 |  |  | FM2 SCM Preamp TV | ETST | LPP |  | Leroy | done
2012-02-17 |  |  |  | TRR: FM2 AFG/DFG Joint Calibration | TRR |  |  | Magnes | Done.
2012-02-21 |  |  |  | Deliveries to KTH: FM2 AEB (modified), FM2 set S-BEB (modified) PWAs, FM2 set SDP Preamp/Cable assemblies, and FM4 & FM5 LVPS. | DEL | UNH | KTH | King | Done.
2012-02-21 |  |  |  | SDP vibration investigation (radial clamp) | ETST | UNH |  | Granoff | Done.
2012-02-22 |  |  |  | TRR: FM1 CEB vibration (workmanship, 1 axis) | TRR | UNH |  | Macri | Done.
2012-02-23 |  |  |  | TRR: FM1 AEB TV Test | TRR | LASP |  | Westfall | Done.
2012-02-23 |  |  |  | FM1 CEB vibration (workmanship, 1 axis) | ETST | UNH |  | Nolin | Done.
2012-02-24 | 2012-03-01 |  |  | FM1 AEB TV Test | ETST | LASP |  | Westfall | done
2012-02-24 | 2012-03-08 |  |  | FM1 CEB TV | ETST | UNH |  | Rau | done
2012-02-24 |  |  |  | TRR: FM1 CEB TV | TRR | UNH |  | Macri | Done.
2012-02-24 |  |  |  | Submit GFY13 PPBE | DEL | UNH |  | Macri | done
2012-02-24 |  |  |  | Return EM4 SCM Sensor to UNH | DEL | GSFC | UNH | Sturm | done
2012-02-27 |  |  |  | SDP deployment problem (update for project) | REV | UNH |  | Granoff | done
2012-02-28 | 2012-03-09 |  |  | FM2 AFG/DFG Joint Calibration | ETST |  |  | Magnes | done
2012-02-29 |  |  |  | Update on ADP Boom plan forward | MTG | LASP |  | Westfall | done
2012-03-01 |  |  |  | ***CANCELLED***. EQM SDP delivery to GSFC for qual deck testing | DEL | UNH | GSFC | King | Done.
2012-03-05 | 2012-03-14 |  |  | FM1 AEB-RE calibration | TST | LASP |  | Ergun | done
2012-03-05 | 2012-03-15 |  |  | FM2 SCM Calibration | ETST | LPP |  | Leroy | done
2012-03-10 |  |  |  | Tested hardware delivery (FM2 AEB, Probes through BEBs S/Ns 5-8) | DEL | KTH | UNH | King | done
2012-03-12 |  |  |  | EDI Correlator (Xilinx) peer review | REV | UNH |  | Vaith | done
2012-03-14 |  |  |  | FRR: EDI GDU (internal review) | FRR | UNH |  | Turco | Done.
2012-03-14 |  |  |  | FRR: EDI GDU (internal review) | FRR | UNH |  | Turco | Done.
2012-03-16 | 2012-03-22 |  |  | Repeat SCM Preamp S/N4 TV test | ETST | LPP |  | Leroy | done
2012-03-16 | 2012-03-23 |  |  | Repeat SCM Preamp S/N4 (SCM SS#3) TV test | ETST | LPP |  | Leroy | done
2012-03-16 |  |  |  | FM1 AEB (and ADP simulators (2 channels)) Delivery | DEL | LASP | UNH | Westfall | done
2012-03-19 |  |  |  | FM2 CEB housing ready |  |  |  | Nolin | Done.
2012-03-20 | 2012-03-21 |  |  | MMS SWT (San Antonio) | MTG |  |  | Torbert | done
2012-03-20 | 2012-03-21 |  |  | MMS SWT (San Antonio) | MTG |  |  | Torbert | Done.
2012-03-20 |  |  |  | EM4 SCM Sensor delivery to LPP. Thermal test for verification following QM boom deploy (shock) test | DEL | UNH | LPP | Williams | done
2012-03-20 |  |  |  | SDP ship set #4 boom cables (and spares?) | DEL | UNH | LASP | Beckman | done
2012-03-21 |  |  |  | S/N3 EDI Beam Gen Syst | DEL | UNH | IWF | Vaith | done
2012-03-22 | 2012-03-23 |  |  | SDP prototype (SN1 w/ RWC) vibe | ETST | UNH |  | Granoff | done
2012-03-22 |  |  |  | MMS SWG |  |  |  | Torbert | done
2012-03-22 |  |  |  | TRR: FIELDS FM1 FIT (timing) testing | TRR | UNH |  | Macri | done
2012-03-22 |  |  |  | MMS SWG |  |  |  | Torbert | Done.
2012-03-22 |  |  |  | FM2 CEB housing assembly complete | DEL | UNH | UNH | Nolin | done
2012-03-22 15:00 |  |  |  | FIELDS data processing meeting (San Antonio) | MTG |  |  | Torbert | done
2012-03-22 15:00 |  |  |  | FIELDS data processing meeting (San Antonio) | MTG |  |  | Torbert | done
2012-03-23 |  |  |  | New over-shield material for SCM harnesses | DEL | UNH | LPP | Turco | done
2012-03-23 |  |  |  | FM2 AEB | DEL | UNH | LASP | Rau | done
2012-03-26 | 2012-03-28 |  |  | FIELDS FM1 FIT (part 1, magnetometer timing) testing. FM1 CEB, AFG, DFG, SCM | TST | UNH |  | Dors | done
2012-03-26 | 2012-05-25 |  |  | FM1 FIELDS I&T: CPT, FIT, procedure and script development | TST | UNH |  | Rau | done
2012-03-26 |  |  |  | FM2 AFG Delivery and acceptance test. | DEL | UCLA | UNH | Strangeway | done
2012-03-26 |  |  |  | TRR: FIELDS FM1 FIT test part 1 (magnetometer timing) | TRR | UNH |  | Macri | Done.
2012-03-27 | 2012-03-28 |  |  | SwRI PMs at UNH (schedule review) | MTG | UNH |  | Macri | done
2012-03-27 | 2012-03-30 |  |  | SDP prototype (SN1 w/ RWC) vibe | ETST | UNH |  | Granoff | Done.
2012-03-27 |  |  |  | FM2 DFG delivery and acceptance test | DEL | IWF | UNH | Valavanoglou | done
2012-03-29 |  |  |  | S/N3 & 4 EDI Beam Gen Syst | DEL | UNH | IWF | Valavanoglou | done
2012-03-29 |  |  |  | FM3 set A-BEB PWA | DEL | SYN | UNH | Turco | Done.
2012-04-03 | 2012-04-03 |  |  | Integrate first set EDI Optics (S/N2) with Sensor (S/N1) at UNH | ASSY | Iowa | UNH | Dvorsky | Done.
2012-04-05 | 2012-05-09 |  |  | EM4 SCM Sensor verification following QM boom deploy (shock) test | ETST | LPP |  | Alison | done.
2012-04-10 |  |  |  | Peer Review: SDP RWC mechanism | REV | UNH |  | Granoff | done
2012-04-11 | 2012-04-18 |  |  | SNs 3&4 EDI Sensor boards ready for bench testing | ASSY | UNH |  | Tyler | done
2012-04-11 |  |  |  | FM2 LVPS ready for CEB I&T (incoming functional test wth UNH GSE) | TST | UNH |  | Troop | done
2012-04-12 | 2012-04-20 |  |  | FM S/N2 EDI Gun & GDE (first unit). IWF support at UNH | ASSY | IWF | UNH | Steller | done
2012-04-12 | 2012-04-24 |  |  | FM SN2 GDU (1st unit) integration | ASSY | UNH |  | Vaith | done
2012-04-13 |  |  |  | FM1 and FM2 ship sets ADP booms (S/Ns 1-4) | DEL | ATK | LASP |  | done
2012-04-16 | 2012-04-24 |  |  | Parylene coating of FM2 CDPU A&B, AFG, DFG, EDI Controller | ASSY | UNH |  | Turco | done
2012-04-17 | 2012-04-19 |  |  | FM S/N2 GDU integration (Iowa support) | ASSY | Iowa |  | Bounds | Done.
2012-04-17 | 2012-05-15 |  |  | Revised random environment analyses for SDP | ANA | GSFC | UNH | Dirks | done
2012-04-17 | 2012-05-15 |  |  | Revised random environment analyses for EDI | ANA | GSFC | UNH | Dirks | done.
2012-04-19 | 2012-04-20 |  |  | FIELDS FM1 FIT testing (AEB timing) FM1:CEB, AEB | TST | UNH |  | Dors | done
2012-04-20 |  |  |  | Remaining Gun DFL2 PWBs | DEL | UNH | IWF | Steller | Done.
2012-04-20 |  |  |  | SDP preamp/cable assemblies (S/Ns 9-12) | DEL | LASP | UNH | Vermeer | done
2012-04-23 |  |  |  | Return EM AEB to LASP | DEL | UNH | LASP | Rau | Done.
2012-04-23 |  |  |  | Nulling Coil GSE. UCLA will send 2 with a SW update; return 1 to UCLA for addional coil turns. | DEL | UCLA | UNH | Strangeway | done
2012-04-24 |  |  |  | FM2 BPM ready for FM2 CEB | DEL | UNH |  | Bodet | done
2012-04-24 |  |  |  | STP file for AEB interface plate | DEL | LASP | SwRI | Tucker | done
2012-04-25 |  |  |  | TRR: S/N2 GDU bench test | TRR | UNH |  | Macri | done
2012-04-25 12:00 | 2012-04-26 |  |  | GDU SN2 bench test | TST | UNH |  | Vaith | done
2012-04-26 |  |  |  | FM2 CDPU (2) delivery to CEB | DEL | UNH | UNH | Turco | done
2012-04-26 |  |  |  | Discussion of ADP and SDP deployment test plans at Obs. | MTG |  |  | Pope | done
2012-04-26 |  |  |  | FM2 DFG Delivery to CEB | DEL | UNH | UNH | Turco | Done.
2012-04-30 | 2012-05-03 |  |  | FM2 SCM Harness outgassing certification | ETST | LPP |  | Alison | Done.
2012-04-30 |  |  |  | PER: FM2 set AEB and Receiving Elements | PER |  |  |  | Done.
2012-04-30 |  |  |  | TRR: FM2 set Receiving Elements vibration | TRR | LASP |  |  | done
2012-05-02 | 2012-05-04 |  |  | SDP S/N1 vibration (RWC on new outer cylinder) | VIB | UNH |  | Granoff | Done.
2012-05-03 |  |  |  | FM2 EDI Contrtoller Delivery to CEB | DEL | UNH | UNH | Turco | done
2012-05-03 |  |  |  | FM2 AFG Delivery to CEB | DEL | UNH | UNH | Turco | done
2012-05-07 | 2012-05-18 |  |  | FM3 DFG TU-BS calibration |  |  |  |  | Done.
2012-05-07 |  |  |  | S/N2 GDU FFT (room 145 chamber) | ETST |  |  | Singer | Done.
2012-05-07 |  |  |  | TRR: FM2 AEB TV test | TRR |  |  |  | done
2012-05-08 | 2012-05-16 |  |  | S/N2 GDU characterization (room 145 chamber) | ETST | UNH |  | Singer | Done.
2012-05-08 |  |  |  | TRR: S/N2 GDU vacuum test and characterization | TRR | UNH |  | Macri | done
2012-05-11 |  |  |  | SDP thermal test plan distribution | RFA |  |  | King | done.
2012-05-15 | 2012-05-24 |  |  | Repair of FTS (UNH TV) | TV |  |  | Ellis | done
2012-05-17 |  |  |  | Outer cylinders ready for SDP S/N3 integration | ASSY | UNH |  | Granoff | done
2012-05-17 |  |  |  | GDU SN2 test with FM1 CEB |  |  |  | Vaith | done.
2012-05-18 | 2012-05-24 |  |  | FM1 SCM harness bakeout and certification (new overshield). | TV | UNH |  | Turco | done
2012-05-18 | 2012-06-05 |  |  | Integration SN3 SDP | ASSY | UNH |  | Granoff | done.
2012-05-18 |  |  |  | FIELDS FM1 FIT testing (EDI timing). FM S/N2 EDI-GDU, EM CEB. | TST | UNH |  | Dors | done.
2012-05-18 |  |  |  | SDP RWC covers returned from vendor PFE | DEL | VEND | UNH | Granoff | done
2012-05-18 |  |  |  | SDP pins returned from vendor Tiodize | DEL | VEND | UNH | Granoff | done
2012-05-18 |  |  |  | SDP boom cable S/Ns 17-18 | DEL | UNH | LASP | Beckman | done
2012-05-18 |  |  |  | TRR: SN FM2 EDI GDU EMI/EMC Testing (1st unit). | TRR | UNH |  | Macri | done.
2012-05-21 | 2012-05-25 |  |  | SN FM2 EDI GDU EMI/EMC Testing (1st unit). | ETST |  |  | Dors | done
2012-05-21 |  |  |  | Fluxgate harness deliveries | DEL | UCLA | UNH |  | done.
2012-05-21 |  |  |  | PER: S/N2 EDI GDU (1st unit) | PER |  |  | Myers | done.
2012-05-22 | 2012-05-23 |  |  | PSR: FM1 FIELDS (partial) delivery to IS (includes all except EDI & SDP) | PSR | UNH |  | Myers | done
2012-05-22 |  |  |  | FM2 set DSP (2) Delivery | DEL | LASP | UNH | Westfall | done
2012-05-23 | 2012-05-24 |  |  | SDP Sphere/Preamp integration s/ns 3 and 4 and crimping outer guards with probes for 5 and 6. Vermeer support | ASSY | UNH |  | King | done.
2012-05-23 |  |  |  | Return SN1 Gun Support Collar to UNH | DEL | Iowa | UNH | Bounds | done
2012-05-23 |  |  |  | FM SDP Doors F/Ms 9-16 | DEL | LASP | UNH | Vermeer | done
2012-05-25 |  |  |  | Test FM1 AFG/DFG harnesses with FIELDS | TST | UNH |  | Rau | done.
2012-05-29 | 2012-06-01 |  |  | FM4 DFG Sensor Capacitor installation | ASSY |  |  | Valavanoglou | done.
2012-05-29 | 2012-06-05 |  |  | Return SN1 and SN3 EDI Gun BGS to UNH for filament swap and short investigation | DEL | IWF | UNH | Steller | done.
2012-05-29 | 2012-06-05 |  |  | TV survival test: SDP ship set 3 preamp/cable assemblies (S/Ns 9-12). | TV | UNH |  | King | done
2012-05-29 |  |  |  | TRR: EDI GDU SN2 Vibe | TRR |  |  |  | Done.
2012-05-29 |  |  |  | EM4 SCM Sensor return to UNH | DEL | LPP | UNH | Alison | Done.
2012-05-30 | 2012-05-31 |  |  | FM1 FIELDS (partial) Delivery to IS. FM1 CEB, DFG, AFG and SCM and Harnesses, SDPs: (SN1, FIT BEBs w/ motor and HOP load sims) ; | DEL | UNH |  | Rau | done
2012-05-30 | 2012-06-01 |  |  | S/N 2 EDI GDU Vibration Testing (1st unit) | VIB |  |  | Granoff | done
2012-05-31 | 2012-06-15 |  |  | FIELDS FM1 IS I&T (except SDP and GDU) | TST | UNH |  | Rau | done.
2012-06-04 | 2012-06-17 |  |  | Calibration: FM2 set RE & AEB | TST | LASP |  | Tucker | done
2012-06-04 |  |  |  | ADP Simulator and test harness for IS | DEL | LASP | UNH | Tucker | Done.
2012-06-06 |  |  |  | BGS S/N5 | DEL | UNH | IWF | Singer | done
2012-06-06 |  |  |  | TRR: S/N2 EDI GDU TV Testing | TRR |  |  | Macri | Done.
2012-06-07 | 2012-06-28 |  |  | S/N2 EDI GDU TV Testing | TV |  |  | Vaith | done
2012-06-07 |  |  |  | FM3 set S-BEB PWAs | DEL | SYN | UNH | Turco | Done.
2012-06-07 |  |  |  | FM2 DSP boards acceptance test | TST | UNH |  | Dors | done
2012-06-11 |  |  |  | Delta PER: SDP S/sN 3&4 (WebEx agreed) | PER | UNH |  | Myers | done
2012-06-11 |  |  |  | TRR: SDP S/N3 & 4 vibration | TRR | UNH |  | Granoff | done
2012-06-12 | 2012-06-15 |  |  | FM SDP SN3-4 Vibration Testing | VIB |  |  | Granoff | done
2012-06-12 |  |  |  | FM3 AEB | DEL | UNH | KTH | King | done
2012-06-15 |  |  |  | FM2 CEB mehanical assemby complete | ASSY | UNH |  | Nolin | done
2012-06-20 | 2012-06-21 |  |  | FM SDP S/N 3 EMI/EMC CE and magnetics test (@UNH) | ETST | UNH |  | Dors | Done.
2012-06-20 |  |  |  | FM2 AEB | DEL | LASP | UNH | Tucker | done
2012-06-20 |  |  |  | TRR: FM SDP S/Ns 3&4 EMI/EMC tests (@UNH) | TRR | UNH |  | Dors | done
2012-06-22 |  |  |  | FM4&5 AEB boards | DEL | SYN | UNH | Turco | done
2012-06-25 | 2012-06-26 |  |  | FM2 CEB 1st FFT | TST | UNH |  | Dors | done
2012-06-26 |  |  |  | PER: FM4 AFG/DFG Sensors | PER | UCLA |  | Strangeway | done
2012-06-26 |  |  |  | TRR: FM4 AFG/DFG Sensors (all env tests) | TRR | UCLA |  | Strangeway | done
2012-06-28 | 2012-06-29 |  |  | FM SDP S/N 4 EMI/EMC test (@UNH) | ETST | UNH |  | Dors | done
2012-06-28 |  |  |  | SDP TV test procedure for review. | REV |  |  | Beckman | done
2012-06-29 |  |  |  | Outgassing certification of SS#1 ADP booms | TST | LASP |  | Tucker | done
2012-06-29 |  |  |  | TRR: FM SDP SN3-4 TV Testing | TRR | UNH |  | Macri | done
2012-06-29 |  |  |  | AFG tuning harness | DEL | UNH | UCLA | Rau | done
2012-07-03 | 2012-07-20 |  |  | FM SDP SN3-4 TV Testing | TV | UNH |  | King | done
2012-07-09 |  |  |  | FIELDS ADP Simulator | DEL | LASP | UNH | Tucker | done
2012-07-09 |  |  |  | Fluxgate Sensor labels for bakeout | DEL | UCLA | SwRI | Strangeway | done.
2012-07-11 | 2012-07-12 |  |  | PER: FM2 CEB | PER | UNH |  | Myers | done.
2012-07-11 |  |  |  | TRR: FM2 CEB EMI/EMC CE testing @UNH | TRR | UNH |  | Dors | done
2012-07-13 | 2012-07-13 |  |  | FM2 CEB EMI/EMC CE testing @UNH | EMI | UNH |  | Dors | done
2012-07-16 | 2012-08-22 | CEB |  | FM3 set CDPU boards assembly | ASSY | UNH |  | Googins/Jones | done
2012-07-16 |  | CEB |  | TRR: CEB FM2 vibration | TRR | UNH |  | Macri | done
2012-07-17 | 2012-07-18 | CEB |  | CEB FM2 vibration | VIB | UNH |  | Nolin | done.
2012-07-23 | 2012-07-26 | FIELDS |  | Magnetometer acceptance testing at UNH ( AFG FM3 AT, DFG FM3 AT, SCM FM2 AT, SCM FM3 AT) | TST | UNH |  | Rau | done
2012-07-23 |  | AFG |  | FM3 AFG (and test harnesses) | DEL | UCLA | UNH | Rowe | done
2012-07-23 |  | DFG |  | FM4 DFG Sensor | DEL | UCLA | UNH | Rowe | done
2012-07-24 |  | DFG |  | FM3 DFG | DEL | IWF | UNH | Valavanoglou | done
2012-07-25 | 2012-07-26 | SCM |  | FM2 SCM (Sensor, Preamp and harness) and FM3 SCM (Sensor and Preamp only) | DEL | LPP | UNH | Leroy | done
2012-07-26 |  | DFG |  | FM4 DFG Sensor | DEL | UNH | IWF | Valavanoglou | done.
2012-07-27 | 2012-08-09 | CEB |  | FM2 CEB TV | TV | UNH |  | Rau | done
2012-07-27 |  | CEB |  | TRR: FM2 CEB TV | TRR | UNH |  | Macri | done
2012-07-30 | 2012-08-28 | SDP |  | S-BEB boards (SNs 13-18) assembly | ASSY | SYN |  | Turco | done
2012-07-31 | 2012-08-03 | EDI |  | Study Inductor placement on HV-FIL Bd SN5 |  | UNH |  | Turco | done
2012-07-31 |  | EDI |  | EDI GDU S/N2 Magnetics testing | TST | UNH |  | Dors | done.
2012-08-01 | 2012-08-03 | SDP |  | SDP SNs 5&6 FFT | TST | UNH |  | King | done
2012-08-02 | 2012-08-03 | SDP |  | SDP 3&4 FIT testing (with EM CEB) | TST | UNH |  | Dors | done
2012-08-07 |  | SDP |  | PER: SDP SNs 5&6 | PER |  |  | Myers | done
2012-08-07 |  | SDP |  | TRR: SDP SNs 5&6 Vibration | TRR | UNH |  | Macri | done
2012-08-07 |  | ADP |  | FM2 AEB acceptance test | TST | UNH |  | Rau | done.
2012-08-07 |  | AFG |  | 2 more AFG/DFG Nulling Coils | DEL-U | UCLA | UNH | Rowe | done
2012-08-08 | 2012-08-10 | EDI |  | SN1&3 BeamGenSys Disassembly&Inspection |  | UNH |  | Singer | done
2012-08-08 | 2012-08-10 | SDP |  | SDP SNs 5&6 Vibration | VIB | UNH |  | Granoff | done
2012-08-08 | 2012-08-22 | CEB |  | FM3 BPM assembly | ASSY | UNH |  | Googins | done
2012-08-08 |  | EDI |  | GDU SN2 Cleaning and Bagging for Shipment |  | UNH |  | Singer | done
2012-08-10 | 2012-08-24 | EDI |  | Sensor SN4 Board Parylening | ASSY | UNH |  | Singer | done.
2012-08-10 |  | SDP |  | FM9-12 SDP preamp /cables assemblies. FM9-12 SDP BEB. FM4-5 AEB. | DEL | UNH | KTH | King | done
2012-08-10 |  | ADP |  | FM4-5 AEB. | DEL | UNH | KTH | King | done
2012-08-12 |  | EDI |  | GDU S/N2 & SDP S/Ns 3&4 (EM CEB-SDP supports testing) | DEL-G | UNH | GSFC | Needell | done
2012-08-13 | 2012-08-14 | SDP |  | SDP S/N3&4 bench test, inspection, I&T | PDS | UNH |  | Needell | done
2012-08-13 | 2012-08-17 | IS |  | GDU SN2 bench test, inspection integration with IS#1 | PDS | UNH |  | Vaith | done
2012-08-13 | 2012-08-20 | SDP |  | SDP SN5-6 EMI/EMC testing | EMI | UNH |  | Dors | done
2012-08-13 | 2012-08-24 | FIELDS |  | FM2 FIELDS I&T and Magnetometer FIT (CEB, AEB, SCM, Mags, SDP 5/6, SDP01/QM) | TST | UNH |  | Rau | done
2012-08-17 |  | CEB |  | FM3-5 LVPS | DEL-U | KTH | UNH | King | done
2012-08-17 |  | ADP |  | FM3 AEB | DEL-U | KTH | UNH | King | done
2012-08-17 |  | SDP |  | 5 SDP Probes (C1, C2, D1, D2, D4) | DEL-U | KTH | UNH | King | done
2012-08-20 | 2012-10-10 | ADP |  | FM4-5 AEB testing | TST | KTH |  | King | done
2012-08-21 |  | AFG |  | FM2 Fluxgate Harnesses | DEL-U | UCLA | UNH |  | done.
2012-08-21 |  | ADP |  | FM3 AEB | DEL | UNH | LASP | King | done.
2012-08-22 | 2012-08-23 | SDP |  | SDP SNs 5&6 Penalty Vibration (microswitch issue) | VIB | UNH |  | Granoff | done
2012-08-22 | 2012-09-13 | CEB |  | FM3 set CDPU boards testing & final assembly | TST | UNH |  | Bodet/ Googins | done
2012-08-22 | 2012-09-21 | CEB |  | FM3 EDI Controller board testing & final assembly | TST | UNH |  | Gaidos/ Googins | done
2012-08-22 |  | FIELDS |  | FM2 AEB FIT | TST | UNH |  | Dors | done
2012-08-23 |  | FIELDS |  | TRR: IS#1 CPT | TRR | SwRI |  | Henry | done
2012-08-24 | 2012-08-30 | EDI |  | Sensor SN3 MCP module assembly | ASSY | UNH |  | Granoff/Singer | done
2012-08-24 |  | AFG |  | fluxgate harness segment material (10 ft., no connectors) for GSFC | DEL | UCLA | GSFC | Strangeway | done.
2012-08-24 |  | SDP |  | TRR: FM SDP SN5&6 TV Testing | TRR | UNH |  | Macri | done
2012-08-24 17:00 | 2012-09-07 | SDP |  | FM SDP SN5&6 TV Testing | TV | UNH |  | King | done
2012-08-27 | 2012-08-30 | PM |  | Mission SIR | MTG | GSFC |  | Torbert/Macri | done.
2012-08-27 | 2012-08-31 | EDI |  | Sensor SN3 final assy/staking w/o MCP module | ASSY | UNH |  | Granoff/Singer | done
2012-08-27 | 2012-08-31 | EDI |  | Sensor SN3 assembly with MCP module | ASSY | UNH |  | Granoff/Singer | done
2012-08-28 | 2012-08-29 | SDP |  | SDP SN1 and QM BEB (for IS#1 CPT) | DEL-G | UNH | GSFC | Rau/King | done.
2012-08-29 | 2012-10-05 | SDP |  | S-BEB boards (SNs 13-16) complete assembly | ASSY | UNH |  | Googins | done
2012-08-29 |  | CEB |  | FM2 CEB EMI/EMC Magnetics testing | EMI | UNH |  | Dors | done.
2012-08-30 | 2012-08-31 | SDP |  | SDP SN1 and QM BEB I&T (for IS#1 CPT) | PDS | UNH | GSFC | Rau/Needell | done
2012-09-04 | 2012-09-06 | ADP |  | QM ADP Boom and Receiving Element delivery to GSFC | DEL-G | LASP | GSFC | Tucker/ Henry | done
2012-09-05 | 2012-09-12 | IS |  | IS#1 CPT (with FIELDS Support @GSFC) | PDS | UNH |  | Rau/Needell | done
2012-09-05 |  | ADP |  | ADP Simulator and test harness for S/C | DEL | LASP | UNH | Tucker | done
2012-09-07 |  | ADP |  | PER: FM3 set ADP RE and AEB [chair: Dirks] | PER | LASP |  | Tucker | done
2012-09-08 |  | FIELDS |  | Mount thermistors on FM2 set AEB and SCM Preamp | ASSY | UNH |  | Salwen / Nolin | done
2012-09-10 |  | FIELDS |  | PSR (WebEx): FM2 FIELDS (partial) delivery to IS (includes all except EDI & SDP) [chair: Stone] | PSR | UNH |  | Myers | done
2012-09-11 | 2012-09-13 | Sci |  | MMS SWT @GSFC | MTG |  | GSFC | Torbert | done
2012-09-11 | 2012-09-14 | EDI |  | SN1 Sensor/Optics pre-integration | ASSY | Iowa |  | Dvorsky | done
2012-09-11 |  | EDI |  | Shipment of GDE/Gun SN1 | DEL-U | IWF | UNH | Steller | done
2012-09-11 |  | FIELDS |  | Current Generator return to IWF (Carnet expires end of Sep) | DEL | UNH | IWF | Chutter | done
2012-09-12 | 2012-09-14 | Sci |  | MMS SDWT & Data Processing TIM (Riesberg) @GSFC | MTG |  | GSFC | Torbert/ Chutter | done
2012-09-13 | 2012-09-19 | EDI |  | GDU SN1 Assembly | ASSY | UNH |  | Granoff | done
2012-09-13 |  | SDP |  | SDP SN5-6 Magnetics testing | EMI | UNH |  | Dors/ King | done
2012-09-13 |  | DFG |  | Return current generator to IWF | DEL | UNH | IWF | Magnes | done
2012-09-17 | 2012-09-20 | ADP |  | Integration of QM ADP Boom and Receiving Element on qual S/C deck | PDS | LASP |  | Tucker/ Mack | done
2012-09-17 | 2012-09-28 | FIELDS |  | FM2 FIELDS (partial) I&T (incl SDP SN1 and QM BEB) | PDS | UNH |  | Bodet/ Dors (Needell untill 22 Sep) | done
2012-09-17 |  | SCM |  | PER: FM4 set SCM [chair: Dirks] | PER | LPP |  | Alison | done
2012-09-17 |  | FIELDS |  | FM2 FIELDS (partial) delivery/I&T | DEL-G | UNH | GSFC | Dors/ Bodet | done
2012-09-18 | 2012-09-28 | IS |  | IS#1 burst and FDC tests | PDS | UNH |  | Needell | done
2012-09-19 | 2012-09-21 | SDP |  | SDP 7-10 probe to preamp assembly and remaining preamp cable deliveries | ASSY |  |  | King | done
2012-09-19 |  | CEB |  | FM1 CEB CDPUA C-RAM test on IS#1 (NCR investigation) | TST | UNH |  | Bodet/ Needell | done
2012-09-19 |  | SDP |  | SDP preamp/cable assemblies (S/Ns 13-16) | DEL-U | LASP | UNH | Tucker | done
2012-09-19 |  | SDP |  | SDP preamp/cable assemblies (S/Ns 17-18) | DEL-U | LASP | UNH | Tucker | done
2012-09-19 |  | SDP |  | SDP Doors SN17 - SN18 | DEL-U | LASP | UNH | Tucker | done
2012-09-19 |  | EDI |  | 20 HV Opto-Couplers for partial discharge testing | DEL-U | IWF | UNH | Steller | done
2012-09-21 | 2012-09-26 | EDI |  | GDU SN1 Baseline Vacuum FFT | VAC | UNH |  | Vaith | done
2012-09-21 |  | EDI |  | BGS S/N 6&8. | DEL | UNH | IWF | Myers/ Steller | done.
2012-09-21 |  | EDI |  | SN5&6 HV&FIL board | DEL | UNH | IWF | Myers/ Steller | done.
2012-09-24 | 2012-10-31 | EDI |  | 20 HVOCs partial discharge tests (round 1) | TST | UNH |  | Widholm | underway
2012-09-26 |  | EDI |  | SNs 5&6 Sensor Digital board kits to Iowa | DEL | UNH | Iowa | Turco | done.
2012-09-27 | 2012-10-08 | CEB |  | Stake and coat FM3 set CDPU, EDI Controlller, DFG, AFG boards | ASSY | UNH |  | Turco/ Specialty Coatings | done.
2012-09-27 |  | FIELDS |  | IS#1 Acceptance Review with Project (Part-1, mechanical) | REV | UNH |  | Macri/ Rau | done
2012-09-27 |  | FIELDS |  | TRR: Obs. Risk Reduction EMI/EMC Test (Obs) | TRR | GSFC |  | Won/ Dors/ Rau | done
2012-09-28 | 2012-10-02 | EDI |  | Sensor SN3 Vacuum Test | VAC | UNH |  | Singer | done
2012-09-28 |  | EDI |  | GDU SN1 PER [Chair: Stone] | PER | UNH |  | Myers/ Vaith, Steller | done.
2012-10-01 |  | EDI | 3 | Sensor SN3 Electrical Test | TST | UNH |  | Singer | done.
2012-10-02 | 2012-10-04 | SDP |  | SDP preamp workmanship (SNs 13-16) | TV | UNH |  | King/ Troop, Frost | done.
2012-10-03 |  | EDI | 1 | GDU SN1 EMI test | EMI | UNH |  | Dors/ Vaith | done
2012-10-03 |  | EDI | 1 | TRR: GDU SN1 vibration test | TRR | UNH |  | Granoff/ Macri | done
2012-10-04 |  | SDP |  | PSR (IIRT @UNH): FM1 set SDP (4 units) (SNs 3, 4, 5, &6) [chair: Phan] | PSR | UNH |  | Myers | done
2012-10-08 | 2012-10-11 | DFG |  | FM4 DFG calibration @ TU-BS | TST | IWF |  | Magnes | done
2012-10-08 | 2012-10-19 | SCM |  | TQCM measurement FM3 SCM harness | TST | LPP |  |  | done. Unsuccessful
2012-10-09 | 2012-10-11 | EDI |  | GDU SN1 vibration | VIB | UNH |  | Granoff | done
2012-10-10 |  | FIELDS |  | FM2 FIELDS trend data | REV | UNH | SwRI | Rau | Open work from PSR
2012-10-10 |  | SDP |  | S-BEB boards (SNs 13-16), preamp/cable assemblies (13-16). | DEL | UNH | KTH | King | done
2012-10-11 |  | EDI |  | TRR GDU SN1 TV | TRR | UNH |  | Myers/ Vaith | done
2012-10-12 | 2012-10-26 | EDI |  | GDU SN1 TV | TV | UNH |  | Vaith | done
2012-10-12 |  |  |  | Mag harness integration on S/C#1 | PDS |  |  | Rau | done
2012-10-15 | 2012-10-19 | ADP |  | Qual deck vibe testing (LASP support remotely) | PDS | LASP |  | Tucker | done
2012-10-15 | 2012-10-24 | CEB |  | FM3 CEB assembly | ASSY | UNH |  | Rau/ Nolin | done
2012-10-16 |  | SDP |  | PER: SDP SNs 7&8 [chair: Dirks] | PER | UNH |  | Myers | done.
2012-10-17 | 2012-10-19 | SDP |  | SDP 7 & 8 Vibe | VIB | UNH |  | Granoff | done
2012-10-17 |  | DSP |  | FM3 set DSP boards (SNs 5&11) | DEL-U | LASP | UNH | Tucker | done
2012-10-18 | 2012-10-19 | ADP |  | Fit check ADP Booms and REs (ship sets 1&2) | TST | LASP |  | Tucker | done
2012-10-18 |  | SDP |  | AEB 4&5, probes (SNs13, 15, 16), S-BEBs (SNs 9-11), preamps/cable assemblies (SNs 9-12) | DEL-U | KTH | UNH | King | done
2012-10-22 | 2012-11-05 | ADP |  | Ship Set 3 ADP Receiving Elements TV | TST | LASP |  | Tucker | done
2012-10-22 | 2012-11-08 | EDI |  | 20 HVOCs partial discharge tests (round 1) | TST | UNH |  | Widholm | done
2012-10-22 |  | EDI |  | Sensor SN4 final assy/staking w/o MCP module | ASSY | UNH |  | Singer/ Granoff | done.
2012-10-23 | 2012-10-24 | EDI |  | Sensor SN4 assembly with MCP module | ASSY | UNH |  | Granoff/ Singer | done
2012-10-23 |  | ADP |  | FM3 AEB | DEL-U | LASP | UNH | Tucker | done
2012-10-23 |  | FIELDS |  | IS#1 Acceptance Review with Project (Part-2) | REV | UNH |  | Macri/ Rau, Needell, Chutter | done
2012-10-25 |  | FIELDS |  | SCM Preamp install on S/C#1 | PDS |  |  | Rau | done
2012-10-25 |  | CEB |  | FM3 CEB FFT | TST | UNH |  | Rau | done
2012-10-25 |  | ADP |  | FM4 AEB. Use the shipping containers that need to go back to LASP. | DEL | UNH | LASP | King | done
2012-10-25 |  | SCM |  | PER: SCM FM Preamp Spare. Send data to UNH. | PER | LPP |  | Alison / Macri | done
2012-10-25 |  | SDP |  | SDP7-8 emi/emc test | EMI | UNH |  | Dors | done
2012-10-25 |  | SDP |  | TRR: SDP SN7&8 TV Testing | TRR | UNH |  | Macri/ King | done
2012-10-26 | 2012-11-27 | SDP |  | SDP SN7&8 TV Testing | TV | UNH |  | King | done
2012-10-26 |  | ADP |  | PER: Ship Set 4 ADP Receiving Elements | PER | LASP |  | Tucker | done
2012-10-27 |  | SDP |  | SDP SNs 5&6 delivery to IS#2 | DEL-G | UNH | GSFC | Bodet | done
2012-10-29 |  | SCM |  | FM3 SCM Harness to UNH for bakeout and certif. | DEL-U | LPP | UNH |  | done
2012-10-29 |  | CEB |  | FM3 CEB PER | PER | UNH |  | Myers | done
2012-10-31 | 2012-10-31 | FIELDS |  | Mag Boom harness fit checks | PDS | UNH |  | Rau | done.
2012-10-29 | 2012-12-20 | SDP | 9, 10 | SDP SNs 9&10 assembly | ASSY | UNH |  | King | done.
2012-10-31 | 2012-11-01 | SDP |  | SDP SNs 5&6 I&T w/ IS#2 | PDS | UNH |  | Rau/ Bodet | done
2012-10-31 | 2012-11-01 | ADP |  | Post vibe test first motion deployment, QM boom and RE | PDS | LASP |  | Tucker | done.
2012-10-31 | 2012-11-09 | EDI |  | SN3 GDU I&T (Iowa support, 31 Oct-2 Nov) | ASSY | UNH |  | Granoff/ Singer, Steller, Vaith | done.
2012-10-31 |  | CEB |  | TRR: FM3 CEB Vibration Test | TRR | UNH |  | Macri | done
2012-11-01 | 2012-11-02 | CEB |  | FM3 CEB Vibration Test | VIB | UNH |  | Rau/ Nolin | done
2012-11-01 |  | EDI |  | Shipment of GDE/Gun SN3 | DEL-U | IWF | UNH | Steller/ Myers | done
2012-11-05 | 2012-11-06 | EDI | 1 | GDU SN1 magnetics testing | EMI | UNH |  | Dors | done
2012-11-05 | 2012-11-07 | FIELDS |  | Observatory #1 CIDP to Observatory electrical integration | PDS | UNH |  |  | done
2012-11-05 | 2012-11-07 | FIELDS | 1 | GDU SN1 FIT (timing - using EM-Full CEB) | TST | UNH |  | Dors/ Vaith | done
2012-11-05 | 2012-11-09 | EDI |  | Sensor SN4 Vacuum Test | VAC | UNH |  | Singer | done
2012-11-05 |  | EDI |  | Sensor SN4 Electrical Test | TST | UNH |  | Singer | done
2012-11-06 | 2012-11-13 | SCM |  | FM4 PA TVAC | TST | LPP |  | Alison | done
2012-11-08 |  | EDI |  | 20 HVOCs return to IWF | DEL | UNH | IWF | Steller | done
2012-11-09 |  | EDI |  | Acceptance Review (telephone): GDUs (SN 1) at UNH | PSR (AR) | UNH |  | Vaith/ Myers | done
2012-11-13 |  | EDI |  | Clean and inspect SN1 GDU for delivery | CLEAN | UNH |  | Turco | done
2012-11-14 |  | EDI |  | SN1 GDU to IS#2 | DEL-G | UNH | GSFC |  | done
2012-11-14 |  | ADP |  | PER: FM4 AEB | PER |  |  | Tucker | done
2012-11-15 | 2012-11-19 | EDI |  | GDU SN1 I&T with IS#2 @ GSFC | PDS | UNH |  | Vaith/ Needell | done
2012-11-15 | 2012-11-19 | FIELDS |  | Tests with ADP simulator (Obs-1) | PDS | UNH |  | Rau | done
2012-11-20 |  | EDI |  | GDU SN3 PER [chair: Stone] | PER | UNH |  |  | done
2012-11-26 | 2012-11-30 | FIELDS |  | Observatory #1 FFT | PDS | UNH |  | Needell/ Chutter, Rau | done
2012-11-26 |  | EDI |  | FRB: SN4 Gun | FRB |  |  | IWF/UNH | done
2012-11-27 | 2012-11-28 | EDI | 3 | SN3 GDU vibration | VIB | UNH |  | Granoff/ Singer, Dors | done
2012-11-28 | 2012-11-29 | SCM |  | FM3 SCM Harness Bake Out | TV | UNH |  | Turco | done
2012-11-28 | 2012-12-04 | FIELDS |  | IS#2 CPT | PDS | UNH |  | Needell/ Chutter | done
2012-11-29 | 2012-12-14 | FIELDS |  | SDP deployments (without wires), operational scenario. SN1 and QM BEB. | PDS | UNH |  | Needell | done
2012-11-30 | 2012-12-10 | EDI | 3 | GDU SN3 T/V Test | TV | UNH |  | Vaith | done
2012-12-04 | 2012-12-05 |  |  | IS#2 Burst and FDC tests | PDS | UNH |  | Remote | done
2012-12-04 | 2012-12-07 | FIELDS |  | Obs-1 deck prep for EMI test | PDS | UNH |  | Rau | done
2012-12-04 | 2013-01-04 | EDI |  | SNs 7, 8 & 9 Sensor Digital boards - partial assembly | ASSY | Iowa |  | Bounds/ Kutcher | done.
2012-12-04 |  | AFG |  | FM3 set fluxgate harness delivery | DEL-U | UCLA | UNH | Strangeway | done
2012-12-06 |  | SDP | 7, 8 | SDP 7 & 8 EMI & magnetics test | EMI | UNH |  | Dors | done
2012-12-07 | 2012-12-10 | FIELDS |  | IS2 delivery to S/C | PDS | UNH |  | Rau | done
2012-12-08 | 2012-12-10 | FIELDS |  | Move IS2 to Obs for delivery | PDS | UNH |  | Rau at GSFC | done
2012-12-10 | 2012-12-14 | SCM |  | Calibration FM4 set | TST | LPP |  | Alison | done
2012-12-10 | 2012-12-18 | S/C |  | Observatory-1 Risk Reduction EMI test | PDS | UNH |  | Dors/ Needell | done
2012-12-11 | 2012-12-12 | DFG |  | FM4 DFG | DEL-U | IWF | UNH | Magnes | done
2012-12-11 | 2012-12-12 | AFG |  | FM4 AFG | DEL-U | UCLA | UNH | Rowe | done
2012-12-11 | 2012-12-13 | SDP |  | SDP 7&8 penalty TV test | TV | UNH |  | King | done
2012-12-11 |  | FIELDS |  | Current Generator return to UNH | DEL | IWF | UNH | Magnes | done
2012-12-12 | 2012-12-20 | FIELDS |  | SOC real-time telemetry flow test | TST | SOC |  | Mello | done
2012-12-13 |  | EDI |  | FRB: SN3 GDU fold-backs and comm locks | FRB | UNH |  |  | done
2012-12-13 |  | SDP |  | Clean and inspect SDP SN 7&8 for delivery | CLEAN | UNH |  | Turco | done
2012-12-14 | 2013-01-07 | CEB |  | FM3 CEB TV | TV | UNH |  | Rau | done
2012-12-14 |  | SDP |  | PSR (acceptance review): SDP SNs 7&8 | PSR (AR) | UNH |  | King | done
2012-12-16 | 2012-12-21 | MAG |  | OBS 1 Mag boom installation | PDS | UNH |  | Rau | done
2012-12-17 |  | SDP | 7, 8 | SDP SNs 7&8 delivery | DEL-G | UNH | GSFC | Rau | done
2012-12-19 | 2012-12-21 | SDP | 7, 8 | SDP SNs 7&8 S2M with IS#(2) @ GSFC | PDS | UNH |  |  | done
2012-12-19 |  | SDP |  | Remove SDP SN1 and EQM from Obs-1, return to UNH | PDS | UNH |  | Rau | done
2013-01-02 | 2013-01-04 | ADP |  | Ship sets 1&2 ADP Booms and REs | DEL-G | LASP | GSFC |  | done
2013-01-03 |  | ADP |  | FM5 AEB: Rework screws and self locking helicoils | DEL-U | UNH |  | King/ Tucker | done.
2013-01-07 | 2013-01-08 | EDI |  | SN4 GDU pre-integration (Iowa support) | ASSY | Iowa | UNH | Granoff | done
2013-01-07 | 2013-01-09 | EDI |  | SN4 Optics - delivery and integratin with sensor | DEL-U | Iowa | UNH | Dvorsky | done
2013-01-07 | 2013-01-11 | FIELDS |  | Install FM1 mag HW on booms | PDS | UNH |  | Rau/ Rowe | done
2013-01-07 | 2013-01-11 | SDP |  | SDP SN01: TV EMI investigation | TV | UNH |  | King/ Olsson | done
2013-01-07 | 2013-01-21 | FIELDS |  | FM3 FIELDS I&T | TST | UNH |  | Dors | done
2013-01-07 |  | SDP |  | S-BEB SN12 investigation | TST | UNH |  | King/ Olsson | done
2013-01-07 |  | SDP |  | FRB: SDP SN10 motor failure | FRB | UNH |  | Turco | done
2013-01-08 | 2013-01-11 | ADP |  | Integrate the -Z ADP Boom and ADP RE Launch Latches on observatory #1 | PDS | LASP |  | Tucker | done
2013-01-08 | 2013-01-11 | SDP | 7, 8 | SDP SNs 7&8 I&T with IS#(2) @ GSFC | PDS | UNH |  | Rau/ Needell | done
2013-01-10 | 2013-01-11 | SDP | 9, 10 | SDP SNs 9&10 EMI/EMC | EMI | UNH |  | Dors | done
2013-01-11 | 2013-01-14 | SCM |  | 48 hr bake out SS#3 SCM preamp and sensor (+50C w/ TQCM) | TV | UNH |  | Turco | done
2013-01-11 |  | SDP |  | PER: SDP 9 & 10 (Chair: Dirks) | PER | UNH |  | King | done
2013-01-14 | 2013-01-18 | MAINT |  | TV chamber maintenance | TV | UNH |  | Turco | done.
2013-01-14 |  | ADP |  | RE vibe (2 units SS4) | TST | LASP |  | Tucker | done
2013-01-15 |  | FIELDS |  | FM3 FIELDS CPT | TST | UNH |  | Dors | done
2013-01-16 | 2013-01-17 | SDP |  | SDP 9 & 10 Vibe | VIB | UNH |  | Frost/ Beckman | done
2013-01-16 | 2013-01-18 | FIELDS |  | FM3 FIELDS (partial). Clean and inspect. | CLEAN | UNH |  | Turco | done
2013-01-16 |  | EDI |  | NCR discussion (IIRT) |  |  |  | Vaith / Macri, Turco | done
2013-01-17 |  | EDI |  | PSR: GDU SN 1 at UNH (IIRT) | PSR | UNH |  | Vaith/ Myers | done
2013-01-18 |  | FIELDS |  | PSR: FM3 FIELDS (Chair: Stone) | PSR | UNH |  | Myers | done
2013-01-21 | 2013-02-04 | SDP | 9, 10 | SDP 9 & 10 TV test | TV | UNH |  | King | done
2013-01-22 | 2013-01-22 | SDP |  | Return SDP EQM and FIT BEB to GSFC | DEL-G | UNH |  |  | done
2013-01-22 | 2013-01-25 | FIELDS | Obs-2 | Observatory #2 FFT | PDS | UNH |  | Needell | done
2013-01-22 | 2013-01-30 | FIELDS |  | FM3 FIELDS I&T | PDS | UNH |  | Rau/ Needell | done
2013-01-22 |  | FIELDS |  | FM3 FIELDS (partial) | DEL-G | UNH | GSFC | Rau | done
2013-01-24 | 2013-01-25 | FIELDS |  | Mag boom#1 integration on Obs-1 | ASSY | UNH |  | Rau | done
2013-01-29 |  | SDP |  | FRB: SDP 10 gear box jam | FRB | UNH |  | King/ Granoff, Turco | done
2013-01-30 |  | ADP |  | FRB: open RE launch latch SN08 | FRB | LASP |  | Tucker | done